## Mandatory milestones
Project Milestones as outlined in the ToR
1. Development phase - Milestones to be achieved by Kick-Off Workshop
Milestones
1.1 Presentation and documentation of solution and adaptation requirements
1.2 Agreed Pilot Plan
1.3 Agreed project KPIs
2. Implementation phase (solution deployement) - Milestones to be achieved by Mid-Term Workshop
Milestones
2.1 Installation/Integration of solution successfully completed
2.2 Assessment of KPIs
2.3 Presentation of implementation (numbers deployed, identified impact)
3. Results of pilot available and pilot successfully competed - Milestones to be achieved by Final Workshop
Milestones
3.1 Solution successfully operated and maintained
3.2 Presentation of results for dissemination
4. Support with dissemination of pilot results
Milestones
4.1 Results have been disseminated to prospective users

## Pricing schedule Form Template
Instructions for completing the financial offer:
1. The financial offer is primarily based on business day usage. Successful bidders must attend the three mandatory workshops, and can attend the complementary offer of support on demand and as needed and as agreed upon at the kick-off meeting. Time invested in attending these meetings and offers of support cannot be factored into the proposal budget by bidders, as the goal is to help them successfully pilot their solution.
The financial offer must be completed as in the example:
| Cost Category (staff, travel, licenses, external consultants, hosting, production costs, license fees, etc) |  | Expected Outcome | Achieved by when? | Unit (number of days) | Amount (quantity needed) | Unit price in ZAR including VAR | Amount in ZAR including VAR
Description of activities to achieve milestone
Development phase (6 months)
1. Milestone 1
1.1 Presentation and documentation of solution and of adaptation requirements | IT Developer | Adaptation of the mobile application to suit the public implementing partner's needs | Mobile application is ready to be integrated | 1st Month of the Program | 5 days | 1 | XZAR | 1* X ZAR
2. Travel costs should be budgeted for however, it should be noted that the maximum value of the contract for each project cannot exceed ZAR 800,000 (including travel expenses).
3. Cost Category costs, e.g. staff, travel, licenses, external consultants, for hosting, production costs, license fees, etc. must be listed individually.
4. Reminder on Milestones and payment – bidders can propose individual budgets and timelines, but should be aware of the project's payment plan as outlined in the ToR (25% of contract value at kick-off,…..) bidders must list the milestones (mandatory and additional) here.
5. The mandatory milestones should be achieved and should be included in own planning - bidders must provide descriptions of how milestones will be achieved here. Bidders can include additional milestone to cater the needs of the solution
6. The financial offer will be evaluated according to the two criteria set out below.
F.1 How is the relation between the impact (point B of technical evaluation) and the financial offer?
(This criterion is evaluated at 20 points given its importance)
0 Points | 8 Points | 16 Points | 20 Points
The impact outlined under point B is in no relation to the budget proposed. The impact is too low in terms of budget proposed. | The impact outlined under point B makes it questionable if the proposed budget is adequate to achieve only the impact proposed | The impact outlined under point B justifies partially the proposed budget, which is slightly too high for the impact achieved. | The impact outlined under point B justifies the proposed budget to launch the solution.
F.2 Is the solution financially feasible?
0 Points | 4 Points | 8 Points | 10 Points
It is not realistic that the company will be able to introduce the solution with the foreseen budget. | It is only realistic that the company will be able to introduce a partial solution with the foreseen budget. | It is realistic that the company will be able to introduce the solution almost to its full potential with the budget foreseen. | It is realistic that the company will be able to introduce the solution with the budget foreseen.
Name of Company:
Financial offer
| Cost Category (staff, travel, licenses, external consultants, hosting, production costs, license fees, etc.) | Description of activities to achieve milestone | Expected Outcome | Achieved by when? | Unit (number of days) | Amount (Quantity needed) | Unit price in ZAR including VAT | Amount in ZAR including VAT
Development phase - Milestones to be achieved by Kick-Off Workshop
Milestones
0
0
0
0
Total amount for phase | [7 empty] | 0
Implementation phase (solution deployment) - Milestones to be achieved by Mid-Term Workshop
Milestones
0
0
0
Total amount for phase | [7 empty] | 0
Results of pilot available and pilot successfully completed - Milestones to be achieved by Final Workshop
Milestones
0
0
0
0
Total amount for phase | [7 empty] | 0
Support with dissemination of pilot results
Milestones
0
0
0
0
Total amount for phase | [7 empty] | 0
TOTAL AMOUNT | [7 empty] | 0