| MERL support for partners implementing the Presidential Youth Employment Intervention (PYEI) | Project number/ cost centre: 20.2210.1-001.00 |
| --- | --- |

0.	List of abbreviations	2

1.	Context	3

Project description	3

Problem analysis	3

Project approach	3

2.	Tasks to be performed by the contractor	3

3.	Eligibility Criteria	5

4.	Concept	5

Technical-methodological concept	5

Project management of the contractor (1.6)	5

5.	Personnel concept	6

Team leader	6

Key expert 1	6

Short-term expert pool with minimum 2, maximum 4 members	7

6.	Costing requirements	8

Assignment of personnel and travel expenses	8

Sustainability aspects for travel	8

Workshops and training	9

Payment	9

7.	Inputs of GIZ or other actors	9

8.	Requirements on the format of the tender	10

9.	Outsourced processing of personal data	10

10.	Option	10

11.	Annexes	10

# List of abbreviations

AuV		    Auftragsverarbeitungsvereinbarung

Outsourcing of data processing

BMZ	German Federal Ministry for Economic Cooperation and Development

GDPR	Regulation (EU) 2016/679 (General Data Protection Regulation)

GTCC	General Terms and Conditions of Contract (GTCC) for supplying services and work 2022

MERL	Monitoring, Evaluation, Reflection and Learning

PMO	Project Management Office

PYEI	Presidential Youth Employment Intervention

S2PYEI	Support to the Presidential Youth Employment Intervention

ToRs	Terms of reference

# Context

## Project description

On behalf of the German Federal Ministry for Economic Cooperation and Development (BMZ), the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH implements the project “Support to the Presidential Youth Employment Intervention (S2PYEI)”. The project supports the Programme Management Office (PMO) at the Presidency of the Republic of South Africa in the coordination and implementation of the PYEI.

In doing so, the programme works along two main strains of activity:

(1) Supporting the PMO in coordinating the PYEI and developing its governance structures and

(2) Strengthening the capacities of PYEI implementing organisations.

## Problem analysis

South Africa is currently the country with the highest official unemployment rate in the world. Young people in particular struggle to enter the labour market – a development which has been further exacerbated by the COVID-19 pandemic. Those young people who do manage to access opportunities tend to zigzag on broken pathways, falling in and out of education and short-term work so that they are unable to realise their potential and gain a foothold in the economy. As a result, the unemployment crisis continues to deepen, and youth unemployment is at its highest level in over a decade.

In response to this challenge, the President of the Republic of South Africa has established the Presidential Youth Employment Intervention (PYEI). To measure the impact of the PYEI, a sophisticated system for Monitoring and Evaluation, Reporting and Learning (MERL) has been developed. In order to implement this system effectively, key staff in government departments and organisations involved in the implementation of the PYEI require the capacity and skills to collect, analyse and report data on their interventions in line with the requirements.

## Project approach

S2PYEI supports the Presidency in the coordination and implementation of the PYEI and strengthens the capacities of PYEI implementing organisations. S2PYEI therefore seeks to strengthen the MERL capacities of staff in selected governmental and civil society organisations in the context of the PYEI.

# Tasks to be performed by the contractor

The contractor is responsible for providing the following services to around 20 organisations including government departments and implementing organisations (government, private sector, non-profit entities):

- Identify the capacity in each of the selected partner organisations to implement the aspects of the PYEI MERL framework that are relevant to them

- Develop measures to enhance the capacities of key staff within each organisation that will enable them to meet the MERL requirements (e.g. training, coaching),

- Advise the organisations throughout the process on setting up their M&E system in line with PYEI reporting requirements.

- Reviewing of data to ensure it meets Data Quality Assessment standards.

- Assess the current indicators collected by the departments and assess whether they line up with PYEI indicators.

- Support organizations and departments to process the data for reporting into the PYEI MERL framework.

- Support organizations with determining baselines against PYEI indicators.

In a kick-off meeting, S2PYEI and the Presidency will brief the contractor on the organisations to be supported and the MERL requirements of the PYEI. Relevant documents on the PYEI M&E system will be made available to the contractor.

The contractor will draft a brief inception report outlining the skills required of PYEI implementers in order to contribute to the PYEI MERL system.

S2PYEI will then establish contact between the contractor and the participating organisations. The contractor will independently assess the organisations to identify their current capacities. On this basis, they will then develop measures to enhance their capacities and enhance these to meet the standard required to effectively implement the PYEI MERL requirements.

The capacity development will go hand in hand with advisory support for the organisations in reporting on the PYEI indicators.

Throughout the implementation of the contract, the contractor will hold monthly meetings with S2PYEI and the Presidency to discuss the progress of the activities. The contractor will also submit their assessment of the skills level of the organisations to S2PYEI in writing, as well as a proposal for the capacity development measures.

The final report will contain details on all activities undertaken as part of the contract, including the results and any capacity needs that were identified during implementation that were not addressed. The latter will inform programming of future activities of S2PYEI.

Certain milestones, as laid out in the table below, are to be achieved by certain dates during the contract term:

|  | Milestone | Deadline/place/person responsible |
| --- | --- | --- |
| 1 | Inception report (max. 5 pages) | 1 week after start of the contract |
| 2 | Report on assessment of the level of skills and knowledge | 3 days after assessment with an organisation |
| 3 | Assessment of available data, reporting structures and data processing (only applicable for 1-5 organisations) | 2 weeks after the organisation made the data available |
| 4 | Proposal for capacity development measures | 5 days after milestones 1 and/or 2 respectively |
| 5 | Implementation of capacity development measures | After approval of the proposal by GIZ |
| 6 | Support with baselining of PYEI indicators (if applicable) | 01 February 2024 |
| 7 | Support with quarter one reporting | As of 01 March 2024 |
| 8 | Close-out report | By 31 March 2024 |

Period of assignment: From 16 October 2023 until 31 March 2024.

# Eligibility Criteria

The bidder should fulfil following minimum eligibility criteria:

- Commercial register entry

- Average annual turnover for the last three financial years of at least R 2,000,000

- Average number of employees and managers for the past three calendar years: At least 2 persons

- The bidder must also provide examples of two (2) projects in the field consulting in the area MERL in South Africa with a minimum commission value of R 200,000 in the past 3 years through a brief description of the project, the dates and who the services were provided for.

# Concept

In the tender, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail. (1.6.1)

- The contractor is responsible for selecting, preparing, training and steering the international and national, short and long-term experts assigned to perform the advisory tasks.

- The contractor provides equipment and supplies (consumables) and assumes the associated operating and administrative costs.

- The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ.

The contractor reports regularly to GIZ in accordance with the current AVB of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

# Personnel concept

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 7), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): University degree (Master) in Monitoring and Evaluation, Development Studies or Economics

- Language (2.1.2): C1-level language proficiency in English according to the Common European Framework of Reference for Languages (CEFRL)

- General professional experience (2.1.3): 8 years of professional experience in the evaluation and research sector

- Specific professional experience (2.1.4): 5 years of professional experience in employment promotion.

- Leadership/management experience (2.1.5): 6 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 5 years of experience in projects in South Africa

## Key expert 1

Tasks of key expert 1

- Assist the team leader with the overall project design and implementation, e.g. by development of data collection tools, data analysis and reporting, ensuring data quality and ensuring data is managed in line with data protection guidelines and ethical research standards.

- Oversee the development and implementation of capacity development measures to enhance the knowledge and skill of key staff in the benefitting organisations.

Qualifications of key expert 1

- Education/training (2.2.1): University qualification (Master) in Monitoring and Evaluation, Development Studies, Social Sciences or Economics

- Language (2.2.2): C1 -level language proficiency in English according to the Common European Framework of Reference for Languages (CEFRL)

- General professional experience (2.2.3): 5 years of professional experience in the Evaluation and research sector

- Specific professional experience (2.2.4): 3 years of professional experience in employment promotion.

- Regional experience (2.2.6): 2 years of experience in projects in South Africa

- Development Cooperation (DC) experience (2.2.7): None

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

## Short-term expert pool with minimum 2, maximum 4 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 7 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- Analyse the skills level within the beneficiary organisations.

- Develop and implement measure to enhance MERL capacities of key staff in line with what is required for MERL under the PYEI (training, coaching)

- Support the organisations in meeting their MERL obligations under the PYEI (advisory support)

Qualifications of the short-term expert pool

- Education/training (2.6.1): All experts with university qualification (Honours degree or above) in Monitoring and Evaluation, Development Studies, Social Sciences or Economics

- Language (2.6.2): All experts with C1-level language proficiency in English according to the Common European Framework of Reference for Languages (CEFRL)

- General professional experience (2.6.3): All experts with 5 years of experience in the evaluation and research sector

- Specific professional experience (2.6.4): All experts with at least 1 year of experience in the context of employment promotion

- Regional experience (2.6.5): All experts with at least 2 years of experience in South Africa

- Development Cooperation (DC) experience (2.6.6): None

- Other (2.6.7): None

The tenderer must provide a clear overview of all proposed short-term experts and their individual qualifications.

# Costing requirements

## Assignment of personnel and travel expenses

For travel costs the maximum rates for per diems, accommodation, flight costs etc. can be taken from the table below.

All business travel must be agreed in advance by the officer responsible for the project.

## Sustainability aspects for travel

GIZ would like to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

If they cannot be avoided, CO2 emissions caused by air travel should be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

There are many different providers in the market for emissions certificates, and they have different climate impact ambitions. The Development and Climate Alliance (German only) has published a list of standards (German only). GIZ recommends using the standards specified there.

Specification of inputs

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Designation of TL | 1 | 50 | 50 |  |
| Designation of key expert | 1 | 50 | 50 |  |
| Designation of short-term expert pool | 4 | 40 | 160 |  |
| Travel expenses | Quantity | Price | Total | Comments |
| Per-diem allowance in country of assignment | 160 |  |  |  |
| Overnight allowance in country of assignment | 120 |  |  |  |
| Transport | Quantity | Price | Total | Comments |
| Domestic flights | 30 |  |  | Return flights within the country of assignment during service delivery |
| CO2 compensation for air travel. | 30 |  |  | A budget is earmarked for settling carbon offsets against evidence. |
| Other travel expenses | 40 |  |  | e.g., travel by car/ taxi, toll fees |
| Other costs | Number | Price | Total | Comments |
| Workshops | 1 | R 50 000 | R 50 000 | Fixed budget. Can be invoiced to GIZ against evidence. |

## Workshops and training

Workshop budget: ZAR 50,000

The fixed, unalterable budget given above is specified in the price schedule for workshops. The budget includes the following costs relating to the planning and running of workshops:

- Room hire

- Technical systems

- Catering

- Workshop materials

- Other costs relating to the workshops

Wherever possible, the participating organisations shall cover these above items as their contribution to the joint activities. The workshop budget indicated above is to cover costs for such items where the organisation is unable to provide them.

Please describe in your concept how you implement GIZ’s minimum standards for sustainable event management (see annexes to the terms of reference).

## Payment

After the submission of the inception report (milestone 1), the contractor will submit an invoice for an advance payment of 25% of the total contract volume. Thereafter, the contractor will submit invoices on a quarterly basis for the work performed in the respective quarter. The advance will be offset against the payment of the first quarterly invoice. The contractor will use timesheets to account for the performance.

# Inputs of GIZ or other actors

GIZ is expected to make the following available:

- This activity is complimentary to support GIZ is providing to strengthen MS Excel skills in the context of MERL. Some of the beneficiaries of this contract may also be beneficiaries of the MS Excel training.

# Requirements on the format of the tender

The structure of the tender must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The tender must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English.

The complete tender must not exceed 5 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 5 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long.

# Please calculate your financial tender based exactly on the parameters specified in Chapter 5 Quantitative requirements. The contractor is not contractually entitled to use up the days, trips, workshops or budgets in full. The number of days, trips and workshops and the budgets will be contractually agreed as maximum limits. The specifications for pricing are defined in the price schedule

# Other Requirements

- Please submit your proposal (technical and price proposal) in separate files/folder to ZA_Quotation@giz.de  no later than 29th September 2023 all documents must be in PDF.

- Submission to any other email address may invalidate your bid.

- Please do not mention any price for this measure on your cover letter/Technical proposal.

- Please submit your tax clearance certificate with the bidding documents.

- Please submit your price proposal in ZAR.

- Our General Terms of Conditions (attached) shall not be changed/amended should you be the winner of this tender. These General Terms and Conditions will form part of the contract should you be awarded this contract. By submitting your proposal, we will conclude that you have read and accepted these terms and conditions.

- Participating more than once in same tender is not allowed and it will lead to your proposal as well as that of the company where you appear more than once being disqualified. The responsibility rests with the companies to ensure that their partners/experts are not bidding/participating more than once in same tender.

- Bidders are not allowed to communicate directly with any other person regarding this bid other than the procurement official/s. Failure to comply with this requirement may lead to your bid being disqualified.

- Bidders must strictly avoid conflicts with other assignments or their own interests. Bidders found to have a conflict of interest shall be disqualified. Without limitation on the generality of the above, Bidders, and any of their affiliates, shall be considered to have a conflict of interest with one or more parties in this EOI and tender process, if they:

- are or have been associated in the past, with a firm or any of its affiliates which have been engaged by GIZ or the Interim Supply Chain Management Council to provide services for the preparation of the design, specifications, Terms of Reference, cost analysis/estimation, and other documents to be used for the procurement of the services in this selection process;

- were involved in the preparation and/or design of the programme/project related to the services requested under this EOI and tender;

- are serving or have been serving in the past three months in the structures of the Interim Supply Chain Management; or

- are found to be in conflict for any other reason, as may be established by, or at the discretion of GIZ.

Scientific data

In the event of any uncertainty in the interpretation of a potential conflict of interest, Bidders must disclose to GIZ, and seek GIZ’s confirmation on whether or not such a conflict exists.

- Similarly, the Bidders must disclose in their proposal their knowledge of the following:

- if the owners, part-owners, officers, directors, controlling shareholders, of the bidding entity or key personnel are family members of GIZ staff involved in the procurement functions and/or the Interim SCM Council or any Implementing partner receiving services under this EOI or tender; and

- all other circumstances that could potentially lead to actual or perceived conflict of interest, collusion or unfair competition practices.

- Failure to disclose such an information may result in the rejection of the proposal or proposals affected by the non-disclosure.

- Bids sent via Dropbox and WeTransfer will not be accepted.

# Outsourced processing of personal data

Personal data will be processed on behalf of the client. Therefore, an agreement on “Outsourcing of data processing (AuV)” will be concluded with the contractor in accordance with Art. 28 EU Regulation 2016/679 on General Data Protection Regulation (GDPR). For this purpose, the technical and organizational measures (TOM) for compliance with the data protection requirements must be outlined prior to conclusion of the contract. If the contractor has already been audited by GIZ in the past, an update in accordance with GDPR must nevertheless be sent. After a positive check, the contract is concluded with the AuV attachment.

# Option

The duration of the contract may be extended by six (6) months at no cost. The extension of the contract period is dependent on the extension of the commission of S2PYEI by the commissioning party BMZ.

# Annexes

- Agreement on outsourcing of data processing (AuV)