| Engineering Consultant services for CHPP – Planning services | Project number/ cost centre: 23.1821.0-003.00 / G-012241-003 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

GIZ-SUR	GIZ Project: Strengthening Urban Resilience

CHPP		Combined Heat and Power Plant

IHP		Individual Heating Point

- Context

The Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH is a German federal enterprise. GIZ supports the Federal German Government in achieving its objectives in the field of international cooperation for sustainable development. GIZ operates in more than 130 countries around the globe. In Ukraine, GIZ has been working for more than 30 years.

Since the beginning of the Russian Federation's war of aggression on Ukraine in February 2022, 8.1 million Ukrainians are in neighbouring European countries and more than 5.3 million people have fled within Ukraine (source: UN Refugee Agency for UNHCR, April 2023). Large parts of the civilian infrastructure have been destroyed. In addition to the destruction of housing, the critical supply infrastructure (heat, gas, electricity, water, sewage, mobile telephony, internet) is a direct target of attacks. The situation in Ukraine remains volatile, with the frontline continuing to run through the eastern and southern parts of the country.

The utilities infrastructure and the housing sector are two of the sectors most affected by destruction, with deficiencies directly affecting people's lives. The estimated total physical damage to buildings and infrastructure is over 135 billion USD (source: Ukraine Rapid Damage Needs Assessment March 2025).

The Bundestag Budget Committee has approved a winter package from the BMZ for the heat and electricity supply in Ukraine. The BMZ will use the additional funds to provide Ukrainian cities and municipalities with smaller combined heat and power plants, boilers, generators and solar systems. This should help to ensure that people in Ukraine can live in their homes and withstand the Russian attacks. This is because Russia is deliberately attacking Ukraine's civilian energy infrastructure in order to destroy the Ukrainian economy and defence force and drive the people out in winter.

The additional support from the BMZ totalling 70 million euros is intended to help protect the people of Ukraine from the consequences of these attacks. The rapid expansion of decentralised and flexible energy generation with the help of smaller combined heat and power plants, boilers, generators and solar systems can prevent the worst consequences in affected cities and communities. Community centres, hospitals, schools and other social facilities will thus have a more secure and independent energy supply.

The purpose of this task is that Contractor to provide services for the preparation and coordination of planning services related to thermomechanical and electrical connections.

Brief description of current status of implementation of delivered CHPs to the city of Chernihiv

The city of Chernihiv was selected as one of the recipients of the above explained German support. In detail this materialized in the provision of one CHP “Avus 500plus NG | ct70-B-1” from the manufacturer 2G. Due to a lack of budget funds and the necessary experience in the management and implementation of planning of CHPs, the decision was made to support the city of Chernihiv in this task.

The contract resulting from this tender is intended to provide - the preparation of all necessary planning services, coordination of the planning results with all relevant stakeholders required for implementation.

- Tasks to be performed by the contractor

The contractor resumes the responsibility for the mentioned services and management of all related activities during its assignment in close cooperation with the Construction Advisor from GIZ-SUR and Authorized Representative of the Partner. In this capacity the contractor prepares all required documents and ensures efficiency and compliance of all the task activities under this ToR. The contractor ensures that the duties assigned, and all related tasks, are handled in the context of an overall technically and economically appropriate result within the time constraints. The services (tasks and work results) to be provided by the contractor are described here.

  - Tasks

The contractor is responsible for providing the following services:

- Preparation of the necessary planning services for engineering surveys, architectural and construction solutions, gas supply, thermo-mechanical and electrical connections, and organization of the construction in accordance with the applicable Ukrainian norms and standards (see Annex 1, 2 and 3) and the manufacturer's instructions for the respective CHPP (2G Annex 4 and 5).

- Coordination and approval of planning services with all relevant stakeholders.

- Implementation of the necessary measures to pass the expertise of design and estimate documentation and obtain a positive expert opinion.

- Provide consultation and support of the Partner on using Portal of the Unified State Electronic System in the field of construction (Register of construction activities).

- Prepare Bill of Quantities regarding the final planning decisions, according to the Annex 8 of the ToR

- Support for the GIZ Project in evaluating the proposals and preparing adjustments to the contract with the construction contractor (if necessary).

- Author supervision during execution of construction and installation works, including all required checks for quality of works and monitoring of executed quantities as well as examination of invoices in the qualitative and quantitative area.

- Since the Partner is the customer as per the law of Ukraine, the additional agreement between the Contractor and the Partner (the customer) may be needed to comply the existing norms of Article 11 of the Law on the law on architectural activity.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Preparation of the initial data | 03.04.2026 (12 workdays) |
| Implementation of all planning activities | 10.06.2026 (36 workdays) |
| Support on stage of tendering of construction companies | 10.06.2026 (5 workdays) |
| Passing the expertise and handover planning documents | 15.07.2026 (12 workdays) |
| Consultation on using Register of construction activities | 16.10.2026 (15 workdays) |
| Carrying out the author's supervision of construction | 16.10.2026 (20 workdays) |

The contract duration is from 16.03.2026 till 15.11.2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Preparation of the initial data | - Report in DOCX format - Copies of all initial data documents in PDF format - Obtaining approval and confirmation of initial data by the Chernihiv City Council and/or other key stakeholders - Timesheet | 03.04.2026 |
| Support on stage of tendering of construction companies | - Report in DOCX/Excel format (if any) - Timesheet | 10.06.2026 |
| Implementation of all planning activities | - Report in DOCX format - Completed planning documents in PDF format have been shared with the Project and Executive Committee of Chernihiv City Council - Timesheet | 10.06.2026 |
| Passing the expertise and handover planning documents | - Approved and stamped by a certified independent expert organization planning documents have been shared with the Project and Executive Committee of Chernihiv City Council - Timesheet | 15.07.2026 |
| Consultation on using Register of construction activities | - Report in DOCX format (if any) - Timesheet | 16.10.2026 |
| Carrying out the author's supervision of construction | - Report in DOCX format - Author supervision journal - PDF drawings (if any) - Timesheet | 16.10.2026 |

In addition to the reports required by GIZ in accordance with the AVB, the contractor submits the following reports:

  - Weekly reports on the implementation status of planning services in accordance with the reporting format in Annex 6)

## Codes and standards

All activities carried out by the Contractor shall follow Ukrainian norms (DBN, DSTU, DNAOP, etc.) relevant for installation and operation of CHPs (including, but not limited to the legislation acts and norms, mentioned in Annexes 1.

## License and property rights

Copyright of all documents prepared under this assignment shall remain with GIZ.

GIZ shall be entitled to use them or copy for any purpose and does not need to obtain the contractor's permission to copy for such use.

- Reports to be delivered in editable word-form and pdf in the English and the Ukrainian languages.

- Digital files should contain date and be named in English.

- The number of the Paper copies:(according to the Annex1).

- All information exchange must be sent only to e-mail addresses with the domain name.surname@giz.de

- attachments and graphic materials should be sent to:

up to 30 MB - by mail or via file transfer	https://filetransfer.giz.de

more than 30 MB - via file transfer		https://filetransfer.giz.de

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ Project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

## Further requirements (1.7)

The bidder should have experience in designing the installation of the CHP units in Ukraine, particularly 2G Energy manufacturer, which should be confirmed by letters from the customers/recipients and, preferably, by an official letter from the manufacturer.

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

## The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

## Team leader

Tasks of the Team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

- Handling of all required administrative procedures in cooperation with GIZ

- Support Project on stage of tendering of construction companies

- General support of GIZ-SUR on request

Qualifications of the Team leader

- Education/training (2.1.1): university degree (Master) in fields of electrical engineering, energy management, energy saving technologies, renewable energy or relatable/relevant fields

- Language (2.1.2.) - B2-level language proficiency in English

- Language – Ukrainian - native

- General professional experience (2.1.3): 10 years of professional experience in the engineering sector

- Specific professional experience (2.1.4): 5 years in complex projects in the energy sector

- Leadership/management experience (2.1.5): 10 years of management/leadership experience as project team leader, branch manager, chief engineer, chief design engineer or construction company manager

Regional experience (2.1.6): 5 years of experience in projects in Ukraine (country) resulting familiarity with Ukrainian legislation in the fields of construction and other laws relevant for these ToR.

## Key expert 1 – Chief design engineer

Tasks of the Chief engineer of the project

- Provide assistance to the Partner with preparation the initial data materials

- Consultation the Partner on using Register of construction activities

- Support Project on stage of tendering of construction companies

- Provide assistance to the Partner with passing the expertise of the design

- Conducting all necessary measures in supporting design, support of the Team Leader in his area of responsibility. Other tasks will be defined by team leader

- Carrying out the author's supervision of construction

Qualifications of key expert 1

- Education/training (2.2.1): university degree (Master) in fields of electrical engineering, energy management, energy saving technologies, renewable energy or relatable/relevant fields.

- Language (2.2.2): C2-level language proficiency in Ukrainian

- General professional experience (2.2.3): 10 years of professional experience in the engineering sector

- Specific professional experience (2.2.4): 5 years in complex projects in the energy sector including installation of the CHP units

- Regional experience (2.2.6): 5 years of experience in projects in Ukraine (country) resulting familiarity with Ukrainian legislation in the fields of construction and other laws relevant for these ToR

- Other (2.2.8): An actual qualification certificate of a design engineer must be present

## Key expert 2 – Thermal and mechanical design engineer

Tasks of the Thermal and mechanical design engineer

- Conducting all necessary measures in supporting design, supporting the Team Leader and the Chief design engineer in their area of responsibility. Other tasks will be defined by the Chief design engineer

- Carrying out the author's supervision of construction

Qualifications of key expert 2

- Education/training (2.3.1): university degree (Master/Bachelor) in fields of thermal and mechanical engineering, electrical engineering, energy management, energy saving technologies, renewable energy or relatable/relevant fields.

- Language (2.3.2): C2-level language proficiency in Ukrainian

- General professional experience (2.3.3): 10 years of professional experience in the thermal and mechanical engineering sector

- Specific professional experience (2.3.4): 5 years in complex projects in the energy sector including installation of the CHP units

- Regional experience (2.3.6): 5 years of experience in projects in Ukraine (country) resulting familiarity with Ukrainian legislation in the fields of construction and other laws relevant for these ToR

## Key expert 3 – Electrical design engineer

Tasks of the Electrical design engineer

- Conducting all necessary measures in supporting design, supporting the Team Leader and the Chief design engineer in their area of responsibility. Other tasks will be defined by the Chief design engineer

- Carrying out the author's supervision of construction

Qualifications of key expert 3

- Education/training (2.4.1): university degree (Master/Bachelor) in fields of thermal and mechanical engineering, electrical engineering, energy management, energy saving technologies, renewable energy or relatable/relevant fields.

- Language (2.4.2): C2-level language proficiency in Ukrainian

- General professional experience (2.4.3): 10 years of professional experience in the electrical engineering sector

- Specific professional experience (2.4.4): 5 years in complex projects in the energy sector including installation of the CHP units

- Regional experience: 5 years of experience in projects in Ukraine (country) resulting familiarity with Ukrainian legislation in the fields of construction and other laws relevant for these ToR

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Efficient, partner- and client-focused working methods

# Costing (quantitative) requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference, the following travel regulations and reporting documents are to be observed. See Annex 7 to these Terms of References.

Specification of inputs for contracts for services:

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of Team Leader | day | 1 | 65 | Performed works are tracked by evidence in the form of the timesheet. |
| Designation of Key expert 1 | day | 1 | 100 | Performed works are tracked by evidence in the form of the timesheet. |
| Designation of Key expert 2 | day | 1 | 75 | Performed works are tracked by evidence in the form of the timesheet. |
| Designation of Key expert 3 | day | 1 | 75 | Performed works are tracked by evidence in the form of the timesheet. |
| Travel expenses | Unit of measurement | Quantity | Budget [UAH] | Comments (if any) |
| Fixed travel budget | - | 1 | 200 000 | A fixed budget of UAH 200 000 is earmarked for settling travel expenses against evidence/performance. This amount includes accommodation, per diems, travel costs (train, compensation for own transport 15,38 UAH/km, taxi, bus)., Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. |
| Other costs | Unit of measurement | Quantity | Budget [UAH] | Comments (if any) |
| Procurement of GAS design services from Chernihiv branch of LLC Hazorozpodilni Merezhi of Ukraine | - | 1 | 130 000 | A budget of 130 000 UAH contains the costs of contracting Chernihiv branch of LLC Hazorozpodilni Merezhi of Ukraine for required design services under the responsibility of the monopolist. |

## There are no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors – not applicable

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the bid.

Anticipated payment schedule:

In consideration of works completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting |
| --- | --- | --- | --- |
| 1 Interim payment | 17.04.2026 | 15 % | Acc. to cl. 2.2 |
| 2 Interim payment | 24.06.2026 | 45 % | Acc. to cl. 2.2 |
| 3 Interim payment | 29.07.2026 | 15 % | Acc. to cl. 2.2 |
| 4 Final payment | 30.10.2026 | 25 % | Acc. to cl. 2.2 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, incl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance and timesheets, service entry sheet (LERF)  etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- In order to reimburse the costs of concluding a contract with Chernihiv branch of LLC Hazorozpodilni Merezhi of Ukraine for the implementation of necessary design works under the responsibility of the monopolist, it is necessary to provide documents confirming the costs incurred, such as concluded contracts, payment invoices, act of service provided/delivery notes.

- Each invoice and act of acceptance shall contain the Project Number, contract number

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link  Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _________________________

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

The Tenderer/ Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption – not applicable

# Outsourced processing of personal data – not applicable

# Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- tentative work plan;

- CVs of all experts with relevant work experience, qualifications (education, certificates)

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 5 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the Tenderer

Shall be provided according to the requirements of tender documentation.

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| Confirmation of previous installation of CHP | Provide a reference list of projects implemented over the last 5 years: at least 3 projects implemented on installation of the CHP and provide a self-declaration or any other evidence |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Annexes

- Annex 1	Scope of planning 2G avus 500plus NG | ct70-B-1

- Annex 2	Specifications avus 500plus NG | ct70-B-1

- Annex 3	P&ID_ avus 500plus NG

- Annex 4	Drawings avus 500plus NG

- Annex 5	Drawings avus 500plus NG

- Annex 6	Reporting form

- Annex 7	Travel regulations

- Annex 8	Bill of Quantities

- Annex 9	Technical Conditions of the Gas Grid Operator

Annex 7 Travel regulations (hereinafter – Regulations)

1.Business trips of experts/consultants All experts/consultants who are travelling on behalf of and commissioned by GIZ should use these Travel regulations for calculation and compensation of costs if these costs are stipulated in the Contract. For the claim of travel expenses, the experts/consultants must submit documents according to the terms of the Regulations, unless otherwise is expressly stated in the Contract. Compensation of travel expenses is carried out exclusively within the limits of the amounts for individual items fixed in the Contract. Payment of advances for business trips is possible only if it is expressly stated in the Contract.

2. Definition of a business trip A business trip, as defined by the GIZ’ general regulations governing the reimbursement of travel expense and accommodation, involves an expert/consultant temporarily working at a place other than his/her regular domicile and/or seat of business to conduct official business with GIZ's approval. The duration of a business trip (period of absence) shall be calculated as the time between departure from the place of residence or the principal place of work at the start of the business trip and the return to any of the above-mentioned places on completion of the business trip.

3. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – act of acceptance. Against evidance – copy of the original invoice from the hotel or other actual service provider with period of stay, names of guests, type and number of rooms, price per night, total amount, meals (if included). (Service fee of booking platforms is not to be reimbursed).

4. Per diem allowance The per-diem allowance covers the additional cost of subsistence to the expert/consultant during an assignment away from their regular domicile and/or seat of business and accrued if the condition of a one-day or more business trip is fulfilled. The minimum business trip time is a one-day business trip lasting 10 hours, including working hours and travel time. Per diems are paid within the amount specified in the Contract, as a lump sum. The reduced lump sum rate applies for one-day business trips lasting from 10 to 24 hours and depending on the type of meals at the hotel or the provision of meals from GIZ. The calculation of per diems for business trips depending on the type of meals is given in the Table 1 (see below). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – timesheets in accordance with GIZ limits Against evidence – not applicable

5. Currency of reimbursement of travel expenses Reimbursements of costs of business trips within Ukraine are paid in Ukrainian Hryvnia (UAH). Reimbursements of costs of international business trips are paid in Ukrainian Hryvnia (UAH). Reimbursement of travel expenses in foreign currency (not UAH) must be made according to below mentioned: a) in accordance with the exchange rate that is indicated in bank account statement (for cashless transactions). b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued (for cash transactions when no bank statement is available for confirmation of the used exchange rate). c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates/ (on the date when the financial documents (proof of evidence) were issued)). (In case that invoiced foreign currency is not available at the European Commission site).

6. Flights / ground transportation (train, taxi, private vehicles, car hire/car-sharing/) Costs for transportation are reimbursed within the amount specified in the Contract, against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). The preferred mode of transport shall be economically efficient and environmentally friendly. GIZ is committed to the principles of resource conservation and environmental protection and therefore requires all partners to choose the most environmentally friendly means of transport. Experts/consultants shall take advantage of any price reductions (special rates etc.) that are available. If travel time by train is 5 hours or less, train transport must be preferred for economic and environmental reasons

7.1 Flights Only economy class flight tickets can be reimbursed to experts/consultants. The choice of an airline company should be based on a comparison of ticket prices. The choice of a more expensive flight should be justified by an expert/consultant (e.g. a tight travel schedule combined only with the selected flight). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.2 Trains Train tickets shall be booked and purchased by the expert/consultant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.3 Taxis and group private transportation If the expert/consultant uses a taxi or a group private transportation during a business trip, abroad or in Ukraine, he\she should follow the principle of economic efficiency and necessity of usage this mean of transport. The justification for such a choice should be provided together with a financial document (proof of evidence). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - Taxi (not applicable); Group private transportation (route sheet with indication point of destination/point of arrival overall km). Against evidance – Taxi (bill or ride report or screenshot of order with price indication); Group private transportation (invoice from the actual service provider).

7.4 Private vehicles As a rule, business trips should be made by rail rather than using a private vehicle. Compensation for usage of private vehicles is allowed if such a category of costs is stipulated in the Contract. In the case of using private vehicles, GIZ compensates for such costs at a fixed rate per kilometre, using the shortest possible route (according to the calculation of the Google Maps navigator). For journeys with a one-way distance of more than 200 km, the expert/consultant must provide evidence that using a motor vehicle is more economical than other means of transport. The basis for reimbursement and for determining which means of transport is more economical is the cost of a second-class rail ticket. If a private motor vehicle is used for other important reasons (e.g. to carry heavy luggage, documents or materials, or if local transport connections are poor), convincing and adequate reasons must be set out by the expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - needs evidence by internal based calculation of route planner like Google-map or similar (15,38 UAH per 1 km which includes all expenses without exception, such as fuel etc.) Against evidance - not applicable

7.5 Buses Bus tickets must be booked and purchased independently by an expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication

Table 1 / Таблиця 1

The calculation of per diems for business trips per Travel Day