| Development of Sustainable Energy and Climate Action Plan (SECAP) for Cities Kremenchuk, Boyarka | Project number/ cost centre: 21.9025.4-012 / G-011989-012 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

BEI	Baseline Emission Inventory

CRVA	Climate Risk and Vulnerability Assessment

CO2	Carbon dioxide

CoM 	Covenant of Mayors

EaP	Eastern Partnership

EU	European Union

EU4ClimateResilience	Decarbonization and Climate Resilience in the European Union’s Eastern Partnership

IPCC	Intergovernmental Panel on Climate Change

FK	Expert

FKT	Expert days

KZFK	Short-term expert

MEI	Monitoring Emission Inventory

MEP	Municipal energy plan

NbS	Nature-based solutions

SECAP	Sustainable Energy and Climate Action Plan

ToRs	Terms of reference

WG	Working Group

- Context

The EU4ClimateResilience project, jointly co-financed by the European Union and the German Federal Ministry for the Environment, Climate Action, Nature Conservation and Nuclear Safety (BMUKN), aims to support Armenia, Azerbaijan, Georgia, the Republic of Moldova, and Ukraine in addressing the challenges posed by climate change. These countries, highly vulnerable to the adverse effects of climate change, face increasingly severe weather events, including heat waves, droughts, forest fires, heavy precipitation, and flooding, which threaten to exacerbate disaster risks, public health concerns, and economic losses. In response, the EaP countries are committed to reducing their carbon footprint and aligning with the European Union’s climate policies, while simultaneously building national capacities to implement the Paris Agreement.

To achieve these goals, the EU4ClimateResilience project focuses on supporting the green transition, enhancing decarbonization efforts, improving energy security, and boosting resilience to climate change impacts. The project’s specific objectives are as follows:

- Increase countries’ capacities to adequately measure and reduce national emissions and adapt to the impact of climate change, and advance the implementation of the climate policy framework.

- Demonstrate the benefits of climate adaptation through specific projects.

- Support the establishment of credible regulatory frameworks on green finance in line with EU norms and to support the diversification and scaling-up of bond issuance.

As part of Outcome 1 — Climate change mitigation policy frameworks and strategies updated and implementation advanced — specifically under Indicator 1.1.3 Number of technical documents (bylaws, roadmaps, technical specifications, standards, technical reports/papers on demonstration projects feeding on technical documents etc.) supporting implementation of legal acts — the project includes the development of two Sustainable Energy and Climate Action Plan (SECAP) for selected Cities Kremenchuk and Boyarka, who is signatories to the Covenant of Mayors. These SECAPs aim to support local authorities in anticipating, preparing and responding to the impacts of climate change.

CoM Signatory (municipalities) share a vision for making cities decarbonized and resilient, where citizens have access to secure, sustainable and affordable energy. To translate commitments into action, they commit to:

- Setting ambitious mitigation and adaptation goal(s) / target(s);

- Measuring their GHG emission level in a base year, according to a common methodological approach; Baseline Emission Inventory (BEI)

- Assessing climate risks and vulnerabilities within their cities; Climate Risk and Vulnerability Assessments (CRVAs)

- Defining a comprehensive set of actions that local authorities plan to undertake in order to reach their climate mitigation and adaptation goals; Sustainable Energy and Climate Action Plan (SECAP). The plan will be based on the results coming from the previous assessments (BEI and CRVAs)

- Approving and making their action plan publicly available;

- Regularly reporting (both qualitatively and quantitatively) to the EC on the implementation of their action plan;

- Sharing their vision, results, experience, and know-how with fellow local and regional authorities within the EU and beyond through direct cooperation and peer-to-peer exchange.

Recently in 2021 the law on Energy efficiency was released. In this Law the national policy obliges the cities to develop Municipal energy plans (MEPs) starting from the year of 2023. Thus, those cities who are under SECAP development process need technical assistance in this process with the recommendations how to integrate the SECAPs into MEPs. The technical assistance will provide the support to develop of action plans with greater involvement of local administration and coherence with national policy (Municipal energy plans).

In additional, newly adopted Ukraine’s new Climate Law (effective from October 30, 2024) sets the following goals:

- Long-term: Achieving climate neutrality by 2050 through a just, low-carbon transition and limiting global temperature rise to 1.5°C–2°C.

- Medium-term: Reducing greenhouse gas emissions, increasing renewable energy, lowering GDP energy intensity, adopting nature-based solutions, and enhancing resilience to climate change.

In the upcoming future, local and regional climate adaptation plans will become mandatory, with secondary legislation to be developed in 2025-2026. Adaptation planning at the local level will follow a standardized methodology for climate risk and vulnerability assessment based on IPCC materials.

As the result, it is expected to have at least 2 developed and submitted SECAPs in Ukraine for follow municipalities: Kremenchuk, Boyarka.

- Tasks to be performed by the contractor

The overall objective of the assignment is to develop for two Ukrainian municipalities SECAPs and Municipal energy plans (MEP) in coherence with national policy during the period of 2025-2026 years. And development technical and economic justification of the project for climate mitigation, adaptation, or energy projects on the level of feasibility study.

  - Tasks

The contractor is responsible for providing the following work:

- to perform development of two full Sustainable Energy and Climate Action Plans (SECAPs) for municipalities Kremenchuk, Boyarka within tree pillars – mitigation with commitments till 2030 and 2050, adaptation with commitments till 2030 and 2050 and energy poverty with commitments till 2030 and 2050, and their online submission to the Covenant of Mayors initiative for local climate and energy actions;

Development of SECAP document must be fully aligned with Covenant of Mayors' guidelines, recommendations and best practices, both in terms of process of SECAP-development, and structure and contents of the final SECAP document.

The Contractor's assignment includes provision of high-quality technical assistance and on-the-job training to targeted City and stakeholders to efficiently perform the following tasks:

WP 1: Planning phase: Define the key elements of the SECAP and its structure based on SECAP structure mentioned below as SECAP structure and follow issues:

- Definition of scope of SECAP document (geographical/administrative, target activity sectors to be included in BEI/MEI inventories till 2030 and 2050 and reported during the SECAP implementation, mitigation/adaptation, time horizon, etc.) – two cities (Boyarka and Kremenchuk);

- Definition of the baseline year (the reference year against which the achievement of emission reductions in 2030 and climate neutrality in 2050 shall be compared) – two cities (Boyarka and Kremenchuk).

WP 2: Baseline Analysis and Risk Assessment

2.1. Elaborate a Baseline Emission Inventory (BEI) 2030 and 2050 which must inter alia elaborate the following issues:

- Proposed emission inventory approach;

- Activity sectors that will be included in the BEI/MEI;

- Detailed methodology for collecting baseline & reported final energy-consumption data for all proposed activity sectors, including indication of data sources;

- Detailed methodology for calculating respective baseline emission inventories (BEI) for all proposed activity sectors.

2.2. Perform a Climate Risk and Vulnerabilities Assessment (CRVA)

2.3. Identify energy poverty level on local level

WP 3: Strategic Visioning and Investment Planning

3.1. Establish the city vision within three CoM pillars till 2030 and 2050

3.2. Develop investment catalogue/strategy till 2030 and 2050

WP 4: 6 technical and economic justifications of the project for climate mitigation, adaptation, or energy projects on the level of feasibility study, 3 per city

WP 5: Finalisation of SECAP for targeted cities

5.1. Preparation of a finalised SECAP for the targeted city, developed in consultation with key stakeholders and the general public, and submission of the document to the respective city for review, endorsement and approval by the City Council or other competent decision-making body. After adoption by the cities, format the final approved version of the SECAP and submit to the Covenant of Mayors online platform.

WP 6. Two online Capacity-building workshops for municipalities

In additional, it should be covered the follow scope of works during SECAP development:

- Proposed structure of meetings and workshops with targeted City and stakeholders, that inter alia includes number of meetings and workshops per different tasks and activities, their purpose and brief agenda, target participants and their numbers per workshop /meeting, location /venue, etc.;

- Modalities of communication with general public.

SECAP structure attached in Annex 1.

Adoption of SECAP by the City and prepare final version for submission to the Covenant of Mayors online platform.

The service provider should have in mind that the overall sequence of the service is connected to each task aimed the development of SECAP document.

The total duration of the service is planned for 15 months.

The main deliverables from this assignment are as follows:

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance Deliverables |
| --- | --- | --- |
| WP 1. Planning phase: Define the key elements of the SECAP and its structure based on SECAP structure mentioned below as SECAP structure and follow issues: - Definition of scope of SECAP document (geographical/administrative, target activity sectors to be included in BEI/MEI inventories till 2030 and 2050 and reported during the SECAP implementation, mitigation/adaptation, time horizon, etc) – two cities (Boyarka and Kremenchuk); - Definition of the baseline year (the reference year against which the achievement of emission reductions in 2030 and climate neutrality in 2050 shall be compared) – two cities (Boyarka and Kremenchuk). | 27 May 2026/ Remote/ Team leader | Stakeholders identified. The Working plan presented for Working Group which approved by WG of each city and EU4Climate Resilience Minutes/report of the meeting submitted to EU4ClimateResilience, including key agreements, roles clarified, and next steps in Ukrainian and English, up to 4 pages in DOC format. |
| WP 2. Baseline Analysis and Risk Assessment: 2.1. Development of Baseline Emission Inventory (BEI) 2030 and 2050 which must inter alia elaborate the following issues: - Proposed emission inventory approach; - Activity sectors that will be included in the BEI/MEI; Detailed methodology for collecting baseline & reported final energy-consumption data for all proposed activity sectors, including indication of data sources; - Detailed methodology for calculating respective baseline emission inventories (BEI) for all proposed activity sectors. | 30 October 2026/ Remote/ Team leader | The deliverable covers all the elements described within the ToR (Annex 1. SECAP Executive Summary, Chapter 2-3). SECAP detail structure for UA CoM East Signatories. The SECAP template (BEI sheet) submitted, and covers information relevant for BEI for City. The deliverable is approved by city and EU4ClimateResilience via stakeholder meeting. Notes meeting provided in English at least 3 pages, with participants list. |
| 2.2. Development of Climate Risk and Vulnerabilities Assessment | 30 October 2026/ Remote/ Team leader | The deliverable covers all the elements described within the ToR, (Annex 1. SECAP Executive Summary, Chapter 4). SECAP detail structure for UA CoM Signatories. - The Climate Risk and Vulnerabilities Assessment report and SECAP template (CRVA sheet + adaptation scoreboard) submitted covers information relevant for adaptation strategy for City. - The deliverable is approved by city and EU4Climate Resilience via stakeholder meeting. Notes meeting provided in English at least 3 pages, with participants list. |
| 2.3. Development of Energy Poverty Assessment | 30 October 2026/ Remote/ Team leader | - The deliverable covers all the elements described within the ToR, (Annex 1. SECAP Executive Summary, Chapter 5) of SECAP detail structure for UA CoM Signatories - Energy Poverty Assessment report submitted covers information relevant for (Annex 1. SECAP Executive Summary, Chapter 5) of SECAP detail structure for UA Signatories and SECAP template. The deliverable is approved by city and EU4Climate Resilience via stakeholder meeting. Notes meeting provided in English at least 3 pages, with participants list. |
| WP 3. Strategic Visioning and Investment Planning: 3.1. Establishing сity vision within three CoM pillars till 2030 and 2050 within 3 CoM pillars | 30 December 2026/ Remote/ Team leader | The deliverable covers all the elements described within the ToR, (Annex 1. SECAP Executive Summary, Chapter 10) of SECAP detail structure for UA Signatories. The deliverable is approved by city and EU4Climate Resilience via stakeholder meeting. Notes meeting provided in English at least 3 pages, with participants list. |
| 3.2. Development of investment catalogue/strategy till 2030 and 2050 completed | 28 February 2027/ Remote/ Team leader | The deliverable covers all the elements described within the ToR, (Annex 1. SECAP Executive Summary, Chapter 8) of SECAP detail structure for UA CoM Signatories. The deliverable is approved by city and EU4Climate Resilience via stakeholder meeting. Notes meeting provided in English at least 3 pages, with participants list |
| WP 4. 6 technical and economic justifications of the project for climate mitigation, adaptation, or energy projects on the level of feasibility study, 3 per city | 30 May 2027/ Remote/ Team leader | Three (3) technical and economic justification of the project documents per municipality, 6 total. All documents meet IFs (EBRD and etc.) requirements, submitted in both editable and final formats All 6 documents are submitted to EU4ClimateResilience and municipalities in English and Ukrainian languages, minimum 15 pages each document |
| WP 5. Finalisation of SECAP for targeted cities: 5.1. Preparation of a finalised SECAP for the targeted city, developed in consultation with key stakeholders and the general public, and submission of the document to the respective city for review, endorsement and approval by the City Council or other competent decision-making body. After adoption by the cities, format the final approved version of the SECAP and submit to the Covenant of Mayors online platform. | 31 April 2027/ Remote/ Team leader | The deliverable covers SECAP updated draft for cities council decision (minimum 150 pages), based on and taking into account comments and recommendations of Boyarka and Kremenchuk city council or equivalent decision-making bodies as well as EU4ClimateResilience. Documents ready for submission for final approval and submission to the Covenant of Mayors. |
| WP 6. Two online Capacity-building workshops for municipalities completed | May 2026 – April 2027/ Remote/Offline/ Team leader | 2 online training sessions up to 4 hours Topics to be defined by cities. Provide agenda, materials, list of participants, photos/screenshots from events and evaluation form after events in Ukrainian and English to EU4ClimateResilience |

The contract duration is from 4 May 2026 till 30 June 2027.

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to describe its backstopping concept. The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

- Process-oriented steering for implementation of the commission

- Securing the administrative conclusion of the project

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

If the Contractor provides fewer experts than the number of positions described, the experts will be assessed for all requirements and qualifications for all positions they are intended to cover.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

- Lead and coordinate the SECAP development and delivery process across three cities

- Ensure alignment with CoM standards and EU4ClimateResilience expectations

- Oversee deliverables such as BEI, CRVA, energy poverty assessments, investment strategies

- Manage team resources and reporting

Qualifications of the team leader

- Education/training (2.1.1): Master's degree in technical or natural sciences or economy area

- Language (2.1.2): B2-level language proficiency in English according to the Common European Framework of Reference for Languages

- General professional experience (2.1.3): 5 years of professional experience in the in developing action/strategic plans for different levels of government in the areas of Energy poverty, or Climate Change Mitigation and Adaptation;

- Specific professional experience (2.1.4): 5 years in energy efficiency measures and renewable energy generation, or Nature-based Solutions and adaptation measures for municipal critical infrastructure, building sectors, ecosystems and environmental sectors.

- Leadership/management experience (2.1.5): 5 years of management/leadership experience as project team leader or manager in a company.

- Other (2.1.8): 3 years of experience to develop SECAPs via CoM methodology

Key Expert 1: Technical expert - Energy and Mitigation

Tasks of the Key expert 1

- Compile Baseline Emission Inventory (BEI) for each city in accordance with CoM methodology

- Support technical analysis of energy systems and identification of priority mitigation projects

- Lead development of pre-feasibility documentation for selected climate mitigation projects

- Contribute to the investment strategy (to 2030 and 2050)

Qualifications of the Key expert 1

- Education/training (2.2.1): Master's degree in Energy Engineering, Environmental Engineering, or related field

- Language (2.2.2): B1-level language proficiency in English Language according to the Common European Framework of Reference for Languages

- General professional experience (2.2.3): 5 years of professional experience in the development of technical part of energy and climate strategies or relevant document (SECAPs, MEPs etc.) and/or in development of EE, RES, NbS or adaptation measures within different type of municipal sectors.

- Specific professional experience (2.2.4): 3 years in CO2 calculations related to emissions from municipal relevant sectors, energy balance development with climate neutrality till 2050

Key Expert 2: Finance expert

Tasks of the Key expert 2

- Analyse and propose bankable projects in energy, climate, and adaptation sectors

- Provide cost-benefit analysis for SECAP investment strategies

- Support cities in linking plans to potential financial instruments

Qualifications of the Key expert 2

- Education/training (2.3.1): Master's degree in Finance, Economics, Public Administration

- Language (2.3.2): B1-level language proficiency in English Language according to the Common European Framework of Reference for Languages

- General professional experience (2.3.3): 5 years of professional experience in the development of investment part of energy and climate strategies or relevant document (SECAPs, MEPs etc.) and in development the economic background of EE, RES, NbS or adaptation measures within different type of municipal sectors.

- Specific professional experience (2.3.4): 5 years in public finance, financing mechanisms and models, budgeting process

Key Expert 3: climate change adaptation expert

Tasks of the Key expert 3

- Conduct CRVA for each city in line with CoM template

- Support adaptation strategy development and alignment with national plans

- Ensure integration of local risks into long-term climate vision

Qualifications of the Key expert 3

- Education/training (2.4.1): Master's degree in Environmental Science, Climate Resilience, or Disaster Risk Management

- Language (2.4.2): B1-level language proficiency in English Language according to the Common European Framework of Reference for Languages

- General professional experience (2.4.3): 5 years of professional experience in the development of climate risk and vulnerability assessment for municipal sectors, planning of adaptation measures and adaptation policy on municipal level based on IPCC methodology and recommendation.

- Specific professional experience (2.4.4): 2 years in NbS and adaptation project development within different municipal sectors.

Key Expert 4: Technical Expert Urban Planning and Energy Poverty

Tasks of the Key expert 4

- Develop Energy Poverty Assessment in line with SECAP guidance

- Support cities in vision-building (2030/2050) and alignment with 3 CoM pillars

- Coordinate stakeholder engagement for inclusive strategy development

Qualifications of the Key expert 4

- Education/training (2.5.1): Master's or Bachelor's degree in technical or engineering  area

- Language (2.5.2): C2 level (native) language proficiency in Ukrainian Language according to the Common European Framework of Reference for Languages

- General professional experience (2.5.3): 3 years in urban planning or community development

- Specific professional experience (2.5.4): 2 years in energy poverty, inclusive planning

# Costing requirements

## Assignment of personnel and travel expenses

N/a

Specification of inputs

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| Milestones/partial works | Estimated expert days for orientation | Anticipated deadline/place/person responsible |
| --- | --- | --- |
| WP 1. Planning phase: Define the key elements of the SECAP and its structure based on SECAP structure mentioned below as SECAP structure and follow issues: - Definition of scope of SECAP document (geographical/administrative, target activity sectors to be included in BEI/MEI inventories till 2030 and 2050 and reported during the SECAP implementation, mitigation/adaptation, time horizon, etc.) – two cities (Boyarka and Kremenchuk); - Definition of the baseline year (the reference year against which the achievement of emission reductions in 2030 and climate neutrality in 2050 shall be compared) – two cities (Boyarka and Kremenchuk). | Team leader – 4 Key Expert 1 – 3 Key Expert 2 - 2 Key Expert 3 – 2 Key Expert 4 - 2 Total: 13 | 27 May 2026/ Remote/ Team leader |
| WP 2. Baseline Analysis and Risk Assessment: 2.1 Development of Baseline Emission Inventory (BEI) 2030 and 2050 which must inter alia elaborate the following issues: - Proposed emission inventory approach; - Activity sectors that will be included in the BEI/MEI; Detailed methodology for collecting baseline & reported final energy-consumption data for all proposed activity sectors, including indication of data sources; - Detailed methodology for calculating respective baseline emission inventories (BEI) for all proposed activity sectors. 2.2 Development of Climate Risk and Vulnerabilities Assessment 2.3 Development of Energy Poverty Assessment | Team leader – 30 Key Expert 1 – 30 Key Expert 2 - 5 Key Expert 3 – 40 Key Expert 4 - 25 Total: 130 | 30 October 2026/ Remote/ Team leader |
| WP 3. Strategic Visioning and Investment Planning: 3.1. City vision within three CoM pillars till 2030 and 2050 within 3 CoM pillars 3.2. Investment catalogue/strategy till 2030 and 2050 completed | Team leader – 15 Key Expert 1 – 10 Key Expert 2 - 25 Key Expert 3 – 10 Key Expert 4 - 5 Total: 65 | 30 December 2026/ Remote/ Team leader 28 February 2027/ Remote/ Team leader |
| WP 4. 6 technical and economic justifications of the project for climate mitigation, adaptation, or energy projects on the level of feasibility study, 3 per city | Team leader – 40 Key Expert 1 – 30 Key Expert 2 - 30 Key Expert 3 – 20 Key Expert 4 - 18 Total: 138 | 30 May 2027/ Remote/ Team leader |
| WP 5. Finalisation of SECAP for targeted cities 5.1. Preparation of a finalised SECAP for the targeted city, developed in consultation with key stakeholders and the general public, and submission of the document to the respective city for review, endorsement and approval by the City Council or other competent decision-making body. After adoption by the cities, format the final approved version of the SECAP and submit to the Covenant of Mayors online platform. | Team leader – 8 Key Expert 1 – 6 Key Expert 2 - 4 Key Expert 3 – 4 Key Expert 4 - 4 Total: 26 | 31 April 2027/ Remote/ Team leader |
| WP 6. Two online Capacity-building workshops for municipalities completed | Team leader – 2 Key Expert 1 – 2 Key Expert 2 - 2 Key Expert 3 – 1 Key Expert 4 - 1 Total: 8 | May 2026 – April 2027/ Remote/ Team leader |

# Inputs of GIZ or other actors

GIZ shall be copied in all official communication related to the implementation of the assignment and invited to all relevant meetings, workshops, and consultations. The Contractor awarded under this tender shall ensure close and continuous coordination with GIZ throughout the duration of the contract.Participating municipalities shall establish a municipal working group, comprising relevant local stakeholders, to provide local expertise, data, and contextual input for the assignment. The Contractor shall regularly consult with the municipal working groups, actively seek their feedback, and reflect relevant inputs in the development of deliverables.

The Contractor shall also maintain regular and structured communication with the municipalities, including close cooperation with the working group established under each municipality for the purposes of this assignment. All key deliverables, interim outputs, and final results shall be subject to review, comments, and formal approval by both GIZ and the respective municipality prior to acceptance.

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of work completed, the Contractor shall be paid in the following installments:

| Installment # | Anticipated payment date | Payment for WP | Deliverables and reporting |
| --- | --- | --- | --- |
| 1 Interim payment | 16.11.2026 | WP 1; WP 2 | Acc. to cl. 2.1 (table with Milestones/partial works) |
| 2 Interim payment | 15.03.2027 | WP 3 | Acc. to cl. 2.1 (table with Milestones/partial works) |
| Final payment | 19.06.2027 | WP 4, WP 5, WP6 | Acc. to cl. 2.1 (table with Milestones/partial works) |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, excl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF), submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheets (LERF), etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- Each invoice and act of acceptance shall contain the Project Number and contract number:

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- Service Entry Sheets (LERF) will be provided during contract implementation.

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

The Contract /Supplement to this Contract (if any) enter into force upon its signing by the Parties.

If there are two different dates, then the signing date of the Contract/Supplement to this Contract (if any) is considered to be the last date of signature of one of the Parties.

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local)  published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor: ____________________________________.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

The given procurement of services/ works upon the Contract shall be carried out at the funds of the Project of International Technical Assistance (Project ITA), PN: 2021.9025.4,  Project title “Підтримка країн Східного партнерства в їх наближенні до Green Deal / EU4ClimateResilience (PROGRESS /EU4ClimateResilience)”, registered by the Secretariat of the Cabinet of Ministers of Ukraine (registration card of the project (program) No. 6213 dated 30.09.2025) and complies with the category (type) of Services specified in the purchase plan available at address https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel

The above-mentioned ITA project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008.

The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, then the Contractor must notify GIZ of such VAT registration in writing or in electronic form by means of submission of an e-mail with copy of the Excerpt from VAT Registration Registry to the GIZ’s e-mail address indicated in the details of the Contract. The Contractor must submit the mentioned notification to the GIZ not later than 1 calendar day following the day of VAT registration.

# At the same time the Parties agreed that the purchase of Services after the VAT registration of the Contractor shall be exempt from VAT in accordance with the abovementioned.Outsourced processing of personal data

The performance of the contract may be associated with the processing of personal data by the contractor, who would define alone the nature of such data and how such processing would be carried out. In such cases, the contractor shall act as an independent DATA CONTROLLER and must comply alone with ALL applicable data protection obligations, including those stemming from regional and local laws. The contractor must process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GDPR’s data transfer rules must be considered whenever personal data leaves the EU for a third country. The GIZ is NOT in any way responsible for such processing.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English(language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in Ukrainian or English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Annexes

Annex 1. SECAP Executive Summary

Chapter 1. Introductory part. General analytical part of municipality

General characteristics of the urban territorial community

- Energy and climate policy

- Legal framework

Chapter 2. Energy balance and energy development of community

Chapter 3. Baseline Emission Inventory (BEI) till 2030 and 2050 with climate neutrality for Boyarka and Kremenchuk

Inventory year

Number of inhabitants in the inventory year

Emission factors approach (standard or LCA)

Emission reporting unit (CO2 or CO2-equivalent)

Responsible body /department (main contact)

Detailed BEI results in terms of final energy consumption and GHG emissions

If relevant, also need to be specified:

Inclusion of optional sectors and sources

Assumptions made, references or tools used

Chapter 4. Expected weather and climate events particularly relevant for the local authority or region

Vulnerability of the local authority or region

Expected climate impacts in the local authority or region

Assets and people at risk from Climate Change impacts

Chapter 5. Energy poverty, energy security and sustainable energy

Chapter 6. Mitigation actions and measures for the full duration of the plan (2030-2050) for each measure /action it should be specified (whenever possible) for Boyarka and Kremenchuk

Description

Responsible department, person or organisation

Timing (end-start, major milestones)

Cost estimation (investment and running costs)

Estimated energy saving /increased renewable energy production by target year

Estimated GHG reduction per target year

Indicators for monitoring

Chapter 7. Adaptation actions and measures for the full duration of the plan (2030-2050); the actions should be coherent with outcomes of the municipality /city climate vulnerability and risk assessment (CRVA); for each measure /action it should be specified (whenever possible):

Sector

Title

Description

Responsible body /department and contact point

Timing (end-start, major milestones)

Actions also affecting mitigation

Stakeholders involved /advisory group

Impacts, vulnerabilities and risks tackled

Costs (investment and running costs)

Indicators for monitoring

Chapter 8. Overall budget for implementation and financial sources. Investment catalogue till 2030 and 2050

Chapter 9. Involvement of stakeholders and citizens. Stakeholders’ engagement plan.

Chapter 10. SECAP Strategy 2030-2050

Vision

Commitments both for mitigation, for adaptation and for energy poverty:

    - For mitigation, the SECAP document should clearly indicate the emission reduction target by 2030 (and possibly beyond) clearly stating the BEI year and the reduction-target type (absolute reduction or per capita reduction) and by 2050 with climate neutrality;

    - For adaptation, the SECAP should include a certain number of adaptation goals, coherent with the identified vulnerabilities, risks and hazards;

    - For energy poverty, the SECAP should include a certain number of goals related to decrease energy poverty on the level of citizen.

Coordination and organizational structures created /assigned

Staff capacity allocated

Implementation and monitoring process

Assessment of the adaptation options

Strategy in case of extreme climate events or no energy access

SECAP structure should be developed based on SECAP detail structure for UA Signatories:

https://com-east.eu

SECAP should be developed based on follow methodologies and documents:

# Guidebook: How to develop a Sustainable Energy and Climate Action Plan (SECAP)

https://com-east.eu

# Reporting Guidelines on Energy Poverty

https://eu-mayors.ec.europa.eu

- The methodology for Municipal Energy Plans (MEPs) approved by the Ministry of Infrastructure

https://zakon.rada.gov.ua/laws/show/z0245-24#Text

- Climate risk and Vulnerability assessment – Ukraine country specific recommendation

https://com-east.eu