| IMPLEMENTATION OF MUNICIPAL ENERGY MANAGEMENT SYSTEM IN COAL COMMUNITIES | Project number/ cost centre: G-012619-002 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

MEM                   Municipal Energy Management

- Context

In the coming years, unprofitable state-owned coal mines will seize their operations. Up to 40,000 employees in mining and many more in companies related to the mining sector will lose their jobs. This poses great social and economic challenges for the coal regions. The structural change required to cope with the Just Transition and Green Recovery concepts can set new development and growth impulses in the affected regions and beyond. Decarbonising the economy also makes a significant contribution to Ukraine being able to increase its level of ambition in the context of global climate protection.

The goal of this German-Ukrainian cooperation is to enable Ukraine to shape the structural change associated with the phase-out of coal at national, regional, and local level, involving civil society and applying appropriate funding instruments, using the concepts of Just Transition and Green Recovery, socially and economically viable, as well as energy-economic and ecologically sustainable, thus contributing to a climate-neutral economy.

Power4JustTransition is implemented by GIZ on behalf of the German Ministry of Economic Affairs and Energy. The project focuses on empowering local stakeholders, strengthening regional capacities, and fostering economic diversification to ensure that no community is left behind in the shift away from coal.

The project is implemented in close cooperation with key national and regional partners, including the Ministry of Energy of Ukraine, the Ministry for Communities and Territories Development, and regional authorities such as the Lviv, Volyn, and Dnipropetrovsk Regional Military Administrations, as well as the Ladyzhyn City Council. Based on the Memorandums of cooperation signed between GIZ/Project and partners, GIZ/Project plans to support the process of Just Transition policies development and implementations on the territory of Lviv, Volyn, Vinnytsa and Dnipropetrovsk regions.

Coal communities face economic, environmental, and social challenges related to the energy transition and the high energy intensity of municipal infrastructure. The implementation of a Municipal Energy Management System is an effective tool to improve energy efficiency, reduce energy costs, lower greenhouse gas emissions, and strengthen local energy security.

This Agreement aims to establish and implement a Municipal Energy Management System in 9 coal communities to support sustainable development, enable a just transition, enhance the institutional capacity of local authorities, and improve the quality of life for residents.

- Tasks to be performed by the contractor

The objective of this assignment is to provide 9 coal communities with comprehensive consultancy services, aiming at the implementation of key elements of the Municipal Energy Management System, improvement of energy efficiency and energy saving policy in this communities through the creation of a system management tool following the “COMMON PROCUREMENT VOCABULARY“ SC/DK 021:2015: 71314300-5 "Energy-efficiency consultancy services" and SC/DK 021:2015:71314200-4 "Energy-management services" with focus on the sustainable development.

List of coal communities and number of municipal buildings:

- Belz (164 buildings)

- Sokal (152 buildings)

- Dovbrotvir (115 buildings)

- Velyki Mosty (43 buildings)

- Radekhiv (45 buildings)

- Ternivka (100 buildings)

- Ladyzhyn (44 buildings)

- Poromiv (28 buildings)

- Lytovezh (21 buildings)

Coal communities focus on providing adequate living, working, learning facilities, and educational opportunities for the locals and IDPs, including the relocated businesses, but lacks internal resources. Energy Efficiency and Energy Saving are crucial for the challenging period of war. Energy Efficiency and Energy Saving measures could be sufficiently supported by organising the Municipal Energy Management system.

The main goal is implementing key elements of the energy management system, improving energy efficiency and energy saving policy in coal communities through establishing a system management tool following the Law of Ukraine "On Energy Saving".

The task is to implement a step-by-step approach to the energy management system's organisation following the conditions and needs of coal communities. The Municipal Energy Management (MEM) system provides a step-by-step approach to implementing energy management adapted to their actual needs. The concept defines three levels of MEM – from a low-threshold start for small municipalities with no experience and few resources to a holistic MEM covering all municipal buildings’ relevant areas. Currently, it is planned to implement two levels of MEM (Basics; Building Inventory; Portfolio-Analysis; Capacity Building; Energy Monitoring; Optimization; Reporting) - from regulatory support for the beginning of the process of establishing energy management, through the inventory of buildings and the establishment of effective energy monitoring, to the introduction of a periodic reporting system.

  - Tasks

The methodological basis for the development of the Energy Management system of coal communities is the national standard of Ukraine DSTU ISO 50001:2014, which defines the requirements for the energy management system, norms and standards in the field of energy saving, increasing the energy efficiency of public buildings and is based on the Plan-Do-Check-Act (PDCA) cycle, and also provides for the inclusion of energy management in the daily activities of local government. The standard is based on common elements of the ISO standards and the management system, guaranteeing a high level of compatibility with the ISO 9001 and ISO 14001 standards. Furthermore, in addition to the national standard of Ukraine DSTU ISO 50001:2014, the system must comply with the methodology of the Municipal Energy Management Modules.

These Terms of Reference include four Work Packages:

Work package 1. Normative, legal and institutional support for the implementation of MEM. (up to 4 experts, up to 90 man-days)

Task 1.1. Develop and adopt normative legal acts of local governments regarding implementing MEM.

Provide expert assistance to local governments in ensuring the development of regulatory and legal acts, finding adequate and sufficient time and budget resources for sustainable implementation, and functioning of MEM. Assistance will apply to:

- Development of 9 drafts decision of the city/village council / executive committee/order of the /village mayor on the implementation of municipal energy management;

- Preparation of documents for recruiting and holding a competition for the selection of responsible persons for the position(s) of energy manager(s). Development of drafts regulations/job descriptions, duties and distribution of working time for energy manager(s);

- Analysis and justification of the need to allocate resources for the organization of the workplace and the salary of the energy manager(s);

- Development of recommendations/draft plan for professional development, education, and exchange of knowledge for energy manager(s).

Task 1.2. Ensure the involvement of key executors and conduct their training.

- Provide assistance in the formation of the energy management units, a map of key performers in the MEM system and conduct training for key stakeholders and executors. Assistance will apply to:

o Collection, analysis, and systematization of information about relevant departments, balance-keepers of municipal buildings, with which it is necessary to maintain managers, technical staff, and users of communally owned buildings;

o Conducting offline training for heads of budget institutions with the participation of the energy manager(s) and key executors on the implementation of MEM (in the learning-by-doing format) - for at least 10 people in each community;

o Conducting offline trainings for caretakers / supply and maintenance managers of budget institutions with the participation of the energy manager(s) and key executors on MEM implementation issues (1) Information on the state and plans for MEM implementation; 2) Provision of essential technical information on the operation of the building (e.g., temperature schedule of heating, hydraulics, ventilation, electricity, etc.); 3) Discussion of actual problems and ideas regarding technical and organisational improvement) - for at least 10 people in each community).

Work package 2. Implementation of 9 systems for collecting, analysing, and systematising information in the field of energy consumption and energy efficiency.

(up to 4 experts, up to 54 man-days)

Task 2.1. Conduct an inventory of buildings.

Provide assistance in establishing a system for local governments to collect specific information about buildings owned or used by the community, and this consists of creating a general database/registry of the community's building fund with the simultaneous collection of relevant primary data.

Minimum requirements for database parameters:

- Building: the official name of the building;

- Address of the building;

- Category – use of the building, including possible features of use;

- Ownership/use – the building is owned by the community or leased;

- Renovation (already renovated, planned in the coming years, etc.);

- Year of construction and repair (repairs);

- Area in m²;

- Heating / Air-conditioning area in m²;

- Heating system;

- The main source of heat energy is an energy carrier;

- Annual consumption of heat, electricity and water;

- If available: energy and water consumption costs.

Task 2.2. Carry out portfolio analysis.

Provide expert assistance in analysing energy consumption in budget buildings of 9 coal communities, which is essential for assessing the energy efficiency of the building stock and determining potential savings from the implementation of MEM. Completing this task involves collecting building energy consumption data, calculating specific values, and comparing them with the best reference values of existing buildings, and comparing buildings of different sizes within the same purpose or category.

To complete the task, it is necessary to collect information and carry out the following:

- Collection of heat energy (kWh or Gcal) and electricity (kWh) consumption data for at least one year;

- Collection of information on the heating area of buildings (m²);

- Adjustment of heat energy consumption to the temperature schedule;

- Calculation of the specific consumption of heat and electrical energy (kWh/m²/year);

- Comparison of reference indicators from databases (national or regional);

- Calculation of deviation from reference values (%);

- Visualisation of the obtained data set using a portfolio diagram.

Work package 3. Set-up of the energy monitoring and reporting systems. (up to 4 experts, up to 126 man-days)

Task 3.1. Set-up an energy monitoring systems.

The Contractor shall procure all necessary software for the implementation of the Municipal Energy Management System for all coal communities, in accordance with the number and type of municipal buildings. The Contractor shall provide expert assistance in setting-up 9 systems of energy monitoring, the establishing systematic control of energy consumption, regular registration of heat, electricity and water consumption, analysis of received data and preparation of reports with possibility of further managerial decisions.

Completing this task involves the following steps and measures:

- Deciding on the indicators and depth of energy monitoring (which buildings will be covered by energy control);

- Identifying buildings that need to be equipped with heat, electricity and water consumption meters, ensuring regular meter readings;

- Climatic adjustment of heat energy consumption;

- Setting up a systems of constant analysis of energy consumption with tracking of consumption fluctuations/deviations from expected consumption; documenting exceptional cases causing increased consumption;

- Establishment of an effective feedback mechanism with responsible technical personnel and building users, in particular, in the form of short periodic reports.

Technical specification for the software:

The software is designed for centralized accounting, monitoring, analysis and optimization of energy consumption in municipal buildings of a territorial community. The system provides data collection and processing for the building envelope with a separate possibility of aggregating information at the community, industry or balance holder level. The system must support web access (via browser), be scalable, secure and suitable for use by employees of local government bodies without special technical training.

Each municipal building is considered as a separate energy management object and must have its own electronic card with a full set of characteristics and indicators.

The objects include, in particular:

- educational institutions (schools, lyceums, kindergartens);

- healthcare facilities;

- administrative buildings;

- cultural and sports facilities;

- other municipal facilities.

The system must ensure the creation and maintenance of an electronic card for each building with the following data:

- name and type of building;

- address and geographical coordinates;

- balance holder;

- year of construction and/or last reconstruction;

- total and heated area;

- number of floors;

- number of users (students, employees, etc.);

- energy characteristics (energy efficiency class, type of enclosing structures).

The system must support accounting for the following types of energy resources:

- electricity;

- natural gas;

- thermal energy;

- solid fuel (firewood, pellets, coal);

- water (cold/hot);

- alternative energy sources (solar panels, heat pumps, etc.).

For each resource:

- monthly entry of meter readings;

- automatic or manual data entry;

- saving the history of readings;

Technical requirements:

- web-based architecture (access via browser);

- support for the Ukrainian language;

- adaptive interface (PC, tablet);

- data storage in a secure database;

- data backup;

- compliance with personal data protection requirements;

- the ability to integrate with other municipal systems;

- аnnual subscription

Task 3.2. Create a reporting systems.

Provide assistance with developing the reporting systems and format for it, forming a typical annual energy report based on energy control data, considering energy bills from supplier companies. The Contractor shall ensure proper installation, configuration, and correct functioning of the software, including testing and commissioning. In addition, the Contractor shall provide comprehensive training for relevant municipal personnel on the use, administration, and basic maintenance of the software to ensure its effective and sustainable operation.

These are the minimum requirements for the annual energy report, which must include the following:

- Energy consumption in different sectors (heat, electricity, water) and by different energy carriers (natural gas, central heating, coal, firewood, etc.);

- Dynamics of energy prices and costs; Calculation of CO2 emissions in connection with heat and electricity consumption;

- Calculation of savings (energy, costs, reduction of CO2 emissions) in connection with the implementation of MEM;

- Objectives and achievements of MEM, including a description of implemented measures.

Work package 4. Optimisation of the technical infrastructure. (up to 4 experts, up to 90 man-days)

Task 4.1. Implement priority measures to optimise the technical infrastructure of buildings.

Provide expert assistance in establishing the systems of ongoing optimising the existing technical infrastructure through measures that do not require significant investments, taking into account the parameters of public buildings, which must be adapted to the actual mode of their use.

Completing the task includes:

- Development of instructions for the operation of buildings taking into account aspects of energy efficiency;

- Establishing the process of regular visits to buildings by the energy manager together with the responsible/technical staff;

- Provision of technical templates for the process of checking the functioning of control and regulation systems;

- Implementing priority measures to optimise the technical infrastructure, considering aspects of energy efficiency;

- Provision of ad-hoc consulting and expert support at the municipality’s request in increasing the energy efficiency of buildings and operational work of energy managers.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Work package 1. Normative, legal and institutional support for the implementation of MEM. | 15.06.2026 |
| Work package 2. Implementation of 9 systems for collecting, analysing, and systematising information in the field of energy consumption and energy efficiency | 15.07.2026 |
| Work package 3. Set-up of the energy monitoring and reporting systems | 30.09.2026 |
| Work package 4. Optimisation of the technical infrastructure | 30.11.2026 |

The contract duration is from 15.04.2026 till 28.02.2027.

This scope of work shall be executed in compliance with the current regulatory framework.

The following legislative documents, norms and acts shall be used to perform this task (the list is not exhaustive):

- The 27th Directive of the EU "On EE" (DIRECTIVE 2012/27/EU OF THE EUROPEAN PARLIAMENT AND OF THE COUNCIL of October 25, 2012, on energy efficiency, amending Directives 2009/125/EC and 2010/30/EU and repealing Directives 2004/8/EC and 2006/32/EC);

- The Law of Ukraine "On Energy Efficiency";

- The Law of Ukraine on Local government;

- National standard of Ukraine DSTU ISO 50001:2014;

- National sanitary, construction and technical standards and norms of Ukraine;

- Other relevant norms and regulations.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| - Expected deliverables for the WP 1 |  |  |
| 9 Drafts Decision of the session of the city council / executive committee/order of the city mayor on the implementation of energy management. | 9 PDF files in Ukrainian (up to 100 pages each) | 15.06.2026 |
| 9 Drafts Regulations/job descriptions and duties of the energy manager(s). | 9 PDF files in Ukrainian (up to 50 pages each) | 15.06.2026 |
| Recommendations/drafts training and professional development plan, knowledge exchange for energy manager(s) | PDF file in Ukrainian (up to 10 pages) | 15.06.2026 |
| Report on conducting 9 trainings for the heads of budget institutions with the participation of the energy manager(s) and key executors on the implementation of MEM – for at least 10 people in each community (Appendices: agenda, list of participants, presentations, methodological, photo and video materials). | PDF file in Ukrainian (up to 5 pages) | 15.06.2026 |
| Report on conducting 9 trainings for caretakers/supply and maintenance managers of budget institutions with the participation of the energy manager(s) and key executors on the implementation of MEM – for at least 10 people in each community (Appendices: agenda, list of participants, presentations, methodological, photo and video materials). | PDF file in Ukrainian (up to 5 pages) | 15.06.2026 |
| Interim report with information on the implementation of activities within the work package | PDF file in Ukrainian (up to 5 pages) | 15.06.2026 |
| - Expected deliverables for WP 2 |  |  |
| 9 databases/registers/tables in Excel with a set of necessary data on all budget buildings in each coal community's communal ownership. | 9 databases/registers/tables in Excel | 15.07.2026 |
| 9 reports with recommendations and visualisation of the analysis of the portfolio of buildings of the each coal community | 9 PDF files in Ukrainian (up to 20 pages each) | 15.07.2026 |
| Interim report with information on the implementation of activities within the work package | PDF file in Ukrainian (up to 5 pages) | 15.07.2026 |
| - Expected deliverables for WP 3 |  |  |
| 9 Draft Decisions of the Executive Committee of the City/Village Council/Order of the City/Village Mayor for heads of institutions and establishments on the regular reading of meter readings, accounting and reporting | 9 PDF files in Ukrainian (up to 10 pages each) | 30.09 2026 |
| 9 reports with recommendations based on the results of the analysis and identification of buildings that need to be equipped with heat, electricity, and water consumption meters | 9 PDF files in Ukrainian (up to 20 pages each) | 30.09 2026 |
| Specification for the purchase of a software product for energy monitoring, procured them and hang over for the communities and after that installation of the software. | 9 Specification in Excel Hang over protocols | 30.09 2026 |
| 9 Annual energy reports | 9 PDF files in Ukrainian (up to 20 pages each) | 30.09.2026 |
| Interim report with information on the implementation of activities within the work package | PDF file in Ukrainian (up to 5 pages) | 30.09.2026 |
| - Expected deliverables for WP 4 |  |  |
| 9 instructions regarding the energy-efficient operation of buildings by their users. | 9 PDF files in Ukrainian (up to 20 pages each) | 30.11.2026 |
| 9 reports with recommendations on possible low-cost and/or free measures to be implemented/ already implemented in buildings | 9 PDF files in Ukrainian (up to 20 pages each) | 30.11.2026 |
| Interim report with information on the implementation of activities within the work package | PDF file in Ukrainian (up to 5 pages) | 30.11.2026 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) .

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications. The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Key experts 1,2, 3 and 4

Tasks of key experts 1, 2, 3 and 4

- Provide overall technical coordination and quality assurance for the implementation of the Municipal Energy Management (MEM) System in 9 coal communities.

- Support local authorities in developing and adopting regulatory and institutional documents for MEM implementation.

- Assist in the recruitment, role definition, and capacity building of municipal energy managers.

- Organise and conduct trainings for heads of budget institutions, technical staff, and building managers.

- Establish and supervise the creation of municipal building inventories and energy databases.

- Lead portfolio analysis of energy consumption and identify energy-saving potential.

- Support the set-up of energy monitoring systems, including metering, data collection, and climate adjustment.

- Develop reporting formats and supervise the preparation of annual energy reports.

- Provide technical guidance on low-cost and no-cost energy efficiency measures in public buildings.

- Ensure compliance with ISO 50001, Ukrainian legislation, and project requirements, and coordinate with GIZ and local stakeholders.

Qualifications of key experts 1,2, 3 and 4:

- Education/training (2.1.1, 2.2.1, 2.3.1, 2.4.1): University degree (Bachelor in Energy Engineering, Energy Efficiency, Environmental Studies, Municipal Management, Public Management or a related field.

- Language (2.1.2, 2.2.2, 2.3.2, 2.4.2): B2-level language in English

- General professional experience (2.1.3, 2.2.3, 2.3.3, 2.4.3): 7 years of professional experience in the of energy efficiency, energy management, sustainable development, or municipal governance

- Specific professional experience (2.1.4, 2.2.4, 2.3.4, 2.4.4): 5 years in implementing energy management systems, energy efficiency programmes, energy audits, or energy monitoring in the public sector

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

# Costing requirements

Specification of inputs

## Contract for services:

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of Key expert 1 | Man day | 1 | 90 |  |
| Designation of Key expert 2 | Man day | 1 | 90 |  |
| Designation of Key expert 3 | Man day | 1 | 90 |  |
| Designation of Key expert 4 | Man day | 1 | 90 |  |
| Other costs | Unit of measurement | Quantity |  | Comments (if any) |
| Procurement of materials and equipment Sets of software product for conducting energy monitoring for each community (according to the number of municipal buildings) | pcs | up to 715 |  | Reimbursement of costs will be done based on proof o evidence. The Contractor must provide the following documents for reimbursement: copies of Invoice, Act of acceptance from the seller, Software license |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors

GIZ and/or other actors (municipalities) are expected to make the following available:

- Venue for the trainings

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of services completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting |
| --- | --- | --- | --- |
| 1 Interim payment | 05.08.2026 | 30% | Acc. to cl. 2.2 |
| 2 Final payment | 31.12.2026 | 70% | Acc. to cl. 2.2 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, incl. VAT if applicable.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance and timesheets, service entry sheet (LERF), etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- Each invoice and act of acceptance shall contain the Project Number, contract number and the percentage for cost split as follows (if applicable):

- Indicate project number ad 50% G-012619-001

- Indicate project number ad 50% G-012619-002

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

The Contract /Supplement to this Contract (if any) enter into force upon its signing by the Parties.

If there are two different dates, then the signing date of the Contract/Supplement to this Contract (if any) is considered to be the last date of signature of one of the Parties.

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _______ (indicate name/-s, surname/-s, phone/-s, e-mail/-s)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption “Not Applicable”

# Outsourced processing of personal data (Not Applicable)

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- strategy

- cooperation concept;

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English or Ukrainian .

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English or Ukrainian.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| Relevant Experience: The tenderer must have proven experience in implementing projects related to the development, supply, and/or implementation of software solutions for municipal energy monitoring and energy management systems in Ukrainian communities. The experience shall be confirmed by 2 successfully completed contracts within the last 3 years. | The tenderer shall provide copies of contracts or recommendation letters confirming successful implementation of similar projects in Ukrainian municipalities or public sector institutions. |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.