| DEVELOPMENT METHODOLOGY FOR ASSESSING THE RISKS OF DISASTERS CAUSED BY CLIMATE CHANGE | Project number/ cost centre: 21.9025.4-012.00 / G-011989-012 |
| --- | --- |

Terms of reference

- List of abbreviations

AG			Commissioning party

AN			Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

BMUKN	Federal Ministry for the Environment, Climate Action, Nature Conservation and Nuclear Safety

DRR			Disaster Risk Reduction

EU			European Union

EU4ClimateResilience 	Regional project decarbonization and Climate Resilience in the European Union’s Eastern Partnership

FK			Expert

FKT			Expert days

KZFK			Short-term expert

ToRs			Terms of reference

UNDRR			United Nations Office for Disaster Risk Reduction

- Context

The EU4ClimateResilience project, jointly co-financed by the European Union and the German Federal Ministry for the Environment, Climate Action, Nature Conservation and Nuclear Safety (BMUKN), aims to support Armenia, Azerbaijan, Georgia, the Republic of Moldova, and Ukraine in addressing the challenges posed by climate change. These countries, highly vulnerable to the adverse effects of climate change, face increasingly severe weather events, including heat waves, droughts, forest fires, heavy precipitation, and flooding, which threaten to exacerbate disaster risks, public health concerns, and economic losses. In response, the EaP countries are committed to reducing their carbon footprint and aligning with the European Union’s climate policies, while simultaneously building national capacities to implement the Paris Agreement.

To achieve these goals, the EU4ClimateResilience project focuses on supporting the green transition, enhancing decarbonization efforts, improving energy security, and boosting resilience to climate change impacts. The project’s specific objectives are as follows:

- Increase countries’ capacities to adequately measure and reduce national emissions and adapt to the impact of climate change, and advance the implementation of the climate policy framework.

- Demonstrate the benefits of climate adaptation through specific projects.

- Support the establishment of credible regulatory frameworks on green finance in line with EU norms and to support the diversification and scaling-up of bond issuance.

As part of Outcome 1 — Climate change mitigation policy frameworks and strategies updated and implementation advanced, specifically under Indicator 1.1.3 (Number of technical documents supporting implementation of legal acts), the project foresees the development of a Methodology for assessing the risks of disasters caused by climate change.

Ukraine has committed to implementing the Sendai Framework for Disaster Risk Reduction 2015–2030 and strengthening its disaster risk reduction system. In 2023, the Cabinet of Ministers of Ukraine adopted the Methodology for Assessing the Risk of Emergencies (Resolution No. 836 of 03 October 2023), which establishes the legal basis for developing specialized methodologies, including for natural hazards. Furthermore, pursuant to the Decision of the Accounting Chamber of Ukraine, there is a requirement to develop a comprehensive and standardized methodology for assessing natural disaster risks.

The proposed National Methodology will provide a unified framework for hazard identification, risk analysis, risk evaluation and prioritization, ensuring alignment with international standards, national legislation, and practical needs of government authorities. It will support evidence-based decision-making and strengthen Ukraine’s capacity to manage and reduce natural disaster risks in the context of climate change.

- Tasks to be performed by the contractor

The contractor will be responsible for the design, development, and delivery of a national methodology for natural hazard risk assessment for Ukraine applicable at national, regional and local level, which is aligned with the Sendai Framework, complies with Resolution of the Cabinet of Ministers of Ukraine No. 836 and takes into account the natural hazards in Ukraine (meteorological, hydrological, geological). The work shall be provided in close coordination with relevant stakeholders, under the framework of the EU4ClimateResilience project. The tasks are designed to ensure that the final national methodology serves as unified framework for hazard identification, risk analysis, risk evaluation and prioritization. The emphasis is on defining the main components and steps in a clear, user-oriented manner, so that the resulting analysis and assessments are harmonized, consistent, and fit for the purpose of supporting the Government of Ukraine and other stakeholders in adaptation planning across sectors.

  - Tasks

Task 1 Preparatory stage.

Concept development of National Methodology for assessing the risks of disasters caused by climate change

1.1 Review of national legislative and institutional framework for DRR (up to 5 legislative acts);

1.2 Review of UNDRR, EU and other relevant international DRR tools and approaches;

1.3 Conduct gap analysis between international best practice and the Ukrainian framework;

1.4 Develop a Concept Note for the National Methodology for assessing the risks of disasters caused by climate change (objectives, scope, structure, key principles, alignment with national and international frameworks);

1.5 Organize and conduct a online validation meeting with the Ministry and key stakeholders; During the meeting the Contractor should present draft structure and contents of Methodology and receive the feedback/comments.

1.6 Revise and fix the Concept note based on comments received.

Task 2: Drafting Methodology for assessing the risks of disasters caused by climate change

The Contractor will design a step-wise framework for natural hazard risk assessment, that includes the following elements:

2.1 Harmonisation of Terminology and Risk Concepts: (Product: Glossary)

2.2 Identification and classification of hazards:  Development of a national list of hazards, selection of natural hazards relevant to Ukraine – meteorological, hydrological, geological – and identification of key hazards for each cluster (Product: National Catalogue of Natural Hazards of Ukraine

2.3 Hazard profile, definition of physical nature, spatial and temporal characteristics, triggers, potential impacts, linkages with climate change, cascading effects (Product: Standardized hazard profile for Ukraine)

2.4 Development of risk scenarios for each key hazard: most-likely scenario, worst-case scenario, (where possible) cascading scenario (product: Unified Risk Scenario Sheet template)

2.5 Probability Assessment: For each key hazard (at least 5), hazard scales will be defined: qualitative, semi-quantitative, (where possible) quantitative (Product: Hazard scales for key natural hazards)

2.6 Vulnerability and Impact Assessment: for each key hazard, define indicators and levels of impact for the following categories: human losses, economic losses, damage to critical infrastructure, environmental losses (Product: Set of indicators and impact scales for key natural hazards affecting population, economy, critical infrastructure and environment)

2.7 Risk evaluation and ranking: Develop a unified national risk matrix ensuring comparability across regions and hazards (product: risk matrix), develop a methodology for risk prioritization at national and regional levels (product: national risk profile and regional risk profiles)

2.8 Addressing uncertainty: define approaches for assessing confidence levels and confidence ranges (product: confidence levels and ranges for key natural hazards)

2.9 Development of recommendation for decision makers: Assess the linkage between high risk natural hazards and risk reduction measures, preparedness and response (product: Decision making recommendations for reducing risks from hazardous natural evens in Ukraine)

Task 3 Stakeholder consultation

3.1 Initial online consultation with relevant ministries and competent authorities; State Emergency Service of Ukraine, Ministry of economy, environment and agriculture, Ukrainian Hydrometeorological Center and broader public consultation (civil society, experts, local authorities);

3.2 Refinement of the methodology based on collected comments;

Task 4 Finalisation of the national methodology for assessing the risks of disasters caused by climate change

4.1. National methodology for natural hazard risk assessment, including the following elements:

4.1.1 Executive summary;

4.1.2 Glossary;

4.1. 3 National catalogue of natural hazards of Ukraine;

4.1. 4 Standardized natural hazard profile for Ukraine;

4.1. 5 Risk scenario templates for key natural hazards;

4.1.6 Hazard scales for key natural hazards (meteorological, hydrological, geological);

4.1.7 Indicators and impact scales for population, economy, critical infrastructure, and environment;

4.1.8 National risk matrix for natural hazards in Ukraine;

4.1.9 National and regional natural hazard risk profiles;

4.1.10 National methodology for natural disaster risk assessment in Ukraine;

4.1.11 Decision-making recommendations for reducing risks from hazardous natural events;

4.1.12 List of data sources for natural hazard risk assessment.

4.2 Recommendations for integration into policies and plans;

4.3. Submit finalised Methodology in Ukrainian and English to EU4ClimateResilience project

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| Preparatory stage | May 2026/ Ukraine Remote/ Team leader | Final version of Concept Note for the National Methodology for assessing the risks of disasters caused by climate change. |
| Drafting National Methodology for assessing the risks of disasters caused by climate change | August 2026/ Ukraine, Remote/ Team leader | Draft national methodology with the elements developed described in Task 2. Draft at least 40-page of Methodology with annexes in DOC format. |
| Stakeholder consultation | September 2026/ Ukraine, Remote/ Team leader | Present developed Methodology at consultation meeting with stakeholders, collect all comments during the meeting Provide materials for consultation meeting 2 weeks in advance before meeting in DOC or PPT format |
| Finalisation of the national methodology for assessing the risks of disasters caused by climate change | October 2026/ Ukraine, Remote/ Team leader | Revise draft based on feedback recived during stakeholder consultation Finalise document and annexes Drafted final Methodology approved by Ministry and EU4ClimateResilience |

The contract duration is from 30.04.2026 till 30.11.2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| 1. Final version of Concept Note for the National Methodology for assessing the risks of disasters caused by climate change | Document type: MS Word (.docx) Length: 5 pages (depending on level of detail) Languages: Ukrainian and English Structure: Cover page with title, project reference Introduction (purpose of the Methodology) Proposed chapters and sub-chapters (numbered and clearly structured) Short description of the content of each chapter (1–2 sentences) List of annexes to be included in the full Methodology Submit to EU4ClimateResilince adaptated concept on basis of comments after validation meeting in DOC format | May 2026 |
| 2. Drafting of the National methodology for assessing the risks of disasters caused by climate change | MS Word; 40 pages; Ukrainian and English; aligned with Sendai Framework and national legislation; annexes. | August 2026 |
| 3. Report on Stakeholder consultation and refining of the methodology based on the collected comments | Report in English and Ukrainian up to 4 pages each | September 2026 |
| 4. Submitted National methodology for assessing the risks of disasters caused by climate change | MS Word; 45 pages; Ukrainian and English; aligned with Sendai Framework and national legislation; annexes with examples of datasets, GIS maps, and calculation tools. | October 2026 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2.2) with them.

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1).

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position; multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of Team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- integrating international best practices and analytical tools into the methodology

- analysis of UNDRR, EU and other international approaches to natural risk assessment, and ensuring methodological alignment with international standards

- contribute to probability assessment, vulnerability analysis, and risk ranking, support the development of hazard profiles and risk scenarios, and lead the preparation of risk maps and spatial analysis

- Present work during validation meeting and stakeholder consultations, contribute to decision-support recommendations, and lead the preparation of the finalized methodology document.

- Translate into Ukrainian and English Methodology, submit to EU4ClimateResilience

Qualifications of Team leader

- Education/training (2.1.1): university degree (PhD) in Environmental Safety

- Language (2.1.2): C1-level language proficiency: in English

- General professional experience (2.1.3): 6 years of professional experience in the climate services and adaptation sector

- Specific professional experience (2.1.4) 6 years in climate risk and vulnerability assessment sector

## Key expert 1

Tasks of key expert 1

- responsible for the development of the core methodological framework for natural hazard risk assessment, with a focus on national context and hazard characterization

- analysis of the national legislative and institutional framework, identification of relevant natural hazards, and development of hazard profiles and risk scenario templates

- conduct probability assessments, vulnerability and impact analysis, and lead the risk assessment and ranking process

- contribute to recommendations for decision-making,

- participate as a presenter at validation meeting and stakeholder consultations and support the finalization of the methodology.

Qualifications of key expert 1

- Education/training (2.2.1): university degree (PhD) in Geography, specialising in Meteorology, Climatology and Agrometeorology

- Language (2.2.2): C1-level language proficiency in Ukrainian

- General professional experience (2.2.3) 6 years of professional experience in climatology sector

- Specific professional experience (2.2.4) 6 years of experience in meteorology

# Costing requirements

## Contracts for works:

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| № of milestone | Milestones/partial works | Estimated expert days for orientation | Anticipated deadline/place/person responsible |
| --- | --- | --- | --- |
| 1 | Preparatory stage | TL: 3 man-days KE 1: 3 man-days Total 6 man-days | May 2026 |
| 2 | Drafting of the National methodology for assessing the risks of disasters caused by climate change | TL 52 man-days KE 1: 52 man-days Total: 104 man-days | August 2026 |
| 3 | Stakeholder consultations | TL: 2,5 man-days KE 1: 2,5 man-days Total: 5 man-days | September 2026 |
| 4 | Preparation of the finalized version of the methodology | TL: 2,5 man-days KE 1: 2,5 man-days Total: 5 man-days | October 2026 |

# Inputs of GIZ or other actors

All materials developed under this contract (including but not limited to publications, presentations) must include the logos of the following donors:

- European Union (EU)

- Federal Ministry for the Environment, Nature Conservation, Nuclear Safety and Consumer Protection (BMUKN)

- International Climate Initiative (IKI)

- Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ)

The contractor will be provided with the required logos, branding guidelines, and instructions once the contract implementation begins.

In addition, the following disclaimer must be visibly included on all produced materials:

“This <publication/film/website> has been produced with the assistance of the European Union and the Federal Ministry for the Environment, Climate Action, Nature Conservation and Nuclear Safety (BMUKN). Its contents are the sole responsibility of <contractor> and do not necessarily reflect the views of the European Union and BMUKN.”
The placeholder <contractor> should be replaced with the name of the organization or individual contracted under this ToR.

and 

EU4ClimateResilience: Decarbonisation and Climate Resilience in the Eastern Partnership. The EU4ClimateResilience project is a strategic initiative aimed at supporting the green transition, enhancing decarbonisation and increasing climate resilience in the Eastern Partnership (EaP) countries: Armenia, Azerbaijan, Georgia, Moldova and Ukraine. Implementing Partners: Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and the Organisation for Economic Cooperation and Development (OECD)

Failure to comply with these visibility requirements may result in a request for revision of the materials before approval.

GIZ and/or other actors are expected to make the following available:

- The contractor will coordinate closely with GIZ Ukraine.

- Provide developed materials 2 weeks in advance before final or public submission

- GIZ will facilitate introductions to relevant institutions and support stakeholder engagement where needed.

- GIZ will support logistics for consultations

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, excl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment within 15 working days in two instalments: for milestones 1–2 and 3–4.;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) and  submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF) etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- Each invoice and act of acceptance shall contain the Project Number, contract number

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

- Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The Contract /Supplement to this Contract (if any) enter into force upon its signing by the Parties.

If there are two different dates, then the signing date of the Contract/Supplement to this Contract (if any) is considered to be the last date of signature of one of the Parties.

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local) published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _______ (indicate name/-s, surname/-s, phone/-s, e-mail/-s)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

The given procurement of works upon the Contract shall be carried out at the funds of the Project of International Technical Assistance (Project ITA), PN: 2021.9025.4, Project title “Підтримка країн Східного партнерства в їх наближенні до Green Deal / EU4ClimateResilience (PROGRESS /EU4ClimateResilience) ”, registered by the Secretariat of the Cabinet of Ministers of Ukraine (registration card of the project (program) No. 6213 dated 30.09.2025) and complies with the category (type) of Services specified in the purchase plan available at address https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel

The above-mentioned ITA project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008.

The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, then the Contractor must notify GIZ of such VAT registration in writing or in electronic form by means of submission of an e-mail with copy of the Excerpt from VAT Registration Registry to the GIZ’s e-mail address indicated in the details of the Contract. The Contractor must submit the mentioned notification to the GIZ not later than 1 calendar day following the day of VAT registration.

At the same time the Parties agreed that the purchase of Services after the VAT registration of the Contractor shall be exempt from VAT in accordance with the abovementioned.

# Outsourced processing of personal data  “Not Applicable”

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

CVs of all experts with relevant work experience, qualifications.

- The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in Ukrainian (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Financial bid (Price schedule)

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (Price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.