| Legal support for technical regulation, market surveillance, general product safety and consumer protection | Project number/ cost centre: G-012550.003/ 24.2122.0-003.00 |
| --- | --- |

Terms of reference

- List of abbreviations

ACAA                  Agreement on Conformity Assessment and Acceptance of Industrial Products

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

EU                       European Union

FK	Expert

FKT	Expert days

KZFK	Short-term expert

MEEA                  Ministry of Economy, Environment and Agriculture of Ukraine

ToRs	Terms of reference

- Context

The Project “Support for Ukraine's EU accession process in the economic sector” (STEP IN 2 EU) (further referred to as – Project) aims at improving the framework for Ukraine's accession negotiations with the EU including the Copenhagen criteria, Association Agreement between the EU and its member states on the one hand and Ukraine on the other (AA) as well as Ukraine’s Strategies and plans related to performance of the EU integration commitments. This includes support to alignment of Ukraine’s economic policies with the EU requirements in the context of the EU accession.

According to the European Commission's Report of 2025 on Ukraine's progress towards the EU accession, Ukraine must bring its legislation into line with the requirements of EU acquis on general product safety, market surveillance, and for the conclusion of the ACAA. Bringing Ukrainian legislation into line with EU acquis in these areas is a key condition for the integration of Ukrainian business into the EU Single Market and is the subject of negotiations on accession to the EU within the framework of the negotiation Cluster 2 "Internal Market".

To perform the EU integration commitments there is a need to develop the new draft Law on general product safety, and related by-laws, procedures regarding the carrying out of market surveillance online inspections, sampling, risk assessment, preparation of checklists by market surveillance authorities and monitoring of products made available on the market, development of legal acts in order to  transpose EU acquis for the EU integration and ACAA conclusion as well as development of a notification procedure for conformity assessment bodies. In addition, the MEEA may need support in transposing EU acquis in the area of consumer protection regarding such aspects as general consumer protection, representative action for the protection of collective consumer interests, alternative consumer disputes resolution etc.

Given the intensity of this process and the complexity of tasks implying highly specialized knowledge the MEEA needs sectorial and legal support.

- Tasks to be performed by the contractor

The overall objective of the assignment is to provide legal support to the Department of Technical Regulation and the Department of Regulatory Policy and Entrepreneurship of the MEEA in creation of conditions for economic integration into the EU market and to the process of preparing for the signing of the ACAA as part of the accession to the EU.

  - Tasks

The contractor is responsible for providing the following services:

    - Legal support for the alignment of Ukraine’s legislation with EU acquis related to general product safety, market surveillance and consumer protection – up to 80 Expert-days

    - Legal support for the alignment of Ukraine’s legislation in the field of technical regulation and conformity assessment with EU acquis – up to 80 Expert-days

    - Advice in supporting draft legal acts during their public discussion and inter-governmental consultations – up to 40 Expert-days

    - Expert support in analysis of and feedback within negotiation process on ACAA conclusion and EU accession regarding tasks agreed with GIZ – up to 15 Expert days

    - Development of information materials for business, participation as expert or trainer on topics of this assignment in public private dialogue events, awareness raising events of the MEEA or trainings conducted for MEEA or other partners of the project agreed with GIZ – up to 25 Expert-days.

The number of days can be redistributed between tasks in agreement with GIZ.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| 1. For the tasks 2.1.1, 2.1.2, 2.1.3: initial analysis, proposals, comments and advice for draft legal acts | 01.07.2026, Kyiv, Contractor |
| 2. For the tasks 2.1.1, 2.1.2, 2.1.3: initial analysis, proposals, comments and advice for draft legal acts | 05.10.2026, Kyiv, Contractor |
| 3. For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5: additional proposals, comments and advice for draft legal acts following consultations with MEEA, analysis and feedback, explanatory notes, summaries for negotiation process, information materials for business, participation in awareness raising events/training | 04.01.2027, Kyiv, Contractor |
| 4. For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5: additional proposals, comments and advice for draft legal acts following consultations with MEEA, analysis and feedback, explanatory notes, summaries for negotiation process, information materials for business, participation in awareness raising events/training | 01.04.2027, Kyiv, Contractor |
| 5. For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5: additional proposals, comments and advice for draft legal acts following consultations with stakeholders, analysis and feedback, explanatory notes, summaries for negotiation process, information materials for business, participation in awareness raising events/training | 01.07.2027, Kyiv, Contractor |
| 6. For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5: additional proposals, comments and advice for draft legal acts following intergovernmental consultations, analysis and feedback, explanatory notes, summaries for negotiation process, information materials for business, participation in awareness raising events/training | 04.10.2027, Kyiv, Contractor |
| 7. For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5: additional proposals, comments and advice for draft legal acts following expertise of public authorities, analysis and feedback, explanatory notes, summaries for negotiation process, information materials for business, participation in awareness raising events/training | 03.01.2028, Kyiv, Contractor |
| 8. For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5: additional proposals, comments and advice for draft legal acts following expertise of public authorities, analysis and feedback, explanatory notes, summaries for negotiation process, information materials for business, participation in awareness raising events/training | 03.04.2028, Kyiv, Contractor |

The contract duration is from 30.04.2026 till 31.08.2028.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Interim report 1: For the tasks 2.1.1, 2.1.2, 2.1.3 - initial analysis, proposals, comments and advice for draft legal acts | Minimum 3 documents in РDF and Word format, language Ukrainian | 01.07.2026 |
| Interim report 2: For the tasks 2.1.1, 2.1.2, 2.1.3 - initial analysis, proposals, comments and advice for draft legal acts | Minimum 3 documents in РDF and Word format, language Ukrainian | 05.10.2026 |
| Interim report 3: For the tasks 2.1.1, 2.1.2, 2.1.3.2, 2.1.4, 2.1.5 – additional proposals, comments and advice for draft legal acts, analysis and feedback, explanatory notes, summaries, materials related to awareness raising/training | Minimum 5 documents in РDF and Word format, language Ukrainian, materials for participation in public events | 04.01.2027 |
| Interim report 4: For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5 – additional proposals, comments and advice for draft legal acts, analysis and feedback, explanatory notes, summaries, materials related to awareness raising/training | Minimum 5 documents in РDF and Word format, language Ukrainian аnd/ог English | 01.04.2027 |
| Interim report 5: For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5 – additional proposals, comments and advice for draft legal acts, analysis and feedback, explanatory notes, summaries, materials related to awareness raising/training | Minimum 5 documents in РDF and Word format, language Ukrainian аnd/ог English | 01.07.2027 |
| Interim report 6: For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5 – additional proposals, comments and advice for draft legal acts, analysis and feedback, explanatory notes, summaries, materials related to awareness raising/training | Minimum 5 documents in РDF and Word or RTF format, language Ukrainian аnd/ог English | 04.10.2027 |
| Interim report 7: For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5 – additional proposals, comments and advice for draft legal acts, analysis and feedback, explanatory notes, summaries, materials related to awareness raising/training | Minimum 5 documents in РDF and Word or RTF format, language Ukrainian аnd/ог English | 03.01.2028 |
| Final report 8: For the tasks 2.1.1, 2.1.2, 2.1.3, 2.1.4, 2.1.5 – additional proposals, comments and advice for draft legal acts, analysis and feedback, explanatory notes, summaries, materials related to awareness raising/training | Minimum 5 documents in РDF and Word or RTF format, language Ukrainian аnd/ог English | 03.04.2028 |

- Concept (technical-methodological design)

## Technical-methodological concept

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation. The tenderer is required to explain the approach for the capacity development of the MEEA staff.

- Personnel concept (proposed staff)

## For the implementation of above-mentioned tasks only 1(one) Expert shall be assigned.

## The bidder is required to provide his/her CV of the Expert, describing in detail the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points.

Tasks of Key expert

Acc. to the cl. 2.1.1 - 2.1.5 of the ToR

Qualifications of Key expert

- Education/training (2.2.1): university degree of Master in Law

- Language (2.2.2): in Ukrainian C2 level (6 points) and in English C1 level (4 points)

- General professional experience (2.2.3): 7 years of professional experience in policy development with consideration of European integration commitments of Ukraine.

- Specific professional experience (2.2.4):

- 7 years in legal drafting and expertise on compliance with the EU acquis in the fields of technical regulation, conformity assessment, product safety, market surveillance and consumer protection (6 points).

- 3 years of legal expertise and advice in order to support state authorities in negotiations and consultations with the European Commission regarding gradual integration into the EU market (4 points).

- Regional experience (2.2.6): Ukraine 5 years (6 points); experience in 3 European or developing/transitional economy countries (4 points).

- Other (2.2.8): 5 years in concurrence and promotion of draft legal acts during public consultations, consideration in the Cabinet of Ministers of Ukraine and the Parliament of Ukraine.

Soft skills of Key expert

In addition to their specialist qualifications, the following qualifications are required of the expert:

- Initiative

- Communication skills

- Efficient, partner-focused working methods

- Interdisciplinary thinking

# Costing requirements

## Assignment of personnel and travel expenses

Travel is not foreseen. Activities will be online or offline in Kyiv.

| Fee days | Unit of measurement | Number of experts | Total number of days, up to | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of Expert 1 | Expert-days | 1 | 240 |  |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors N/A

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of services completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Anticipated payment of up to % from total contract value | Deliverables and reporting |
| --- | --- | --- | --- |
| 1 Interim payment | 22.07.2026 | 12.5% (30 expert days) | Acc. to cl.2.2. – Interim report 1 |
| 2 Interim payment | 26.10.2026 | 12.5% (30 expert days) | Acc. to cl. 2.2. – Interim report 2 |
| 3 Interim payment | 25.01.2027 | 12.5% (30 expert days) | Acc. to cl. 2.2. – Interim report 3 |
| 4 Interim payment | 22.04.2027 | 12.5% (30 expert days) | Acc. to cl. 2.2. – Interim report 4 |
| 5 Interim payment | 22.07.2027 | 12.5% (30 expert days) | Acc. to cl. 2.2. – Interim report 5 |
| 6 Interim payment | 25.10.2027 | 12.5% (30 expert days) | Acc. to cl. 2.2. – Interim report 6 |
| 7 Interim payment | 24.01.2028 | 12.5% (30 expert days) | Acc. to cl. 2.2. – Interim report 7 |
| 8 Final payment | 24.04.2028 | 12.5% (30 expert days) | Acc. to cl. 2.2. – Final report 8 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, and VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid for Expert days as post payment upon performance (acc.to cl.5) in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed services (“up to”), on the ground of original invoices, acts of acceptance and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment;

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

- Each invoice and act of acceptance shall contain the Project Number and contract number.

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed works /services standard template (obligatory for use) can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

The Contract /Supplement to this Contract (if any) enter into force upon its signing by the Parties.

If there are two different dates, then the signing date of the Contract/Supplement to this Contract (if any) is considered to be the last date of signature of one of the Parties.

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _______ (indicate name/-s, surname/-s, phone/-s, e-mail/-s) (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption N/A

# Outsourced processing of personal data N/A

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used). Technical bid must include information about contribution to knowledge management at the partner and at GIZ and to promote scaling-up effects under learning and innovation.

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

- CV with relevant work experience, qualifications (education, certificates).

The CV of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CV shall not exceed 4 pages. They must clearly show the position and job the proposed person held in the reference project and for how long. The CV must be drawn up in English.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| A. Minimum requirements for references At least 3 reference projects with a minimum commission value 5000 EUR in approximation of legislation to the EU acquis, consultancy services to public institutions (e.g. ministries) in the fields of technical regulation and conformity assessment or product safety, market surveillance, consumer protection in the past three financial years. | Self-declaration of Eligibility |
| B. Minimum requirements for regional experience At least 1 reference project with a minimum commission value 5000 EUR in approximation of legislation to the EU acquis, consultancy services to public institutions (e.g. ministries) in the fields of technical regulation and conformity assessment or product safety, market surveillance, consumer protection in Ukraine in the past three financial years. | Self-declaration of Eligibility |
| C. Minimum requirements for average annual turnover At least 15000 EUR/765 000 UAH average annual turnover for the past three financial years. | Self-declaration of Eligibility |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.