| Support to implementation and facilitation of Trainings | Project number/ cost centre: G-012241-001 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

- Context

Description of the project

The project “Strengthening of Urban Resilience in the Areas of Supply Infrastructure and Housing in Ukraine (SUR)” was registered by the Secretariat of the Cabinet of Ministers of Ukraine on August 13, 2024, under number 2023.1821.0 (project registration card No. 5620-04).

The GIZ transitional development assistance project “Strengthening of Urban Resilience in the Areas of Supply Infrastructure and Housing” (SUR), financed by the German Federal Ministry for Economic Cooperation and Development (BMZ) focuses on the repair and rehabilitation of critical supply infrastructure and services as a contribution to municipal civil protection, as well as urban resilience and the rehabilitation, repair, and creation of municipal and private housing as a contribution to social resilience in Ukraine. The goal of the project is to strengthen municipal services of general interest systematically in selected cities and city communities. Urban resilience is the ability of an urban system to react resiliently in the event of crises, while at the same time adapting, reshaping, and strengthening itself in terms of sustainable urban development. The project is part of the transitional development assistance fields of action reconstruction of basic infrastructure and services as well as disaster risk management.

In the area of disaster risk management, the SUR project focuses primarily on war-related dangers and risks (e.g., dangers to the population from shelling, destruction of critical and social infrastructure, housing) in the ongoing war context of Ukraine. Additionally, natural and climate hazards are considered. The project works with cities and municipalities and aims at supporting the development of systematic disaster risk management approaches in municipalities, particularly in risk analysis, disaster prevention, and structural preparedness for disasters, to effectively protect their residents in acute emergencies.

Background information and objective of the service

The Council of the European Union (2024) pointed out that dependence on resilient critical infrastructures (CI) that provide services essential to the maintenance of vital societal functions, economic activities, public health and safety, or the environment is fundamental to the smooth functioning of the internal market and society as a whole. The growing interdependencies between infrastructure sectors are the result of an increasingly interdependent network of service provision using nationwide key infrastructure in the areas of energy, transport, drinking water, wastewater, food production, processing and distribution, health, space and digital infrastructure, and the public administration sector.

Targeted attacks on CI pose a serious threat to the stability and security of the country. Such attacks can affect power grids, water supplies, communication systems or other vital facilities. The attacks affect the supply of the population, disrupt the economy and make it difficult to maintain state functions. The consequences are not limited to the facilities affected but also lead to functional failures of other dependent (critical) infrastructures. This is precisely why the CI is at the centre of Russian attacks, as the effects of disruptions in the provision of services have multiple spatial effects that extend far beyond the site of the attack.

Before this background, the project engages in the following activity: “Employing cascade chain analysis for critical infrastructure”.

In this context, the TU Dortmund University (Technische Universität Dortmund) has developed a framework for assessing the criticality of supply infrastructure. A central element of the framework is the concept of cascade chains, which help uncover the impact of supply disruptions on other public or private services in other infrastructure sectors and areas that are not directly exposed to a specific event. These cascade chains must be understood and their spatial-temporal dimensions analysed. However, experts in the various infrastructure sectors are not necessarily aware of which sectors depend on their services and what interdependencies exist, as well as how responsibilities are distributed and which actors are involved.

In response, the manual “Participatory criticality assessment of critical infrastructure at the local level” has been developed. It is intended to be used by administrators at local and regional levels as well as operators of CI to assess the criticality of individual CIs and to identify cascading effects due to (critical) infrastructure failures. The manual is intended to serve as an easy to generate evidence basis for informing and supporting risk governance, connecting responsible actors, aiming at a more resilient management of CI systems in the future and for improving crisis resilience.

The objective of the service is to support the implementation of the participatory criticality assessment of critical infrastructure at the local level, through the facilitation of in person workshops in cities which will implement the manual described above.

Additionally, the project is working on supporting cities in developing and implementing crisis response capacities on a municipal level through the human centered crisis management approach. Human centred crisis management directly addresses the qualifications and capacities of individuals to adequately respond and act in crisis situations. It structures procedures in institutions such as municipal administrations and ensures the maximum functionality of systems and organizations. In the event of external shocks (e.g. war related attacks and damages), municipal administrations can rely on established procedures, rules and responsibilities to balance shortages and ensure the quickest possible return to normal functioning. Thus, human centred crisis management is an immediate contribution to strengthen urban resilience and support systematic disaster risk management.

The project has developed human centered crisis management training modules which are to be implemented in 5 selected cities. The goal is to convey the developed training materials, facilitate the workshop format and support participants in gaining the maximum benefit from the training measures.

- Tasks to be performed by the contractor

The contractor is responsible for providing the following services

WP 1: Facilitation of three (3) workshops each in two (2) pre-selected cities in Ukraine for the implementation of participatory risk assessment manual (approx 22 Expert days)

The contractor will conduct three (3) workshops each in two (2) pre-selected cities in Ukraine. Based on the identified CI assets at the local level and the differentiation of CI assets according to their importance, the first workshop covers the assessment of dependencies between supply infrastructures. Based on a pre-defined hazard scenario, the second workshop aims at identifying cascading effects of CI asset failures and their effects on goods and services. The validation of cascading effects and interdependencies can be conducted afterwards via interviews (not a task for the contractor). and the identification of dependencies of CI assets on goods and services. For the third workshop, the contractor facilitates coordination meetings between politicians and the administration to define protection goals, do an actual-target comparison and finally the discussion and selection of recommendations. Final task of the contractor is the creation of a summary report per city, highlighting the key findings and recommending actions.

- For all tasks the contractor is required to coordinate closely with TU Dortmund.

- Each workshop will last one (1) day, travel to the respective city is required for the contractor.

- The contractor is required to become familiar with the manual and its technical contents through exchange meetings with TU Dortmund.

- Guide the implementation process of the manual and support participants throughout the process.

- If necessary provide feedback on training materials in terms of feasibility to the Ukrainian context (rules, regulations, laws, other aspects) and provide grounded input for the adaptation of the training materials and training delivery methods.

- The contractor is required for all communication and coordination prior, during and after the workshops with TU Dortmund, interpreters, participants and SUR Project. SUR Project is responsible for organzing translation.

- Ensure technical facilitation of the hybrid formats for workshops across all workshops (coordination with translation services, technical set up, ect.) in coordination with SUR Project and TU Dortmund. Each workshop will require one day on site in the respective city.

- Set up a list of relevant entities/stakeholders to be taking parts in the workshops and that need to be involved in the process, in coordination with SUR Project and TU Dortmund

- If necessary, provide input to the SUR contractor on improvement of training material on pedagogic and methodological aspects and other areas related to achieving success in training implementation.

- Coordinate with GIZ project management regarding scheduling, invitations, logistics, security considerations and any other technicalities.

- Organize all aspects of training preparation (regarding scheduling, invitations, logistics, security considerations and any other technicalities) in close coordination with TU Dortmund and SUR Project

- Conducting hybrid workshop 1 in two (2) pre-selected cities based on the manual and in close collaboration with TU Dortmund

  - Facilitate the online participation of TU Dortmund during the workshop.

  - Document workshop results of the assessment of dependencies between supply infrastructures in the form of tables or fact sheets.

  - Facilitate discussion among participants in workshop 1, using a format developed by TU Dortmund.

  - Potentially support in further documentation and facilitation measures as defined by TU Dortmund.

  - Ensure filling out of all administrative forms required by SUR Project by the participants after the workshop.

- Conducting hybrid workshop 2 in two (2) pre-selected cities based on the manual and in close collaboration with TU Dortmund

  - Facilitate the online participation of TU Dortmund during the workshop.

  - Facilitate workshop 2 on identifying cascading effects of CI asset failures and their effects on goods and services in a format defined by TU Dortmund.

  - Synthesize and standardize outputs from workshop 2 into clear, visually comprehensible formats (e.g. PowerPoint).

  - Potentially support in further documentation and facilitation measures as defined by TU Dortmund.

  - Ensure the completion of a post-evaluation survey by the participants of the workshops as contribution to the results-based monitoring.

  - Ensure filling out of all administrative forms required by SUR Project by the participants after the workshop.

- Conducting hybrid workshop 3 in two (2) pre-selected cities based on the manual and in close collaboration with TU Dortmund

  - Facilitate the online participation of TU Dortmund during the workshop.

  - Facilitate workshop 3 on coordination meetings between politicians and the administration to define protection goals, do an actual-target comparison and finally the discussion and selection of recommendations in a format defined by TU Dortmund.

  - Synthesize and standardize outputs from workshop 3 into clear and approved recommendations.

  - Potentially support in further documentation and facilitation measures as defined by TU Dortmund.

  - Ensure the completion of a post-evaluation survey by the participants of the workshops.

- Creating a summary report per city, highlighting the key findings and recommending actions.

WP 2: Facilitation of five (5) trainings, one (1) in each pre-selected citiy in Ukraine on human centered crisis management (approx 22 Expert days)

The contractor will conduct five (5) trainings, one (1) in each pre-selected city in Ukraine.

If needed, for all tasks the contractor is required to coordinate closely with the SUR partner who has developed the training materials.

The contractor is to perform the following tasks:

- The contractor is required to become familiar with the training materials and its technical contents through exchange meetings with the SUR Contractor.

- If needed, The contractor is required to thoroughly review the training materials and if necessary adapt them to reflect Ukrainian laws/rules/legislations/common practices in the area of crisis management at a municipal level in order to maximize the success of trainings implementation.

- If needed, The contractor is required to coordinate with the five pre selected cities in which the trainings are to be conducted, in order to incorporate specific needs and demands into the existing training materials. The contractor should ensure that training materials reflect the reality and needs by the cities.

- If deemed necessary by the contractor and/or SUR project the contractor is to develop and deliver new/additional training modules in order to reflect the needs of the cities in terms of municipal crisis management. The training duration for each city remains the same.

- Facilitate the training measures in the cities through 2-3 day in person workshops in the respective city and support participants throughout the process.

- The contractor is required for all communication and coordination prior, during and after the workshops with the contractor, interpreters, participants, and SUR Project.

- Ensure technical facilitation of the trainings across all workshops (technical set up, ect.) in coordination with SUR Project and if nessecary the SUR Contractor. Each workshop will require 2-3 days on site in the respective city. The contractor is required to travel to the respective city.

- Dates for the trainings are to be identified in coordination with the trainees, SUR Project and if nessecary the contractor

- Coordinate with GIZ project management regarding scheduling, invitations, logistics, security considerations and any other technicalities.

- Organize all aspects of training preparation (regarding scheduling, invitations, logistics, security considerations and any other technicalities) in close coordination with if nessecary the SUR Service provider and SUR Project

- Set up a list of relevant entities to be taking parts in the trainings and that need to be involved in the process, in coordination with SUR Project and if nessecary  the SUR Contractor.

- For all trainings

  - Facilitate the trainings.

  - Ensure adequate participation and engagement by the trainees.

  - Ensure filling out of all administrative forms required by SUR Project by the participants after the workshop.

  - Ensure the completion of a pre- and post-evaluation survey by the participants of the workshops.

  - Creating a summary report per city, documenting workshop results in photographic and written form and highlighting lessons learnt.

WP 3: Technical Expertise and Advisory for Training development and delivery (approx. 10 Expert days)

- Offering responsive expert guidance and inputs to the SUR project and SUR Contractors , addressing specific challenges, questions, or issues related to development and delivery of trainings, guidance on developing and adapting training materials, input on methods of training delivery, adaptation of training materials to target audiences and pedagogic requirements to achieve successful training measures.

- Advising on the conceptualization and drafting of tender documents for training activities

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |  |
| --- | --- | --- |
| WP 1 Identify stakeholder groups for both cities | By 05.2026/Contractor/Ukraine/online |
| WP1 Conduct hybrid workshop 1 in cities 1 and 2 including the online participation of TU Dortmund, the documentation of workshop results | By 05.2026/Contractor/Ukraine |
| WP1 Conduct hybrid workshop 2 in cities 1 and 2 including the online participation of TU Dortmund, the documentation of workshop results | By 05.2026/Contractor/Ukraine |
| WP1 Conduct hybrid workshop 3 in cities 1 and 2 including the online participation of TU Dortmund, the documentation of workshop results, | By 05.2026/Contractor/Ukraine |
| WP 2 If needed rework training packages for all five cities, if necessary develop additional/new training modules | By end 05.2026/Contractor/Online |
| WP 2 Identify stakeholder groups for all 5 cities | By end 05.2026/Contractor/Online |
| WP 2 Conduct training in city 1 | By end 05.2026/Contractor/Ukraine |
| WP 2 Conduct training in city 2 | By 06.2026/Contractor/Ukraine |
| WP 2 Conduct training in city 3 | By 06.2026/Contractor/Ukraine |
| WP 2 Conduct training in city 4 | By 06.2026/Contractor/Ukraine |
| WP 2 Conduct training in city 5 | By 06.2026/Contractor/Ukraine |
| WP 3 Advisory | Ongoing/Contractor/online |

The contract duration is from 25.04.2026 till 30.07.2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| WP1 Identification of relevant entities within the city administration to participate in workshops | Excel file in English | 05.2026 |
| WP1 Documentation of results of workshop 1 in each city (2 reports) | Word document, photo documentation, in English | 05.2026 |
| WP1 Documentation of results of workshop 2 in each city (2 reports) | Word document, photo documentation, in English | 05.2026 |
| WP1 Documentation of results of workshop 3 | Excel file, Word document,, photo documentation PowerPoint, in English | 05.2026 |
| WP2 If needed reworked training packages for 5 cities | PPT/Word files, Ukrainian | 05.2026 |
| WP 2 Identification of relevant entities within the city administration to participate in trainings | Excel file | 05.2026 |
| WP2 Documentation of results of Training in city 1 | Word document, photo documentation, in English | 05.2026 |
| WP2 Documentation of results of Training in city 2 | Word document, photo documentation, in English | 05.2026 |
| WP2 Documentation of results of Training in city 3 | Word document, photo documentation, in English | 06.2026 |
| WP2 Documentation of results of Training in city 4 | Word document, photo documentation, in English | 06.2026 |
| WP2 Documentation of results of Training in city 5 | Word document, photo documentation, in English | 06.2026 |
| WP3 | To be determined based on advisory services | ongoing |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

Not applicable

## Further requirements (1.7)

Not applicable

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 11), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Key expert 1

Tasks of key expert 1

- Coordination and ensuring communication with GIZ, Partners and others involved in the project

- Regular reporting in accordance with the deadlines

Qualifications of key expert 1

- Education/training (2.2.1): Masters university degree in the area of Disaster Risk Reduction, Emergency management, Security Studies, Critical Infrastructure Management, teaching or a related field.

- Language (2.2.2): C2-level language proficiency in Ukrainian (5 points); C1 -level proficiency in English (5points

- General professional experience (2.2.3): 7 years of professional experience in facilitation and moderation of workshops/trainings

- Specific professional experience (2.2.4): 2 years of experience in developing training materials (5 points), 1 year experience in designing tabletop exercises and/or running live simulations (5 points)

- Regional experience (2.2.6): 2 years of experience in projects in Ukraine

- Development cooperation (DC) experience (2.2.7): 1 years of experience in DC projects

- Other (2.2.8.): 2 years experience in emergency response operations, Disaster response coordination, Security or public safety operations or Institutional crisis leadership

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations and reporting documents are to be observed. See Annex 1 to these Terms of Reference.

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of key expert | days | 1 | 54 |  |
| Travel expenses | Unit of measurement | Quantity |  | Comments (if any) |
| Fixed travel budget | limit | Up to 280.500 UAH |  | A budget is earmarked for travel to the following countries: Ukraine. A fixed budget of UAH 280.500 is earmarked for settling travel expenses against evidence/performance. This amount includes accommodation, per diems, travel costs (train, compensation for own transport 13,71 UAH/km, taxi, bus, travel by taxi/car for the entire route is permitted if security situation requires it after approval by SUR Project)., Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. |
| Other costs | Unit of measurement | Quantity |  | Comments (if any) |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors

TU Dortmund, GIZ and other actors are expected to make the following available:

- TU Dortmund is required to provide a full briefing and access to training materials beforehand to the contractor in preparation of the workshops.

- SUR Service Provider is responsible to provide full access to training material beforehand and maintain a close relationship with the contractor during the implementation of the trainings.

- Logistics for workshops: Translation services to be organized by GIZ; Workshop location to be organized by Workshop recipient, technical equipment for workshops is to be provided by Workshop recipient

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the commercial bid.

Anticipated payment schedule:

In consideration of services completed, the Contractor shall be paid in the following instalments:

| Instalment # | Anticipated payment date | Payment of up to % from total contract value | Deliverables and reporting |
| --- | --- | --- | --- |
| 1 Interim payment | 30.04.2026 | 30% | Acc to 2.1 |
| 2.Interim Payment | 30.05.2026 | 50% | Acc to 2.1 |
| 2 Final payment | 15.06.2026 | 20% | Acc to 2.1 |

  - Financial proposal

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees,  incl. VAT if applicable).

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- Each invoice and act of acceptance shall contain the Project Number, contract number

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not  a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor ____

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- VAT Exemption

Not Applicable

# Outsourced processing of personal data

Not Applicable

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English.

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. Information on additional pages will not be considered for evaluation. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English .

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Commercial bid

The commercial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Commercial bid must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

| The tenderer is obliged to conform to the following eligibility requirements: | The tenderer must provide the following document to confirm the compliance with eligibility requirements: |
| --- | --- |
| Experience in delivering trainings in Ukraine | One Training report on a training conducted in Ukraine (PDF Format; min 2 pages) |
| Experience in developing training materials | Two sets of training materials for a multi-day training including training methodologies applied (PDF/PPT Format; min 5 pages) |
| Provision of one reference project in Ukraine | Filled Self declaration of eligibility with Annex: Overview of reference projects in Ukraine (PDF Format;) |

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Option

Depending on the needs of SUR Projects partners as well as SUR Project itself the following Options can be drawn. The decision on the drawing of Option will approximately be made by June 2026.

  - Option 1

  - Type and scope

In addition, the following tasks should be completed by the contractor:

WP 4 Facilitation of additional Workshops/Trainings: Content to be determined (approx 20 Expert days)

- The contractor is required to become familiar with the training materials and its technical contents through exchange meetings with the SUR Contractor.

- Facilitate the training measures/Workshops of up to 3 days each on site, up to 4 trainings/Workshops.

- If necessary, provide input to the SUR contractor on improvement of training material on pedagogic and methodological aspects and other areas related to achieving success in training implementation.

- Ensure technical facilitation of the trainings /Workshops (technical set up, ect.) in coordination with SUR Project and the SUR Contractor.

- Coordinate with GIZ project management regarding scheduling, invitations, logistics, security considerations and any other technicalities.

- Organize all aspects of training preparation (regarding scheduling, invitations, logistics, security considerations and any other technicalities) in close coordination with other entities and SUR Project

- Dates for the trainings are to be identified in coordination with the trainees, SUR Project and the contractor.

- For all trainings

  - Facilitate the workshops and pre-defined formats

  - Ensure technical facilitation of in person formats or hybrid formats across all workshops/trainings (coordination with translation services, technical set up, ect.) in coordination with SUR Project and the SUR service provider

  - Ensure adequate participation and engagement by the trainees.

  - Ensure filling out of all administrative forms required by SUR Project by the participants after and before the workshop.

  - Ensure the completion of a pre- and post-evaluation survey by the participants of the workshops.

  - Coordinate with GIZ project management regarding scheduling, logistics, and security considerations.

  - Creating a summary report per city, documenting workshop results in photographic and written form and highlighting lessons learnt.

WP 5: Technical Expertise and Advisory for for Training development and delivery (approx 10 Expert days)

- Offering responsive expert guidance and inputs to the SUR project and SUR Contractors , addressing specific challenges, questions, or issues related to development and delivery of trainings, guidance on developing and adapting training materials, input on methods of training delivery, adaptation of training materials to target audiences and pedagogic requirements to achieve successful training measures.

- Advising on the conceptualization and drafting of tender documents for training activities

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |  |
| --- | --- | --- |
| WP 4 Conduct workshop 1 | By 08.2026/Contractor/Ukraine |
| WP 4 Conduct workshop 2 | By 08.2026/Contractor/Ukraine |
| WP 4 Conduct workshop 3 | By 09.2026/Contractor/Ukraine |
| WP 4 Conduct workshop 4 | By 09.2026/Contractor/Ukraine |
| WP 5 Advisory | Ongoing/Contractor/online |

  - Reporting and deliverables

The Contractor will be responsible for the following:

| # | Reporting/ Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| 1 | WP 4 Provision of final report for Training/Workshop 1 | (doc, ppt) form in English and Ukrainian; | 08.2026 |
| 2 | WP 4 Provision of final report for Training/Workshop 2 | (doc, ppt) form in English and Ukrainian; | 08.2026 |
| 3 | WP 4 Provision of final report for Training/Workshop 3 | (doc, ppt) form in English and Ukrainian; | 09.2026 |
| 4 | WP 4 Provision of final report for Training/Workshop 4 | (doc, ppt) form in English and Ukrainian; | 09.2026 |
| 5 | WP 5 Advisory | To be determined based on advisory services | Ongoing |

## Requirements

Exercising the option will depend on the receival of a new commission for SUR Project. The decision on continuation is expected to be made in the period 06.2026. If the option is exercised, it is anticipated that the contract term will be extended to 10.2026.

The option will be exercised by means of a contract extension on the basis of the individual approaches already offered.

  - Quantitative requirements for the optional services

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of key expert | days | 1 | 30 |  |
| Travel expenses | Unit of measurement | Quantity |  | Comments (if any) |
| Fixed travel budget | limit | Up to 160.571 UAH |  | A budget is earmarked for travel to the following countries: Ukraine A fixed budget of UAH 160.571 is earmarked for settling travel expenses against evidence/performance. This amount includes accommodation, per diems, travel costs (train, compensation for own transport 13,71 UAH/km, taxi, bus, travel by taxi/car for the entire route is permitted if security situation requires it after approval by SUR Project)., Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. |

There is no contractual right to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

Requirements on the format of the bid for the option

Price of the option shall be indicated separately from the price of main service.

  - Option 2

  - Type and scope

In addition, the following tasks should be completed by the contractor:

WP 6 Facilitation of additional Workshops/Trainings: Content to be determined (approx 20 Expert days)

- The contractor is required to become familiar with the training materials and its technical contents through exchange meetings with the SUR Contractor.

- Facilitate the training measures/Workshops of up to 3 days each on site, up to 4 trainings/Workshops.

- If necessary, provide input to the SUR contractor on improvement of training material on pedagogic and methodological aspects and other areas related to achieving success in training implementation.

- Ensure technical facilitation of the trainings /Workshops (technical set up, ect.) in coordination with SUR Project and the SUR Contractor.

- Coordinate with GIZ project management regarding scheduling, invitations, logistics, security considerations and any other technicalities.

- Organize all aspects of training preparation (regarding scheduling, invitations, logistics, security considerations and any other technicalities) in close coordination with other entities and SUR Project

- Dates for the trainings are to be identified in coordination with the trainees, SUR Project and the contractor.

- For all trainings

  - Facilitate the workshops and pre-defined formats

  - Ensure technical facilitation of in person formats or hybrid formats across all workshops/trainings (coordination with translation services, technical set up, ect.) in coordination with SUR Project and the SUR service provider

  - Ensure adequate participation and engagement by the trainees.

  - Ensure filling out of all administrative forms required by SUR Project by the participants after and before the workshop.

  - Ensure the completion of a pre- and post-evaluation survey by the participants of the workshops.

  - Coordinate with GIZ project management regarding scheduling, logistics, and security considerations.

  - Creating a summary report per city, documenting workshop results in photographic and written form and highlighting lessons learnt.

WP 7: Technical Expertise and Advisory for Training development and delivery (approx. 10 Expert days)

- Offering responsive expert guidance and inputs to the SUR project and SUR Contractors , addressing specific challenges, questions, or issues related to development and delivery of trainings, guidance on developing and adapting training materials, input on methods of training delivery, adaptation of training materials to target audiences and pedagogic requirements to achieve successful training measures.

- Advising on the conceptualization and drafting of tender documents for training activities

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |  |
| --- | --- | --- |
| WP 6 Conduct workshop 1 | By 09.2026/Contractor/Ukraine |
| WP 6 Conduct workshop 2 | By 10.2026/Contractor/Ukraine |
| WP 6 Conduct workshop 3 | By 10.2026/Contractor/Ukraine |
| WP 6 Conduct workshop 4 | By 11.2026/Contractor/Ukraine |
| WP 7 Advisory | Ongoing/Contractor/online |

  - Reporting and deliverables

The Contractor will be responsible for the following:

| # | Reporting/ Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| 1 | WP 6 Provision of final report for Training/Workshop 1 | (doc, ppt) form in English and Ukrainian; | 09.2026 |
| 2 | WP 6 Provision of final report for Training/Workshop 2 | (doc, ppt) form in English and Ukrainian; | 10.2026 |
| 3 | WP 6 Provision of final report for Training/Workshop 3 | (doc, ppt) form in English and Ukrainian; | 10.2026 |
| 4 | WP 6 Provision of final report for Training/Workshop 4 | (doc, ppt) form in English and Ukrainian; | 11.2026 |

## Requirements

Exercising the option will depend on the receival of a new commission for SUR Project. The decision on continuation is expected to be made in the period 06.2026. If the option is exercised, it is anticipated that the contract term will be extended to 12.2026.

The option will be exercised by means of a contract extension on the basis of the individual approaches already offered.

  - Quantitative requirements for the optional services

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of key expert | days | 1 | 30 |  |
| Travel expenses | Unit of measurement | Quantity |  | Comments (if any) |
| Fixed travel budget | limit | Up to 160.571 UAH |  | A budget is earmarked for travel to the following countries: Ukraine A fixed budget of UAH 160.571 is earmarked for settling travel expenses against evidence/performance. This amount includes accommodation, per diems, travel costs (train, compensation for own transport 13,71 UAH/km, taxi, bus, travel by taxi/car for the entire route is permitted if security situation requires it after approval by SUR Project)., Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. |

There is no contractual right to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

Requirements on the format of the bid for the option

Price of the option shall be indicated separately from the price of main service.

- Annexes

- Annex 1 – Travel regulations

- Annex 2 - Minimum standards for sustainable event management at GIZ

Annex 1 Travel regulations (hereinafter – Regulations)

1.Business trips of experts/consultants All experts/consultants who are travelling on behalf of and commissioned by GIZ should use these Travel regulations for calculation and compensation of costs if these costs are stipulated in the Contract. For the claim of travel expenses, the experts/consultants must submit documents according to the terms of the Regulations, unless otherwise is expressly stated in the Contract. Compensation of travel expenses is carried out exclusively within the limits of the amounts for individual items fixed in the Contract. Payment of advances for business trips is possible only if it is expressly stated in the Contract.

2. Definition of a business trip A business trip, as defined by the GIZ’ general regulations governing the reimbursement of travel expense and accommodation, involves an expert/consultant temporarily working at a place other than his/her regular domicile and/or seat of business to conduct official business with GIZ's approval. The duration of a business trip (period of absence) shall be calculated as the time between departure from the place of residence or the principal place of work at the start of the business trip and the return to any of the above-mentioned places on completion of the business trip.

3. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – act of acceptance. Against evidance – copy of the original invoice from the hotel or other actual service provider with period of stay, names of guests, type and number of rooms, price per night, total amount, meals (if included). (Service fee of booking platforms is not to be reimbursed).

4. Per diem allowance The per-diem allowance covers the additional cost of subsistence to the expert/consultant during an assignment away from their regular domicile and/or seat of business and accrued if the condition of a one-day or more business trip is fulfilled. The minimum business trip time is a one-day business trip lasting 10 hours, including working hours and travel time. Per diems are paid within the amount specified in the Contract, as a lump sum. The reduced lump sum rate applies for one-day business trips lasting from 10 to 24 hours and depending on the type of meals at the hotel or the provision of meals from GIZ. The calculation of per diems for business trips depending on the type of meals is given in the Table 1 (see below). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – timesheets in accordance with GIZ limits Against evidence – not applicable

5. Currency of reimbursement of travel expenses Reimbursements of costs of business trips within Ukraine are paid in Ukrainian Hryvnia (UAH). Reimbursements of costs of international business trips are paid in Ukrainian Hryvnia (UAH). Reimbursement of travel expenses in foreign currency (not UAH) must be made according to below mentioned: a) in accordance with the exchange rate that is indicated in bank account statement (for cashless transactions). b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued (for cash transactions when no bank statement is available for confirmation of the used exchange rate). c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates/ (on the date when the financial documents (proof of evidence) were issued)). (In case that invoiced foreign currency is not available at the European Commission site).

6. Flights / ground transportation (train, taxi, private vehicles, car hire/car-sharing/) Costs for transportation are reimbursed within the amount specified in the Contract, against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). The preferred mode of transport shall be economically efficient and environmentally friendly. GIZ is committed to the principles of resource conservation and environmental protection and therefore requires all partners to choose the most environmentally friendly means of transport. Experts/consultants shall take advantage of any price reductions (special rates etc.) that are available. If travel time by train is 5 hours or less, train transport must be preferred for economic and environmental reasons

7.1 Flights Only economy class flight tickets can be reimbursed to experts/consultants. The choice of an airline company should be based on a comparison of ticket prices. The choice of a more expensive flight should be justified by an expert/consultant (e.g. a tight travel schedule combined only with the selected flight). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.2 Trains Train tickets shall be booked and purchased by the expert/consultant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.3 Taxis and group private transportation If the expert/consultant uses a taxi or a group private transportation during a business trip, abroad or in Ukraine, he\she should follow the principle of economic efficiency and necessity of usage this mean of transport. The justification for such a choice should be provided together with a financial document (proof of evidence). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - Taxi (not applicable); Group private transportation (route sheet with indication point of destination/point of arrival overall km). Against evidance – Taxi (bill or ride report or screenshot of order with price indication); Group private transportation (invoice from the actual service provider).

7.4 Private vehicles As a rule, business trips should be made by rail rather than using a private vehicle. Compensation for usage of private vehicles is allowed if such a category of costs is stipulated in the Contract. In the case of using private vehicles, GIZ compensates for such costs at a fixed rate per kilometre, using the shortest possible route (according to the calculation of the Google Maps navigator). For journeys with a one-way distance of more than 200 km, the expert/consultant must provide evidence that using a motor vehicle is more economical than other means of transport. The basis for reimbursement and for determining which means of transport is more economical is the cost of a second-class rail ticket. If a private motor vehicle is used for other important reasons (e.g. to carry heavy luggage, documents or materials, or if local transport connections are poor), convincing and adequate reasons must be set out by the expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - needs evidence by internal based calculation of route planner like Google-map or similar (13,71 UAH per 1 km which includes all expenses without exception, such as fuel etc.) Against evidance - not applicable

7.5 Buses Bus tickets must be booked and purchased independently by an expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication

Table 1 / Таблиця 1

The calculation of per diems for business trips per Travel Day