| Procurement of expert services to support capacity development of LSG officials on the EU integration related topics | Project number/ cost centre: G-012306-002 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

- Context

In 2020, Ukraine finalized the implementation of the administrative and territorial reform aimed at building up a viable system of local self-government that shall contribute to positive changes in the life of citizens. In October 2020, local elections took place in the newly established municipalities many of which experienced significant territorial changes.

The Multi-Donor Action “Ukraine Local Empowerment, Accountability and Development Programme” is jointly co-financed by the European Union (EU), its member states Germany, Poland, Denmark, Slovenia and France and implemented by Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH. On 1 January 2025 the Programme turned to its Phase III, which will be running until 31 December 2027. The main beneficiary of the Programme at the central level is the Ministry for Development of Communities and Territories of Ukraine that receives support in progressing the decentralisation reform and aligning regional policy with the EU acquis. At the sub-national level, the Programme continues supporting municipalities in all regions by enhancing professional and administrative skills of municipal officials for strong local self-government and by enabling municipalities to implement regional and local development policies and reconstruction planning in the context of Ukraine's accession to the EU.

The Overall Objective of the Programme is to contribute to further advancement of multi-level governance in Ukraine, which is transparent, accountable and responsive to the needs of the population in the context EU integration and rebuilding Ukraine.

Within this overall context, U-LEAD with Europe’s activities throughout Phase III are designed to achieve three results:

Result 1:  The Ukrainian government and the Parliament are increasingly capable of advancing the decentralisation reform and aligning regional policy with the EU acquis.

Result 2:  The professional and administrative skills of municipal officials for strong local self-government in the context of Ukraine's accession to the EU are enhanced, taking into account, among other things, the special needs of vulnerable groups and gender equality.

Result 3: Ukrainian municipalities are enabled to implement regional and local development policies and reconstruction planning in the context of the EU accession process.

Main focus areas of U-LEAD in Phase III comprise:

•	Pillar 1: Policy and legal advice for strong local self-governments and regions,

•	Pillar 2: Capacity development for all municipalities,

•	Pillar 3: Support to local reconstruction and development.

Within Pillar 1, legal and policy advice is rendered to partners in adjustment of legislation and aligning it to EU acquis with regard to multi-level governance. In the framework of Pillar 2, informational, consultative and capacity-development measures are offered to municipalities across Ukraine in a tailor-made and targeted way within 12 thematic support packages and reflecting LSG needs and EU integration. Within Pillar 3, U-LEAD’s expertise contributes to local reconstruction, formation of absorption capacity for EU structural instruments, development of UA-EU partnership projects and support of municipalities in digital transformation.

The management/implementation structure for U-LEAD with Europe comprises a horizontal Directorate and four Programme Units in Kyiv, and 24 Regional Offices which directly support local self-government bodies.

Ukraine's acquisition of European Union candidate status and the start of the negotiation process are radically changing the context of local self-government functioning. European integration is no longer exclusively a geopolitical vector of the central government; it is becoming a daily practice at the municipal level.

According to estimates by European institutions, about 70% of EU legislative norms and standards are implemented at the local and regional levels. This applies to the areas of waste management, energy efficiency, public procurement, water quality, sanitary standards and environmental safety. Without capable local self-government, national European integration is impossible.

The EU Cohesion Policy also provides for significant funding to even out regional development disparities. Municipalities should be the key beneficiaries of these funds. However, access to them requires a high level of administrative and reporting capacity. European integration also opens the door to partnerships with municipalities in EU countries. This is not only a cultural exchange, but also a tool for attracting investment, technology, and best management practices.

However, despite high motivation, most municipalities in Ukraine face a critical lack of knowledge and competence in the field of European procedures and policies.

First of all, representatives of local governments often perceive European integration in the abstract, not understanding how specific EU directives and decisions will affect their municipal sector, budget, or local taxes.

The aim of the U-LEAD with Europe Programme in this area is to create a systemic understanding of the role of local governments in Ukraine's European integration processes and the importance of local governments in shaping and implementing EU policies. The perception of European integration among local government officials should be transformed from a "requirement of the authorities" to "a tool for development of municipality."

Implementing this activity will allow forming a pool of leaders of change on the ground who understand the principles of subsidiarity, know how to work with European partners, and are ready to implement EU standards even before Ukraine’s official accession. It will also strengthen the institutional resilience of municipalities in the context of war and recovery.

The involvement of experts will ensure high quality, relevance, and practical focus of the content. After all, the topic of European integration for local governments is multidisciplinary and highly technical. It covers legal, economic, administrative, and sectoral aspects (environment, energy, infrastructure).

In-depth expertise on specific chapters of the negotiation process (Chapters of the Acquis), EU financing mechanisms, and narrow-profile European regulations also requires the involvement of narrow-profile specialists.

This activity contributes to output 2 (indicator 2.1).

- Tasks to be performed by the contractor

GIZ shall commission the Contractor whose 10 experts will provide support to local self-government officials on the EU integration related topics. The experts shall apply innovative training approaches based on the best European practices. The experts shall be responsible for the development and delivery of training activities aimed at translating complex EU regulatory and policy language into clear, practical guidance for municipality leaders and relevant specialists of local self-government bodies.

  - Tasks

The contractor is responsible for providing the following services:

- Preparing and delivery up to 25 offlinecapacity development events (experts work in tandem). Including up to 24 two-day capacity development events for municipalities representatives of each oblast of Ukraine (10 experts operate in two groups; each group is responsible for conducting up to 12 events, the events will be held on the premises of U-LEAD with Europe Regional offices), as well as a one-day capacity development event (expert 1 and 2 work in tandem). The two-day trainings should cover the topics indicated below, taking into account the European and national context as well as the specific characteristics of the region in which it is held. The language of the events is Ukrainian.

Output: concept, agendas, presentations, tests, practical tasks, other materials,  events held.

- Preparing and delivery up to 3 online two-hour information sessions on various topics indicated below (expert 1 and Expert 2 work in tandem). The language of the information sessions is Ukrainian.

- Output: agendas, presentations, events held.

- Preparing information materials upon request and supporting other requested activities - explanations, individual consultations, work with the hromada upon request (experts work in tandem or individually).

- Output: materials, events held.

- Thematically, the capacity development measures mentioned above cover the following:

- European integration processes in Ukraine;

- Ukraine's implementation of the Association Agreement with the EU, harmonization of policies and legislation;

- EU governing bodies;

- local self-government bodies as policy makers;

- the role of Ukraine's municipalities in European integration processes;

- communication with residents of municipalities about European integration processes in Ukraine.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Preparing and delivery of offline capacity development events | Throughout the contract/Ukraine/experts 1-10 |
| Preparing and delivery of information sessions | Throughout the contract/online/experts 1-2 |
| Preparing information materials and supporting other requested activities | Throughout the contract/ upon request/ experts 1-10 |

Period of assignment is from May 20, 2026  till December 18, 2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Events held | Offline | Throughout the contract period |
| Information sessions delivered | Online meetings conducted via the Microsoft Teams platform. | Throughout the contract period |
| Progress report Concept, agendas, presentations, tests, practical tasks, other materials . | Word/ PDF format Agendas should be provided in English Other materials should be provided in Ukrainian | 31.08.2026 |
| Final report Agendas, presentations, other materials. | Word/ PDF format Agendas should be provided in English Other materials should be provided in Ukrainian | 11.12.2026 |

The Contactor shall submit the written reports in English to the person responsible for the contract.

All written and verbal communication under this contract is confidential and not subject to disclosure to third parties.

Developed documents are considered the property of GIZ and shall not be used by the selected Contractor or any other legal or private person without the prior written approval of the GIZ project team. GIZ receives the exclusive right to use all materials, outputs and developments created by the Contractor within and during the term of this agreement.

- The experts should be able to use interactive IT tools for online information sessions, so they will have their own access/subscription to them, in particular licensed access to the Microsoft Teams platform

- The list of prepared and conducted events and consultations should be reflected in the progress/final reports.

The Contractor must provide the outputs of the contract within the specified deadlines in Ukrainian, but the progress reports and the final report together with the event agendas and MS Teams and ULEARN meetings screenshots shall be submitted in English.

All activities shall be carried out in Ukraine (offline and online).

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

## Project management of the contractor (1.6)

The tenderer is required to explain its approach (1.6.1) for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan (1.6.2) with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

The tenderer is required to describe its backstopping concept (1.6.3). The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

- Process-oriented steering for implementation of the commission

- Securing the administrative conclusion of the project

## Further requirements (1.7)

N/A

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

N/A

## Key experts 1 - 2

Tasks of key experts 1 - 2

- Preparing and delivery offline capacity development events.

- Preparing and delivery information sessions.

- Preparing materials upon request and supporting other requested activities.

Qualifications of key experts 1 - 2

- Education/training (2.2.1; 2.3.1): university degree (Master/Specialist) in International relations, Law, Sociology, History, Political Science, European Studies, Philology, Journalism

- Language (2.2.2; 2.3.2): B2-level language proficiency in English based on CV

- General professional experience (2.2.3, 2.3.3): 8 years of professional experience in the international relations, law, sociology, history, political science

- Specific professional experience (2.2.4, 2.3.4): 7 years in public communications, training activities, and public relations

## Key experts 3 - 10

Tasks of key experts 3 - 10

- Preparing and delivery offline capacity development events.

- Preparing materials upon request and supporting other requested activities.

Qualifications of key expert 3 - 10

  - Education/training (2.4.1 – 2.11.1): university degree (Master/Specialist) in International relations, Law, Sociology, History, Political Science, European Studies, Philology, Journalism

  - Language (2.4.2 – 2.11.2): B2-level language proficiency in English based on CV

  - General professional experience (2.4.3 – 2.11.3): 8 years of professional experience in the international relations, law, sociology, history, political science;

- Specific professional experience (2.4.4 – 2.11.4): 7 years in public communications, training activities, and public relations

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations and reporting documents are to be observed. See Annex 1 to these Terms of Reference.

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of Expert 1 | expert day | 1 | 42 |  |
| Designation of Expert 2 | expert day | 1 | 42 |  |
| Designation of Expert 3 | expert day | 1 | 29 |  |
| Designation of Expert 4 | expert day | 1 | 29 |  |
| Designation of Expert 5 | expert day | 1 | 29 |  |
| Designation of Expert 6 | expert day | 1 | 29 |  |
| Designation of Expert 7 | expert day | 1 | 29 |  |
| Designation of Expert 8 | expert day | 1 | 29 |  |
| Designation of Expert 9 | expert day | 1 | 29 |  |
| Designation of Expert 10 | expert day | 1 | 29 |  |
| Travel expenses | Unit of measurement | Quantity |  | Comments (if any) |
| Experts 1-10 Fixed travel budget |  | UAH 1146800 |  | A budget is earmarked for travel to the following countries: Ukraine. A fixed budget of UAH 1146800 is earmarked for settling travel expenses against evidence/ performance. This amount includes accommodation (Table 2), per diems, travel costs (train, compensation for own transport 15,07 UAH/km, taxi, bus). Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. |

Overall expected number of working days – 316 (42 working days per Experts 1, 2, 29 working days per Experts 3-10).

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors

Tasks do not include administrative processes implemented by the Contractor such as organization of meetings (for example, sending invitations to the participants) - this functionality would be provided by GIZ.

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, but excl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments on quarterly basis. A scan-copy of list of participants, signed by AV for each day of offline events must be provided by GIZ .

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) , timesheets, outputs and reports - submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment.

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF) , timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

- Each invoice and act of acceptance shall contain the Project Number, contract number

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The Contract /Supplement to this Contract (if any) enter into force upon its signing by the Parties.

If there are two different dates, then the signing date of the Contract/Supplement to this Contract (if any) is considered to be the last date of signature of one of the Parties.

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local)  published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _______ (indicate name/-s, surname/-s, phone/-s, e-mail/-s) (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

The given procurement of services upon the Contract shall be carried out at the funds of the Project of International Technical Assistance (Project ITA), No.2023.2122.2, Project title “Supporting decentralization in the context of reconstruction and EU integration in Ukraine / UDU – U-LEAD with Europe: Phase III”, registered by the Secretariat of the Cabinet of Ministers of Ukraine (registration card of the project (program) No. 5974  dated 21/04/2025) and complies with the category (type) of Services specified in the purchase plan available at address https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel

The above-mentioned ITA project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008.

The given procurement of services upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, then the Contractor must notify GIZ of such VAT registration in writing or in electronic form by means of submission of an e-mail with copy of the Excerpt from VAT Registration Registry to the GIZ’s e-mail address indicated in the details of the Contract. The Contractor must submit the mentioned notification to the GIZ not later than 1 calendar day following the day of VAT registration.

At the same time the Parties agreed that the purchase of Services after the VAT registration of the Contractor shall be exempt from VAT in accordance with the abovementioned.

# Outsourced processing of personal data

N/A

- Requirements to the format of the bid

  - Documents to be submitted

Tenderers must provide the following documents:

    - Technical bid

- technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- personnel (team) concept

- CVs of all experts with relevant work experience, qualifications (education, certificates, copies of diplomas).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English language.

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English language.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Option

N/A

- Annexes

- Annex 1 – Travel regulations

Annex 1 Travel regulations (hereinafter – Regulations)

1.Business trips of experts/consultants All experts/consultants who are travelling on behalf of and commissioned by GIZ should use these Travel regulations for calculation and compensation of costs if these costs are stipulated in the Contract. For the claim of travel expenses, the experts/consultants must submit documents according to the terms of the Regulations, unless otherwise is expressly stated in the Contract. Compensation of travel expenses is carried out exclusively within the limits of the amounts for individual items fixed in the Contract. Payment of advances for business trips is possible only if it is expressly stated in the Contract.

2. Definition of a business trip A business trip, as defined by the GIZ’ general regulations governing the reimbursement of travel expense and accommodation, involves an expert/consultant temporarily working at a place other than his/her regular domicile and/or seat of business to conduct official business with GIZ's approval. The duration of a business trip (period of absence) shall be calculated as the time between departure from the place of residence or the principal place of work at the start of the business trip and the return to any of the above-mentioned places on completion of the business trip.

3. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – act of acceptance. Against evidance – copy of the original invoice from the hotel or other actual service provider with period of stay, names of guests, type and number of rooms, price per night, total amount, meals (if included). (Service fee of booking platforms is not to be reimbursed).

4. Per diem allowance The per-diem allowance covers the additional cost of subsistence to the expert/consultant during an assignment away from their regular domicile and/or seat of business and accrued if the condition of a one-day or more business trip is fulfilled. The minimum business trip time is a one-day business trip lasting 10 hours, including working hours and travel time. Per diems are paid within the amount specified in the Contract, as a lump sum. The reduced lump sum rate applies for one-day business trips lasting from 10 to 24 hours and depending on the type of meals at the hotel or the provision of meals from GIZ. The calculation of per diems for business trips depending on the type of meals is given in the Table 1 (see below). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – timesheets in accordance with GIZ limits Against evidence – not applicable

5. Currency of reimbursement of travel expenses Reimbursements of costs of business trips within Ukraine are paid in Ukrainian Hryvnia (UAH). Reimbursements of costs of international business trips are paid in Ukrainian Hryvnia (UAH). Reimbursement of travel expenses in foreign currency (not UAH) must be made according to below mentioned: a) in accordance with the exchange rate that is indicated in bank account statement (for cashless transactions). b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued (for cash transactions when no bank statement is available for confirmation of the used exchange rate). c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates/ (on the date when the financial documents (proof of evidence) were issued)). (In case that invoiced foreign currency is not available at the European Commission site).

6. Flights / ground transportation (train, taxi, private vehicles, car hire/car-sharing/) Costs for transportation are reimbursed within the amount specified in the Contract, against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). The preferred mode of transport shall be economically efficient and environmentally friendly. GIZ is committed to the principles of resource conservation and environmental protection and therefore requires all partners to choose the most environmentally friendly means of transport. Experts/consultants shall take advantage of any price reductions (special rates etc.) that are available. If travel time by train is 5 hours or less, train transport must be preferred for economic and environmental reasons

7.1 Flights Only economy class flight tickets can be reimbursed to experts/consultants. The choice of an airline company should be based on a comparison of ticket prices. The choice of a more expensive flight should be justified by an expert/consultant (e.g. a tight travel schedule combined only with the selected flight). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.2 Trains Train tickets shall be booked and purchased by the expert/consultant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.3 Taxis and group private transportation If the expert/consultant uses a taxi or a group private transportation during a business trip, abroad or in Ukraine, he\she should follow the principle of economic efficiency and necessity of usage this mean of transport. The justification for such a choice should be provided together with a financial document (proof of evidence). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - Taxi (not applicable); Group private transportation (route sheet with indication point of destination/point of arrival overall km). Against evidance – Taxi (bill or ride report or screenshot of order with price indication); Group private transportation (invoice from the actual service provider).

7.4 Private vehicles As a rule, business trips should be made by rail rather than using a private vehicle. Compensation for usage of private vehicles is allowed if such a category of costs is stipulated in the Contract. In the case of using private vehicles, GIZ compensates for such costs at a fixed rate per kilometre, using the shortest possible route (according to the calculation of the Google Maps navigator). For journeys with a one-way distance of more than 200 km, the expert/consultant must provide evidence that using a motor vehicle is more economical than other means of transport. The basis for reimbursement and for determining which means of transport is more economical is the cost of a second-class rail ticket. If a private motor vehicle is used for other important reasons (e.g. to carry heavy luggage, documents or materials, or if local transport connections are poor), convincing and adequate reasons must be set out by the expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - needs evidence by internal based calculation of route planner like Google-map or similar (15,07 UAH per 1 km which includes all expenses without exception, such as fuel etc.) Against evidance - not applicable

7.5 Buses Bus tickets must be booked and purchased independently by an expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication

Table 1 / Таблиця 1

The calculation of per diems for business trips per Travel Day

Table 2 / Таблиця 2