| Services for organising the participation of Ukrainian partners in the 8th German-Ukrainian Municipal Partnership Conference in Berlin, Germany, 07-09 October 2026 | Project number/ cost centre: G-012671-003 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

ToRs	Terms of reference

- Context

On behalf of the Federal Ministry for Economic Cooperation and Development (BMZ), the Service Agency "Communities in One World" (SKEW) of Engagement Global gGmbH (EG), in cooperation with the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ, hereinafter referred to as Commissioning party), supports German-Ukrainian partnerships between municipalities through the SKEW project "Municipal partnerships with Ukraine" and provides them with offers for professional exchange, information, training and networking, as well as human and financial support tools.

Over the ten years of the project (November 2015 - February 2026), the network of partnerships between German and Ukrainian municipalities has grown from 39 to 257 partnerships. The network currently includes 418 municipalities from Germany and Ukraine.

The SKEW project "Municipal partnerships with Ukraine" aims to contribute to the further development of existing partnerships and to strengthen development policy engagement and local expertise in German and Ukrainian municipalities through sustainable partnership work. In addition, new partnerships between German and Ukrainian municipalities are to be established. At the same time, the network between German-Ukrainian partnerships is to be consolidated and expanded. The focus is on promoting constructive and equal cooperation between the partner municipalities. Further background information on the project can be found here: https://skew.engagement-global.de/partnerschaften-mit-kommunen-in-der-ukraine.html.

Part of the project is the German-Ukrainian Municipal Partnership Conference (hereinafter referred to as ‘the Conference’), which is aimed at mayors, district administrators and representatives of German, Ukrainian and selected European local authorities that maintain partnership relations with one another. Other participants in the conference include decision-makers from politics, civil society, embassies and donor organisations.

This year, the 8th German-Ukrainian Municipal Partnership Conference will take place from 7 to 9 October 2026 in Berlin, Germany. It is aimed at local government representatives and other stakeholders from the German-Ukrainian municipal partnership network and offers opportunities for professional and personal exchange, insights into support services, as well as expert forums and panel discussions on current issues. This conference will provide the local authorities from both countries with the opportunity to engage in dialogue, share their needs and wealth of experience, discuss current issues and find out about advisory, funding and support tools.

For up to 550 participants from Ukraine and Germany are expected to attend this event. For up to 270 Ukrainian participants – representatives of Ukrainian local and national authorities, municipal enterprises and/or non-governmental organisations – is to organise the participation at the Conference, including hotel accommodation in transit countries while travelling from/to their place of residence in Ukraine to/from Berlin (Germany) and reimbursement of their travel expenses.

To this end, it is necessary to involve an event service provider who will assist the project team in organising the participation of Ukrainian partners in the Conference.

- Tasks to be performed by the contractor

The objective of this assignment is to provide services for organising the participation of Ukrainian partners in the 8th German-Ukrainian Municipal Partnership Conference in Berlin, Germany, 7-9 October 2026.

Agenda of the event

| Description of event | 8th German-Ukrainian Municipal Partnership Conference |
| --- | --- |
| Duration of the event | 3 days / 24 hours |
| Date and time | 07.10.2026 - 09.10.2026 07.10.2026 - Hours 15:00-21:00 08.10.2026 – Hours 08:00-19:00 09.10.2026 – Hours 08:00-14:30 The exact dates can be shifted and shall be confirmed by the GIZ Representatives not later than 25 calendar days in advance before the event. The Contractor shall not start the preparation to the event without prior confirmation of the date of the event by the GIZ Representatives (via e-mail correspondence). |
| Location (city, country) | Berlin, Germany |
| Number of Participants (up to), composition | Up to 550 participants from Ukraine and Germany including up to 270 Ukrainian participants - representatives of Ukrainian local and national authorities, municipal companies, and NGOs |
| Remarks (if applicable) |  |

  - Tasks

The contractor is responsible for providing the following services:

- providing consultation to Ukrainian participants regarding travel options to/from Berlin, Germany (via email and/or phone communication),

- participation in the coordination meetings with German event agency and the Commissioning party regarding participants from Ukraine,

- compiling, maintaining and finalising the list of Ukrainian participants approved by GIZ and informing the Commissioning party about the date of arrival / departure of Ukrainian participants and regularly updating the Commissioning party,

- informing the Commissioning party about the number of Ukrainian participants who will arrive on 06.10.2026 and have an additional dinner on 06.10.2026 (dinner will be organised by SKEW),

- preparation the information about the reimbursement of travel costs and sending this information to the Ukrainian participants before the Conference,

- organization of hotel accommodation in transit countries while travelling from/to their place of residence in Ukraine to/from Berlin (Germany),

- organization of reimbursement of travel costs (bus/train tickets/ hotel costs) to the Ukrainian participants after the Conference.

The following trave/event scheme is forecasted:

| Date | Travel stage | Required support of the Contractor |
| --- | --- | --- |
| 04.-07.10.2026 | Individual travels of Ukrainian participants to Berlin (Germany) and Bus transfer(s) of the group(s) on the route Lviv (Ukraine) - Münster (Germany) | Organization of hotel accommodation in transit countries while travelling from their place of residence in Ukraine to Berlin (Germany); Providing consultation to Ukrainian participants regarding reimbursement of travel costs (bus/train tickets/ hotel costs) (via email and/or phone communication; |
| 07.-09.10.2026 | Event days |  |
| 09.-11.10.2026 | Individual travel of Ukrainian participants into Ukraine | Organization of hotel accommodation in transit countries while travelling to their place of residence in Ukraine from Berlin (Germany); Providing consultation to Ukrainian participants regarding reimbursement of travel costs (bus/train tickets/ hotel costs) (via email and/or phone communication. |

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Start of the Contract | April 27, 2026 / Ukraine |
| The first online meeting with the Commissioning party | by April 30, 2026 / Ukraine, online / Contractor |
| The first online meeting with the German event agency | by May 15, 2026 / Ukraine, online / Commissioning party & Contractor |
| Consulting Ukrainian participants on travel opportunities to/from Berlin, Germany | May – September 2026 / Ukraine / Contractor |
| Online meetings with the German event agency & Commissioning party | May – September 2026 / Ukraine, online / Contractor |
| Compiling preliminary list of Ukrainian participants after registration deadline and informing the Commissioning party about the date of arrival / departure of Ukrainian participants, dinner on 06.10.2026 | by August 10, 2026 / Ukraine/ Contractor |
| Reservation and booking of accommodation in transit countries by the Contractor | September 2026 / Ukraine/ Contractor |
| Informing Ukrainian participants about reimbursement procedure | by September 10, 2026 / Ukraine/ Contractor |
| Finalising the list of Ukrainian participants and informing the Commissioning party about the date of arrival / departure of Ukrainian participants, dinner on 06.10.2026 | by September 15, 2026 / Ukraine/ Contractor |
| Collecting originals/copies of reimbursed bus and train tickets and hotel bills | by October 15, 2026 / Ukraine/ Contractor |
| Reimbursement of travel costs (train/bus/hotel costs) to the Ukrainian participants | by October 25, 2026 / Ukraine/ Contractor |
| End of the contract | by November 15, 2026 / Ukraine/ Contractor |

The contract duration is from 10.05.2026 till 15.11.2026.

  - Reporting:

The Contractor shall submit the following reporting documents to report for event/conference services:

- a concise event report (maximum 4 pages), summarizing (in bullet points) the services provided; - invoice for payment and act of acceptance, signed and stamped (if applicable) by Contractor;

- and all other documents specified for each item in paragraph 4 “	Costing (quantitative) requirements” of these ToR.

All the documents shall be in English, signed and stamped (if applicable) and should be provided till 5.11.2026.

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Technical-methodological concept

Strategy (1.1): The tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided.

Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

- 1 Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 9), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

Event coordinator (expert 1)

Tasks of the event coordinator

- Overall responsibility for the Contractor's conference services (quality and timing)

- Coordination and communication with GIZ, German event agency and other project participants

- Procurement and booking of all necessary supplies within the contract

- Consulting Ukrainian participants on travel opportunities to/from Berlin, Germany during the registration period up to the beginning of the Conference and on the days of reimbursement period after the Conference

- Organisation of hotel accommodation in transit countries

- Organisation of reimbursement of travel costs to the Ukrainian participants

- Participation at online meetings with the German event agency & Commissioning party

- Reporting to the Project in accordance with GIZ requirements.

Qualifications of the Event coordinator

- Language (2.2.2): B2-level language proficiency in German or English, C1-level language proficiency in Ukrainian.

- General professional experience (2.2.3): 5 years of professional experience in the conference services, event management and logistics sector and financial management.

- Specific professional experience (2.2.4): 3 years in relevant expertise with high-level participants / municipal representatives, in organising of international events

Event Assistant (expert 2)

Tasks of the assistant event coordinator

- Consulting Ukrainian participants on travel opportunities to/from Berlin, Germany during the registration period up to the beginning of the Conference and on the days of reimbursement period after the Conference

- Communication with the German event agency, responsible for the whole participants management regarding the registrations of UA participants (if necessary)

- Preparation of lists, reimbursement of travel cost

- Support throughout the travel of UA participants, being available for communication and on the days of reimbursement period after the Conference

- Reporting to the Project in accordance with GIZ requirements.

Qualifications of the assistant event coordinator

- Ukrainian speaking person is mandatory

- Language (2.3.2): B2-level language proficiency in German or English, C1-level language proficiency in Ukrainian.

- General professional experience (2.3.3) : 2 years of professional experience in the conference services, event management and logistics sector

- Specific professional experience (2.3.4): 1 years in relevant expertise with high-level participants / municipal representatives, in organising of international events

Soft skills of team members

communication skills.

- Costing (quantitative) requirements

Assignment of personnel and travel expenses Not applicable

Sustainability aspects for travel and travel regulations Not applicable

Specification of inputs

| № | Service | Description | UoM | Q-ty | Reporting documents against performance Expenses are to be reimbursed as lump sum per unit of measurement | Reporting documents against evidence Expenses are to be reimbursed as “up to” based on settlement document that contains price |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Reimbursement of travel costs for Ukrainian participants | Reimbursement of bus and / or train tickets and / or hotel costs for up to 270 UA Conference’s participants, if these were bought/ reserved by themself in Ukraine and abroad for the outward and return journey. Reimbursement of 1st class railway tickets is possible in case the journey extends 3 hours. Limits for overnight accommodation are: - up to 100 EUR. Standard single room, including breakfast and tourist tax, at not less than 3* hotel in a transit country (e.g. Poland, Romania, Moldova). No more than 1 night on one way. Reimbursement will be made in Ukraine, after the Conference and return of UA participants in Ukraine, by bank card transfer or cash, or by alternative ways of automating this process as proposed by the Contractor and agreed with GIZ. The reimbursement must be provided by Contractor in UAH. Reimbursement of vouchers and tickets in foreign currency (not UAH) will be realized: a) in accordance with exchange rate that is indicated in bank account statement (for cashless transactions), b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) were issued. A budget of 37000 EUR is foreseen for reimbursement of travel costs. | service | 1 |  | - Original / copies of reimbursed bus, train tickets, hotel invoices, with surnames of the participants and cost in UAH/EUR; - List of UA participants with signatures, who received the reimbursement of travel costs. If reimbursement was conducted via transfer on the bank card of participants, Contractor shall provide bank statements with bank charges and / or related taxes. The ticket purchase fee is not to be reimbursed. Service fee of booking platforms is not to be reimbursed. |
| Accommodation |  |  |  |  |  |  |  |
| 2. | Reservation and booking of accommodation | Standard single room, including breakfast and tourist tax, at not less than 3* hotel in a transit country (e.g. Poland, Romania, Moldova). Limits for overnight accommodation are: - up to 100 EUR. When choosing a hotel, it is important to consider favorable cancellation options. If there is no reasonable accommodation available within the rates/room category as mentioned, a higher amount can be paid after written approval by the project (Customer) within the accommodation budget. No more than 1 night on one way. A budget of 15 000 EUR is foreseen for overnight accommodation. | night | 150 |  | - Copy of invoice from the hotel or other actual service provider with period of stay, names of participants, type and number of rooms and nights, price per night, total amount, meals. |
| Expert services (experts that are directly involved in preparation of the event) |  |  |  |  |  |  |  |
| 3. | Event Coordinator | Tasks and requirements are specified in ToR clause 3. | day | 70 | Timesheet with the actual days utilized. |  |
| 4. | Event Assistant | Tasks and requirements are specified in ToR clause 3. | day | 50 | Timesheet with the actual days utilized. |  |
| Other costs |  |  |  |  |  |  |  |
| 5. | Flexible remuneration | The Contractor shall act only in terms of prices per unit provided. Exceeding such costs is not allowed. Flexible renumeration may be used only to order additional quantities without changing the unit price. A budget of 8000.00 EUR is foreseen for flexible remuneration. Use of the flexible remuneration item requires prior written approval from GIZ. | n/a |  | In case flexible renumeration is used, explanation of the reasons which led to this, and proof of performance specified to the particular item(s) above must be provided in written. | In case flexible renumeration is used, explanation of the reasons which led to this, and proof of evidence specified to the particular item(s) above must be provided in written. |
| 6. | Service fee | Contractor shall calculate its service fee for the services requested above. Service fee should cover contractor’s service fee, taxes, administrative costs and is to be paid based on the total sum of actually provided services. Costs in lines 3,4, are not subject of service fee (that are covered against proof of performance and for experts that are directly involved in organization/preparation of the event). | n/a |  | The confirmation of provided /received services is done via signed Act of acceptance between GIZ and Contractor |  |

There is no contractual obligation to use up the full quantities or budgets.

- Inputs of GIZ or other actors

GIZ and/or SKEW are expected to make the following available:

- Program of the Conference and information about the accommodation in Berlin (name of hotel)

- List of registered Ukrainian participants of the conference after it was held in Berlin

- Financial provisions

  - Contract value and anticipated payment schedule

  - The contract value shall be calculated according to the format of the financial bid (price schedule).Financial bid (price schedule)

The total cost of the Contract is set in EUR, including all direct and related expenses, taxes and fees, incl. VAT (if applicable).

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

The Contractor should be paid 50% prepayment within 10–14 working days after the final list of participants is approved by GIZ, based on the provided by Contractor original Invoice and after provision of the services, 50% post payment within 10 working days on the ground of the original invoices, service entry sheet (LERF) and acts of acceptance signed by both Parties, submitted together with reporting documents indicated in Specification of inputs Section 4. For post payment a list of participants, signed by AV for each day of event must be provided by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment.

Final invoice must account in full for correct use of advance payment. Final payment will not be conducted if financial statement for previous payment is not presented.

If the amount of executed advance payment exceeds the amount of funds used in frames of advance payment (against provided reporting documents), such difference will be used to cover final part of post payment for the Services.

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor. The amount in UAH will be calculated as of the month of the provided invoice based on the exchange currency rate of  European commission Exchange rate (InforEuro) (europa.eu): https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en;

- Travel costs provided in Ukraine shall be reimbursed in UAH on the amount specified in relevant proof of evidence (accommodation, transportation).

- All the activities shall be done exclusively within the timeframe of the Contract;

- In cases when the provision of services (e.g. accommodation, travel costs, etc.) were provided/held abroad,  the following mechanism will be realized:a) in accordance with exchange rate that is indicated in bank account statement (for cashless transactions),

b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) were issued. (for cash transactions when no bank statement is available for confirmation of the used exchange rate),

c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates (on the date when the financial documents (proof of evidence) were issued)). (in case that invoiced foreign currency is not available at the European Commission site).

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF) and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- Each invoice and act of acceptance shall contain the Project Number:

- G-012671-003

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link  Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, and the given procurement of services/ works upon the Contract shall not be determined free from VAT, the cost of the Contract remains unchanged and is to be considered with VAT.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _______ (indicate name/-s, surname/-s, phone/-s, e-mail/-s)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

The Tenderer / Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption “Not Applicable”

- Outsourced processing of personal data

The Contractor confirms that they will process personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and Law of Ukraine “About personal data protection” № 2297-VI dd. 01.06.2010.

The performance of the contract is associated with the processing of personal data by the Contractor, such as (but not limited to) names and contact information. The Contractor will define the nature of such data and how such processing is carried out. The Contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including those stemming from regional and local laws. The Contractor shall process personal data only when a given goal cannot be reasonably attained without such data. Data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be observed and implemented. GIZ is NOT in any way responsible for such processing.

- Requirements to the format of the bid

Documents to be submitted

Tenderers must provide the following documents:

  - Technical bid containing:

- a description of the methodology proposed in relation to the identified tasks, in particular,

- a strategy/plan for cooperation with the Customer and with relevant entities,

- a description of personnel assignment plan (who, when, what work steps),

- the CVs of the personnel proposed in accordance with Chapter 3 of the ToRs.

Technical bid must be signed and stamped (if stamp is used).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English.

The complete technical bid must not exceed 10 pages (excluding CVs).  If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 3 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for personnel or any other payments. Otherwise, the bid will be disqualified.

  - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

  - Registration documents of the Tenderer

Shall be provided according to the requirements of tender documentation.

The tender is obliged to confirm the following eligibility criteria:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.