| Data management in the field of housing 2 | Project number/ cost centre: G-012241-001 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

SUR		GIZ project “Strengthening of Urban Resilience in the Areas of Supply Infrastructure and Housing”

IWO e.V.	 The Housing Initiative for Eastern Europe (Initiative Wohnungswirtschaft Osteuropa (IWO) e.V.)

- Context

The GIZ transitional development assistance (TDA) project Strengthening of Urban Resilience in the Areas of Supply Infrastructure and Housing (SUR) systematically strengthens resilience of municipal services of general interest in selected regions. Urban resilience is the ability of an urban system to react resiliently in the event of crises, while at the same time adapting, reshaping, and strengthening itself in terms of sustainable urban development. The project is part of the TDA fields of action reconstruction of basic infrastructure and services as well as disaster risk management.

On the one hand, the project strengthens capacities of partner cities in urban planning and management. This includes e.g. the introduction of digital tools for effective damage assessment or urban planning cadasters. The anchoring of systematic disaster risk management systems is an additional focus. Local sector concepts, development strategies and additional planning documents on different regional levels (e.g. city-wide, quarter-wide, neighborhood-wide) shall be supported, always under the premise to support urban resilience. Furthermore, the project provides qualification measures for municipal staff in the mentioned fields of actions and beyond. In total, urban partners shall be capacitated to plan and shape their development in a resilient manner, which allows them to not only react to external shocks but also supports a long-term sustainability of local developments.

On the other hand, the focus lies on immediate measures to restore the functionality of damaged or destroyed critical supply infrastructure in a robust, adaptive, and, if possible, future-proof manner. Where available, current damage analyses and existing planning principles are used to contribute to the medium- and long-term development of municipalities in the sense of a build-back-better approach. When selecting measures, care must be taken to ensure that they are modular, flexible, replicable, scalable, and can be implemented quickly in order to achieve economies of scale in procurement processes. Of particular importance is the consideration of local winter relief measures and aid offers from the international community. In addition, the selected cities and municipalities, as well as private actors (owners, if possible, owner associations or neighborhood cooperatives), are supported in the rehabilitation, repair, and creation of housing. The measures proposed here primarily address simple buildings, in the case of rehabilitation, buildings with light (windows, roofing, façade, etc.) and medium damage (light structural damage to walls/ceiling/roof) without significant, structurally relevant damage.

Situational background

In addition to the grave impact on the lives of Ukrainian citizens, the ongoing conflict has significant consequences for the country's infrastructure and housing sector. A substantial percentage of buildings have sustained damage or have been completely destroyed, and numerous municipalities continue to face challenges in accommodating a large number of internally displaced persons (IDPs).

At the same time housing needs have shifted away from the historic dominance of owner-occupied apartments toward an increased share of rental accommodations. This diversification of the housing sector is likely to continue since ownership often is not the most suitable option, or because many people looking for a new home will not be able to afford the downpayment. This shift offers the opportunity to establish new forms of housing in Ukraine. A more adaptable and inclusive housing market, suitable to address the diversifying needs of the population, is also improving urban resilience.

Rebuilding efforts and their funding will emphasize the concept of "building back better". The Ukraine Plan (Link) defines "building back better" as a fundamental principle for recovery, reconstruction, and modernization process. It underscores the significance of rebuilding not only to restore the country to its pre-war state, but also to enhance and modernize infrastructure and systems to make them more resilient, sustainable, and aligned with European Union standards. This principle extends beyond construction sustainability to prioritize financial sustainability, inclusiveness, transparency, and accountability. For this, social housing is mentioned explicitly as one of the topics to be addressed by Ukraine.

Social housing organizations can offer a sustainable and inclusive solution to address new housing needs and can be set up with a governance and auditing structure to meet the funding requirements of international institutions and with it support Ukraine in “building back better”.

Social housing provides housing to the vulnerable population by the government or civil society below market prices. It presents a viable addition in the present housing system to guarantee an essential standard of living for vulnerable populations, while also contributing to the diversification of housing options within municipalities, revitalizing urban areas, and with this enhancing urban resilience.

While Ukraine has a social housing system aiming to solve housing for the most vulnerable population in the long-term, it is distinctive in that it often involves the transfer of ownership from the state to the individual recipients, particularly through the social queue system. This approach is rooted historically in the large-scale privatization of housing after the fall of the Soviet Union, where many tenants of state-owned housing were given the opportunity to acquire their apartments at minimal cost or for free.

The approach has significant challenges, since transferring ownership does not allow a municipality to build up a social housing stock. The creation of new units is highly dependent on government budgets and financially not sustainable compared to other social housing systems in the EU.

It is also unlikely that the European Union (EU) will fund a social housing scheme that involves directly transferring ownership of housing units to individuals without significant oversight or accompanying reforms.

The main business model of the current housing sector, primarily dominated by for-profit private developers selling apartments to individuals, is unsuitable to receive EU funding for similar reasons. Furthermore, the continuation of privatization of the housing stock poses the risk of deepening social tensions and overall reduce the resilience of Ukrainian society, given that low-income groups will be prevented from access to adequate housing.

The SUR project supports partner municipalities in strengthening their capacities to provide sustainable housing for local population. Given the fact that housing is a core stone of urban resilience – ensuring adequate provision of the local population and strengthening social cohesion – the SUR project aims to support municipalities in application of resilient approaches towards housing, integration of resilience strategies into housing sector and improvement of pre-conditions of for housing provision in the cities.

The SUR project, together with the partner organization IWO e.V., addresses the topic of urban resilience in the housing sector and work on the municipal housing strategies for Poltava, Kremenchuk, Zhytomyr and Bila Tserkva, Mykolaiv and other cities. Data management in the field of housing remains the very crucial, but the very challenging element for assessment of the needs and definition of strategic objectives dealing with the current housing crisis in Ukraine.

- Tasks to be performed by the contractor

  - Tasks

The contractor is responsible for providing the following services:

SP 1. Analysis of the housing sectors and organization of the data base on housing sectors in Mykolaiv and up to 3 Ukrainian cities (tbs) in the framework of the IWO cooperation:

- In coordination with SUR project and IWO experts, providing an overview of available data per city for Mykolaiv and up to 3 Ukrainian cities (tbs) and per following topic, but not only:

- Technical state of the housing stock in each city for Mykolaiv and up to 3 Ukrainian cities (tbs) (for ex. which data is available, which cannot be available etc.)

- Comparison of the housing management and maintenance tariffs in Mykolaiv and up to 3 Ukrainian cities (tbs).

- Housing and communal services analysis in Mykolaiv and up to 3 Ukrainian cities (tbs) (how it is provided – local or regional, problems etc.)

- Analysis of the local sectoral programs in housing, their feasibility and achievement, budget allocations in Mykolaiv and up to 3 Ukrainian cities (tbs).

- Dynamic of construction in Mykolaiv and up to 3 Ukrainian cities (tbs) (pre- and post-war).

- Demographic data and prognoses, housing needs of IDPs based on EU housing indicators (considering the input by the SUR contractor for socio-demographic analysis development in Mykolaiv and up to 3 Ukrainian cities (tbs).

- In coordination with SUR project and IWO experts, organizing the data in suitable formats in a database for above mentioned topics, but not only.

- Presentation and clarification of data to the IWO experts.

- In coordination with SUR project and IWO experts, writing short concept notes on data availability and quality for above mentioned topics, but not only

- In coordination with SUR project and IWO experts, formulating feasible goals for data collection in the housing field.

- Providing advice to the SUR project and IWO experts on any data related topics.

SP 2. Supporting the SUR project and IWO expert in processing, analysis and representation of data in the field of housing for Mykolaiv and up to 3 Ukrainian cities (tbs):

- Analysis of the gathered data, preparation of short analytical comments, graphics and diagrams for Mykolaiv and up to 3 Ukrainian cities (tbs).

- Providing an expert advice and support towards IWO experts regarding the interpretation of the data for Mykolaiv and up to 3 Ukrainian cities (tbs).

- Supporting the IWO experts in elaboration of the analytical reports for Mykolaiv and up to 3 Ukrainian cities (tbs) (including drafting analytical notes).

- Providing expert advice regarding the state of art of the national housing strategy development, revising and commenting the suggested indicators and suggest feasible indicators for the local housing strategies for Mykolaiv and up to 3 Ukrainian cities (tbs).

- Providing the expert critical advice regarding the IWO approach towards urban resilience in housing, EU policies and EU-EIB pilots.

- Providing expert advice to IWO experts on terminology of housing and communal economy, data representation. Revision and editing of the analytical drafts

- Upon request, participating in the IWO coordination meetings, feedback sessions, workshops in Mykolaiv or Kyiv or other Ukrainian cities in online or offline formats (depending on the security situation and formats of the coordination meetings, feedback sessions, workshops).

- Upon request, in coordination with IWO drafting analytical sections of the municipal housing strategies for Mykolaiv and up to 3 Ukrainian cities (tbs).

- Upon request, in coordination with IWO engaging with municipal departments and representatives of local self-government bodies, as well as other stakeholders, in municipal housing strategy development, consulting, data collection, task delegation, and monitoring

- Upon request, in coordination with IWO, supporting with structuring elaboration of municipal housing investment projects.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| SP1. - Analytical notes available data per city for Mykolaiv and up to 3 Ukrainian cities for the above-mentioned topic - Dataset for Mykolaiv and up to 3 Ukrainian cities for the above-mentioned topic - Concept notes with the analysis of the data for for Mykolaiv and up to 3 Ukrainian cities for the above-mentioned topic | May 15, 2026 Ukraine, remotely / contractor |
| SP2 - Analytical notes on the gathered data its interpretation for Mykolaiv and up to 3 Ukrainian cities (upon request) - Expert reviews regarding the state of art of the national housing strategy development, revising and commenting on the proposed indicators, feasible indicators for the local housing strategies for Mykolaiv and up to 3 Ukrainian cities as well as terminology of housing and communal economy, data representation (upon request) | June 15, 2026 Ukraine, remotely / contractor |

The contract duration is from 11.05.2026 till 11.07.2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| SP1. - Analytical notes available data per city for Mykolaiv and up to 3 Ukrainian cities for the above-mentioned topic (Up to 10 pages in English and Ukrainian). - Dataset for Mykolaiv and up to 3 Ukrainian cities for the above-mentioned topic (Excel files in English / Ukrainian) - Concept notes with the analysis of the data for Mykolaiv and up to 3 Ukrainian cities for the above-mentioned topic (Up to 10 pages per city, in English and Ukrainian). | - Up to 10 pages, in English and Ukrainian, in docx or pdf or xlsx or ppt formats - In English and Urkainian, in xlsx fromat. - Up to 10 pages, in English and Ukrainian, in docx or pdf or xlsx or ppt formats | May 15, 2026 Ukraine, remotely / contractor |
| SP 2 - Analytical notes on the gathered data its interpretation for Mykolaiv and up to 3 Ukrainian cities (upon request) - Expert reviews regarding the state of art of the national housing strategy development, revising and commenting on the proposed indicators, feasible indicators for the local housing strategies for Mykolaiv and up to 3 Ukrainian cities as well as terminology of housing and communal economy, data representation (upon request) | - Up to 10 pages, in English and Ukrainian, in docx or pdf or ppt formats - Up to 10 pages, in English and Ukrainian, in docx or pdf or ppt formats | June 15, 2026 Ukraine, remotely / contractor |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 8), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Key expert 1

Tasks of key expert 1

  - Responsibility for implementation of the service packages of the contractor (quality and deadlines)

  - Coordinating and ensuring communication with GIZ

  - Research and development of conceptual frameworks and methodology

  - Data analysis

  - Development of the analytical notes datasets

Qualifications of key expert 1

- Education/training (2.2.1): university degree Master in Economy

- Language (2.2.2): C1-level language proficiency in Ukrainian Language (5 points) and C1 in English language (5 points)

- General professional experience (2.2.3): 9 years of professional experience in the Economy or Finance sector

- Specific professional experience (2.2.4): 5 years in Data management in housing and housing economy

- Regional experience (2.2.6): 9 years of experience in projects in Ukraine

- Other (2.2.8): evidence in working in the field  of supply infrastructure projects (10 points for 5 years of experience)

Soft skills of team members

In addition to their specialist qualifications, the following qualifications are required of team members:

- Team skills

- Initiative

- Communication skills

- Socio-cultural skills

- Efficient, partner- and client-focused working methods

- Interdisciplinary thinking

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations and reporting documents are to be observed. See Annex 1 to these Terms of Reference.

Specification of inputs

## contracts for services:

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of key expert | Day | 1 | 44 |  |
| Transport | Unit of measurement | Quantity |  | Comments (if any) |
| Fixed travel budget (transportation and accommodation) |  |  | Fixed budget of up to 30000,00 UAH | A budget is earmarked for travel to the following countries: Ukraine A fixed budget of UAH/ 30000,00 is earmarked for settling travel expenses against evidence/performance. This amount includes accommodation, per diems, travel costs (train, compensation for own transport km, taxi, bus)., Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule)

6.2      Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees,  incl. VAT

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments on monthly basis;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment.

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- - Each invoice and act of acceptance shall contain the Project Number, contract number By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The Contract /Supplement to this Contract (if any) enter into force upon its signing by the Parties.

If there are two different dates, then the signing date of the Contract/Supplement to this Contract (if any) is considered to be the last date of signature of one of the Parties.

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local) published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not  a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, and the given procurement of services/ works upon the Contract shall not be determined free from VAT,  the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor ___________________________

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provided according to the requirements of tender documentation

    - Documents for tenderer’s eligibility confirmation

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine “On the Protection of Personal Data” No. 2297-VI dated 01.06.2010.

- Option

After the services put out to tender have been completed, important elements of these tasks can be continued or extended. Specifically:

  - Type and scope

The contractor is responsible for providing the following optional services:

SP 3. Providing expertise and advice towards the SUR project on various aspects related to the topic of data management, data management in the field of housing and supply infrastructure in Ukraine:

  - Providing responsive expert advice and inputs to the SUR project, addressing specific challenges, questions, or issues regarding housing sector, state of the art strategies and policies, stakeholder mapping, resilient urban development and measures to strengthen urban resilience in the housing sector in Ukraine.

  - Providing expert advice and inputs to the SUR project regarding the requests from the SUR partner cities in the field of housing sector and supply infrastructure.

  - Deliverables and Reporting:

The Contractor will be responsible for the following optional services:

| # | Reporting/ Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
|  | SP 3 Submission of the documentation of the provision of expertise and inputs towards the SUR project on various aspects related to the topic of data management, data management in the field of housing and supply infrastructure in Ukraine as well as regarding the requests from the SUR partner cities in the field of housing sector and supply infrastructure; jour-fix, online meetings | In English or Ukrainian, , in docx or pdf or xlsx or ppt formats | February 20, 2027, Ukraine, remotely / contractor |

## Requirements

Exercising the option will depend on particular request from SUR partner cities and needs.  The decision on continuation is expected to be made in the period 01.07.2026. 27.02.2027. If the option is exercised, it is anticipated that the contract term will be extended to 27.02.2027.

The option will be exercised by means of a contract extension on the basis of the individual approaches already offered. The activation of the optional package will depend on the project needs and available budgets.

  - Quantitative requirements for the optional services

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of key expert | Day | 1 | 32 |  |

There is no contractual right to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

Requirements on the format of the bid for the option

Price of the option shall be indicated separately from the price of main service.

- Annexes 
Annex 1 – Travel regulations

Annex 1 Travel regulations (hereinafter – Regulations)

1.Business trips of experts/consultants All experts/consultants who are travelling on behalf of and commissioned by GIZ should use these Travel regulations for calculation and compensation of costs if these costs are stipulated in the Contract. For the claim of travel expenses, the experts/consultants must submit documents according to the terms of the Regulations, unless otherwise is expressly stated in the Contract. Compensation of travel expenses is carried out exclusively within the limits of the amounts for individual items fixed in the Contract. Payment of advances for business trips is possible only if it is expressly stated in the Contract.

2. Definition of a business trip A business trip, as defined by the GIZ’ general regulations governing the reimbursement of travel expense and accommodation, involves an expert/consultant temporarily working at a place other than his/her regular domicile and/or seat of business to conduct official business with GIZ's approval. The duration of a business trip (period of absence) shall be calculated as the time between departure from the place of residence or the principal place of work at the start of the business trip and the return to any of the above-mentioned places on completion of the business trip.

3. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – act of acceptance. Against evidance – copy of the original invoice from the hotel or other actual service provider with period of stay, names of guests, type and number of rooms, price per night, total amount, meals (if included). (Service fee of booking platforms is not to be reimbursed).

4. Per diem allowance The per-diem allowance covers the additional cost of subsistence to the expert/consultant during an assignment away from their regular domicile and/or seat of business and accrued if the condition of a one-day or more business trip is fulfilled. The minimum business trip time is a one-day business trip lasting 10 hours, including working hours and travel time. Per diems are paid within the amount specified in the Contract, as a lump sum. The reduced lump sum rate applies for one-day business trips lasting from 10 to 24 hours and depending on the type of meals at the hotel or the provision of meals from GIZ. The calculation of per diems for business trips depending on the type of meals is given in the Table 1 (see below). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – timesheets in accordance with GIZ limits Against evidence – not applicable

5. Currency of reimbursement of travel expenses Reimbursements of costs of business trips within Ukraine are paid in Ukrainian Hryvnia (UAH). Reimbursements of costs of international business trips are paid in Ukrainian Hryvnia (UAH). Reimbursement of travel expenses in foreign currency (not UAH) must be made according to below mentioned: a) in accordance with the exchange rate that is indicated in bank account statement (for cashless transactions). b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued (for cash transactions when no bank statement is available for confirmation of the used exchange rate). c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates/ (on the date when the financial documents (proof of evidence) were issued)). (In case that invoiced foreign currency is not available at the European Commission site).

6. Flights / ground transportation (train, taxi, private vehicles, car hire/car-sharing/) Costs for transportation are reimbursed within the amount specified in the Contract, against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). The preferred mode of transport shall be economically efficient and environmentally friendly. GIZ is committed to the principles of resource conservation and environmental protection and therefore requires all partners to choose the most environmentally friendly means of transport. Experts/consultants shall take advantage of any price reductions (special rates etc.) that are available. If travel time by train is 5 hours or less, train transport must be preferred for economic and environmental reasons

7.1 Flights Only economy class flight tickets can be reimbursed to experts/consultants. The choice of an airline company should be based on a comparison of ticket prices. The choice of a more expensive flight should be justified by an expert/consultant (e.g. a tight travel schedule combined only with the selected flight). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.2 Trains Train tickets shall be booked and purchased by the expert/consultant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.3 Taxis and group private transportation If the expert/consultant uses a taxi or a group private transportation during a business trip, abroad or in Ukraine, he\she should follow the principle of economic efficiency and necessity of usage this mean of transport. The justification for such a choice should be provided together with a financial document (proof of evidence). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - Taxi (not applicable); Group private transportation (route sheet with indication point of destination/point of arrival overall km). Against evidance – Taxi (bill or ride report or screenshot of order with price indication); Group private transportation (invoice from the actual service provider).

7.4 Private vehicles As a rule, business trips should be made by rail rather than using a private vehicle. Compensation for usage of private vehicles is allowed if such a category of costs is stipulated in the Contract. In the case of using private vehicles, GIZ compensates for such costs at a fixed rate per kilometre, using the shortest possible route (according to the calculation of the Google Maps navigator). For journeys with a one-way distance of more than 200 km, the expert/consultant must provide evidence that using a motor vehicle is more economical than other means of transport. The basis for reimbursement and for determining which means of transport is more economical is the cost of a second-class rail ticket. If a private motor vehicle is used for other important reasons (e.g. to carry heavy luggage, documents or materials, or if local transport connections are poor), convincing and adequate reasons must be set out by the expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - needs evidence by internal based calculation of route planner like Google-map or similar (15.07 UAH per 1 km which includes all expenses without exception, such as fuel etc.) Against evidance - not applicable

7.5 Buses Bus tickets must be booked and purchased independently by an expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication

Table 1 / Таблиця 1

The calculation of per diems for business trips per Travel Day