| Communication Campaign - Inclusion and Activation for the Labour Market |  | Project number/ cost centre: G-011831-004 G-011831-006/ 21.2145.7-004.00 21.2145.7-006.00 |
| --- | --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

GDPR	General Data Protection Regulation

KZFK	Short-term expert

MoEEA	Ministry of Economy, Environment and Agriculture of Ukraine

OOH print	Out-of-home print

PR	Public Relations

SES	State Employment Service

ToRs	Terms of reference

UX	User Experience

UI	User Interface

- Context

Ukraine’s labour market continues to experience significant pressure due to demographic decline, wartime migration, internal displacement, and rapid technological change. Although 1.4 million young people are currently employed, a similarly large number could still be activated. Many students and young adults remain outside employment, education or training. Among older workers, economic activity is also low: of the 10.3 million Ukrainians of pension age, fewer than 30% are employed due to outdated skills, age discrimination, or disincentives in pension legislation.

As a result, a substantial share of working-age people remains outside the labour market, while employers in key economic sectors face persistent workforce shortages.

To address these challenges, the Ministry of Economy, Environment and Agriculture of Ukraine (MoEEA) has approved a new Employment Strategy to 2030 aimed at reducing unemployment, expanding access to decent jobs, and promoting activation and inclusion, mobilising untapped workforce potential, and boosting labour productivity to support economic resilience and sustainable growth. The strategy underscores the importance of aligning skills development with labour demand and fostering formal, productive employment that increases overall labour productivity and competitiveness.

Among the available policy tools, training, reskilling and upskilling remain the most effective pathways for helping people enter or re-enter the labour market, while also enhancing the productivity and adaptability of Ukraine’s workforce in a rapidly changing technological and economic landscape.

In parallel, the Skills4Recovery Multi Donor Initiative, implemented by GIZ in cooperation with national partners, supports systemic reforms in vocational education, workforce development and labour market integration. The programme strengthens institutional capacity, promotes modern skills development approaches and contributes to expanding access to training and reskilling opportunities across regions.

The proposed communication campaign builds upon these reform efforts and aims to increase awareness, participation and public engagement in labour-market activation measures supported under the Employment Strategy and Skills4Recovery framework. It places a particular focus on positioning activation as a driver of productivity gains, innovation uptake, and sustainable economic recovery.

To support the MoEEA in these efforts, GIZ seeks to procure a contractor to design and implement a nationwide communication campaign under the umbrella theme “Inclusion and Activation for the Labour Market”.

The campaign consists of two flagship strands:

- Strand A – Experience Matters 50+

- Strand B – Youth Skills & Mentorship Pathway

Both strands target groups currently underrepresented in the labour market and promote skills development as a key pathway to activation, productivity enhancement, and long-term employability.

The campaign shall explicitly address behavioral and structural barriers that prevent participation in training and employment pathways, including:

- Low perceived economic value of re-skilling at later stages of life

- Age-based stereotypes among employers

- Youth disengagement or outward migration intentions

- Limited awareness of available activation measures

- Tasks to be performed by the contractor

Objective of the Assignment

- Strategic objective

The campaign supports the implementation of the Employment Strategy 2030 by promoting labour-market activation and inclusion, strengthening participation in training and reskilling measures, and contributing to improved labour productivity and economic resilience.

- Behavioural objective

Increased measurable engagement of target audiences with activation measures, including enrolment in training, mentorship uptake, employer participation, and participation in activation initiatives.

- Institutional Objective

The campaign positions the MoEEA as a leading institutional driver of modern workforce development and inclusive labour-market reform.

- Target groups

The campaign primarily targets two groups currently underrepresented in the labour market:

- adults aged 50+ who are outside the labour market or at risk of labour market exclusion, and

- young people (ages 16-35) seeking pathways into employment through skills development, mentoring and training opportunities.

- In addition, the campaign aims to engage employers and businesses as key partners in workforce activation, encouraging their participation in training, mentoring and employment initiatives.

- Secondary audiences include labour market institutions, training providers and the broader public, to strengthen awareness and support for labour-market activation and skills development.

This ToR defines a set of minimum mandatory deliverables required from all bidders to ensure comparability of offers while preserving the Contractor’s creative flexibility. Contractors may additionally propose optional or value-added elements based on their methodology, strategic approach and expertise.

  - Tasks

The contractor is responsible for providing the following work:

2.1.1 Campaign Strategy & Creative Concept Development

The Contractor shall develop a comprehensive umbrella campaign strategy integrating both flagship strands under the institutional theme:

“Inclusion and Activation for the Labour Market” (by positioning activation as a driver of productivity, competitiveness and sustainable economic recovery).

The umbrella theme reflects the programme output and shall be preserved institutionally. The Contractor may develop a public-facing headline or slogan aligned with this theme.

The Contractor shall deliver:

- Audience segmentation and targeting strategy

- Clearly defined behavioural objectives for each target group (e.g. enrolment in training, internship participation, mentorship uptake, employer engagement)

- Key messaging framework (umbrella + strand-specific)

- Media and activation plan (national and regional components)

- Proposed KPIs and Monitoring & Evaluation framework, including measurable indicators related to awareness, engagement, participation and conversion to activation measures

- Detailed implementation roadmap

- Risk and sensitivity assessment, including mitigation measures related to political, social or reputational risks

- Activity-based budget breakdown

- Three distinct high-level creative directions (each including big idea, draft slogan, tone of voice, indicative visual approach)

- One final approved creative concept

- Draft visual identity system and brand architecture

- Detailed content architecture and production plan for digital, PR and paid promotion outputs. Final production quantities are specified under section 2.1.2.

The communication approach shall:

- Apply dignity-based framing in all messaging

- Avoid any language that may be perceived as ageist, discriminatory or diminishing

- Ensure respectful portrayal of both young people and individuals aged 50+

- Avoid framing target groups as “burden”, “inactive population” or “reserve workforce”

- Promote inclusion, empowerment and opportunity, while reinforcing the economic value and contribution of both target groups.

Branding and Visibility Requirements

All campaign materials, visual identity elements and communication outputs shall comply with:

- Official branding and communication guidelines of the MoEEA;

- Skills4Recovery programme visibility and branding requirements;

The Contractor shall integrate required logos, visual elements and acknowledgements in accordance with the respective branding manuals and approval procedures.

The Contractor shall ensure coherent brand architecture, avoiding visual conflict between institutional and programme identities.

All visual concepts shall be subject to prior approval by the Contracting Authority before production.

2.1.2 Production of Communication Materials

Based on the approved campaign strategy and final creative concept (as defined under section 2.1.1), the Contractor shall produce and deliver all communication materials required for the nationwide implementation of the umbrella campaign and its two flagship strands.

All materials shall comply with approved branding and visibility requirements and shall apply dignity-based framing principles.

Final production quantities may be adjusted at inception phase; bidders shall provide unit rates per item to allow scaling without revising the overall budget structure.

A. Cross-Strand Digital & Paid Production (Umbrella Level)

The Contractor shall produce the following digital and paid promotion materials applicable across both flagship strands:

Organic Digital Content

- 10 static posts (Facebook / Instagram)

- 6 carousel posts (Facebook / Instagram)

- 6 vertical videos (Reels / TikTok / YouTube Shorts format)

- 2 story sets (each set consisting of 3–5 stories)

Copywriting & Adaptations

- Ukrainian-language copy for all materials

- English-language version where required

- Adaptation of visuals and videos into platform formats (1:1, 4:5, 9:16 as applicable)

Paid Promotion Assets

- 4 static ad creatives

- 2 video cutdowns (short paid versions derived from hero or vertical content)

- All assets shall be delivered in ready-for-launch formats optimised for Meta, Google, YouTube and other relevant platforms.

B. Strand A – Experience Matters 50+

The Contractor shall produce strand-specific materials tailored to adults aged 50+ and employers.

Minimum required outputs:

- 1 core message and visual asset package for the 50+ strand

- 1–2 short-form hero videos promoting participation by employers and candidates

- 3–4 storytelling materials illustrating activation pathways (e.g. anonymized profiles, composite narratives, testimonials, photo essays or short-form video formats). Regional activation toolkit (templates, instructions, visuals) for employment centres and partners (in coordination with the State Employment Service)

Materials shall:

- Emphasise the economic and experiential value of workers aged 50+

- Avoid paternalistic or deficit-based framing

- Promote access to upskilling and reskilling modules

- Highlight employer participation and intergenerational workforce value

Engagement with stakeholders shall be conducted via publicly available institutional communication channels, in line with the data protection approach outlined below..

Storytelling materials shall be based on:

- anonymised or composite narratives, or

- individuals who have provided their own prior, informed consent directly to the Contractor.

The Contractor shall be solely responsible for obtaining and documenting any required consent where identifiable individuals are featured.

Any processing of personal data shall be limited to what is strictly necessary for the implementation of the campaign and shall comply with applicable data protection regulations (e.g. GDPR principles such as data minimisation and purpose limitation). No sensitive personal data shall be processed.

C. Strand B – Youth Skills & Mentorship Pathway

The Contractor shall produce strand-specific materials tailored to youth audiences.

Minimum required outputs:

- Youth-centric key messages and visual identity elements aligned with the umbrella concept

- 1–2 short-form hero videos (15–30 sec, vertical-first format suitable for TikTok, Instagram, YouTube Shorts). Collaboration tools for youth networks (templates, briefs, guidance materials).

- Materials shall:

- Promote skills training and mentoring pathways

- Highlight success stories of youth transitioning into employment or launching projects

- Be adapted to youth-oriented digital formats

- Address motivational and structural barriers affecting youth engagement

D. PR & Media Materials

The Contractor shall produce:

- 6 press releases

- 6 media advisories

PR materials shall align with campaign milestones, regional activation phases and the national flagship event.

E. Cross-Strand Production & Technical Requirements

In addition to the above, the Contractor shall deliver:

- Final brand kit and design system

- OOH print-ready adaptations and technical files

- Master production files for all materials

- Materials formatted for both digital and offline dissemination

All materials shall be delivered in approved, ready-for-dissemination format prior to campaign launch.

Production volumes and formats shall be proportionate to the overall campaign objective and budget ceiling and shall not compromise the ability to achieve the required dissemination scale. Production volumes defined under section 2.1.2 shall be sufficient to enable achievement of the reach requirement specified in section 2.1.4.

2.1.3 Landing Page Development

The Contractor shall design and develop a campaign landing page (or standalone one-page website) for integration into the SES/MoEEA website.

This shall include:

- UX/UI design

- Visual design aligned with campaign identity

- Content integration

- Analytics tagging requirements. Privacy-compliant analytics setup using aggregated and anonymized tracking data only, in alignment with GDPR requirements and the data protection framework of the State Employment Service/MoEEA

- Handover package for SEC IT deployment

The landing page shall be fully functional and approved by the Contracting Authority and SEC/ME IT, including confirmation of GDPR compliance, prior to acceptance.

2.1.4 Campaign Implementation

The Contractor shall implement the umbrella campaign and both flagship strands nationwide over a period of 3–4 months.

This includes:

- Dissemination across approved digital and offline channels

- Paid promotion shall rely exclusively on platform-based anonymised targeting tools (Meta, Google, YouTube and relevant platforms).

- Distribution and media pitching of PR materials to national and regional media. OOH placement coordination and monitoring (minimum 10 cities, 2-3 months)

- Regional activation support

- Development and implementation of one national flagship umbrella event in second half of May (Kyiv, offline, 500+ guests).

- Ongoing KPI monitoring (Monitoring and reporting shall rely exclusively on aggregated and anonymised performance data.)

- Mid-campaign optimization

Event participation management shall be organised independently by the Contractor in line with the data protection approach defined in the ToR.

The Contractor shall ensure that any collection and processing of personal data related to event participation is limited to what is strictly necessary and is carried out in compliance with applicable data protection regulations (e.g. GDPR), including appropriate consent or other lawful basis, data minimisation and purpose limitation. No sensitive personal data shall be collected or processed.

Reach Requirement

The campaign shall achieve a minimum net unique reach of 3–4 million individual users within Ukraine.

Reach shall be measured as:

- Unique individuals reached (not impressions)

- Excluding duplicate exposures where technically feasible

- Verified through platform analytics and reporting tools

Impressions alone shall not be considered sufficient for meeting the reach requirement.

Where technically measurable, the Contractor shall aim to ensure a minimum effective frequency of two exposures per user on digital channels.

At least 60% of total reach shall be attributable to measurable digital channels.

Where objectively justified due to external factors beyond the Contractor’s control (e.g. force majeure, major national disruptions), reach deviations of up to 20% may be considered acceptable, subject to documented justification and approval by the Contracting Authority.

Acceptance of Deliverable 4 shall be conditional upon documented evidence of reach and implementation of the national flagship event.

Data protection and data processing approach

The Contractor shall implement the assignment in a way that does not require the collection or processing of personal data on behalf of GIZ.

Any outreach to stakeholders (including employers, businesses, training providers, media or institutions) shall be conducted using publicly available institutional contact details (e.g. general company email addresses or publicly listed contact forms).

GIZ will not provide the Contractor with personal contact data (such as names, personal email addresses or phone numbers of individuals).

Where the processing of personal data is unavoidable (e.g. limited operational activities), it shall be strictly limited to what is necessary and carried out in compliance with applicable data protection regulations (e.g. GDPR), including data minimisation and purpose limitation. No sensitive personal data shall be collected or processed.

2.1.5 Final Reporting & Evaluation

The Contractor shall submit a final report including:

- KPI performance analysis

- Net unique reach verification

- Engagement analysis

- Media performance summary

- Documentation of flagship event

- Lessons learned and recommendations

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| - Campaign Strategy & Creative Concept Development | June 2026, Kyiv | - Submission of a complete campaign strategy covering audience segmentation, behavioral objectives, messaging framework and media/activation plan - Delivery of KPIs and Monitoring & Evaluation framework, implementation roadmap and risk assessment - Presentation of three creative directions and one final approved creative concept - Delivery of draft visual identity system, brand architecture and content production plan - Compliance with branding and visibility requirements (MoEEA and Skills4Recovery) - Formal review and approval of the strategy and creative concept by the Contracting Authority |
| - Production of Communication Materials | June - July 2026, Kyiv | - Delivery of all required communication materials for the umbrella campaign and both flagship strands in line with the approved strategy and creative concept - Production of cross-strand digital content and paid promotion assets in the required formats and quantities - Delivery of strand-specific materials for both strands, including hero videos and storytelling/engagement materials - Production of PR and media materials (press releases and media advisories) aligned with campaign milestones - Delivery of the final brand kit, design system, OOH print-ready files and master production files - All materials delivered in approved, ready-for-dissemination formats and compliant with branding and visibility requirements - Formal review and approval of materials by the Contracting Authority prior to campaign launch |
| - Landing Page Development | July 2026, Kyiv | - Fully functional campaign landing page delivered and integrated (or ready for integration) into the SES/MoEEA website - UX/UI and visual design aligned with the approved campaign identity - Content integrated and ready for public use - Privacy-compliant analytics setup using aggregated and anonymized data in line with GDPR requirements - Handover package delivered for SEC IT deployment - Formal approval by the Contracting Authority and SEC IT |
| - Campaign implementation | July – August 2026, Kyiv | - Nationwide implementation of the campaign across approved digital and offline channels - Execution of paid promotion, PR outreach, OOH placements (min. 10 cities) and regional activation activities - Delivery of the national flagship event in Kyiv (500+ participants) - Achieved campaign reach of 3–4 million net unique users in Ukraine, verified through platform analytics (±20% deviation subject to approval) - Submission of performance documentation and approval by the Contracting Authority |
| - Final Reporting & Evaluation | September 2026, Kyiv | - Submission of a complete final report covering all required sections - Verified KPI performance and net unique reach based on documented analytics data - Inclusion of supporting evidence for campaign implementation and media performance - Documentation of the national flagship event - Clear analysis of campaign outcomes and key lessons learned - Practical recommendations for future activation or communication initiatives - Review and approval of the report by the Contracting Authority |

The contract duration is from 20 May 2026 till 30 September 2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| - Comprehensive campaign strategy and approved creative concept for the umbrella campaign (incl. audience segmentation, messaging framework, media plan, KPIs and implementation roadmap). Task 2.1.1. | Language: English - Strategy document and presentation of creative concepts (PPT/PDF) - Visual examples and summary of key campaign elements (editable and PDF formats) | June 2026, Kyiv |
| - Reporting on the production and delivery of all campaign communication materials for the umbrella campaign and both flagship strands (including digital content, paid promotion assets, strand-specific materials, PR materials, brand kit and OOH files), with submission of all final materials in ready-for-dissemination formats, Task 2.1.2 | Language: English/Ukrainian where required/feasible - Final materials delivered in ready-for-dissemination formats (digital and print), including editable master files, platform-ready assets, compliant with approved branding and visibility requirements | June-July 2026, Kyiv |
| - Reporting on the design, development and delivery of a functional campaign landing page for integration into the SES/MoEEA website, Task 2.1.3 | Language: Ukrainian and English - Delivered with UX/UI design, integrated content and privacy-compliant analytics setup; - Handover package provided for SES/MoEEA IT deployment (design files, code or integration package) | July 2026, Kyiv |
| - Reporting on the nationwide implementation of the umbrella campaign and both flagship strands (including digital and offline dissemination, paid promotion, PR outreach, OOH placements and the national flagship event), with submission of performance data, reach verification and documentation of key activities, Task 2.1.4 | Language: Reporting submitted in English (with campaign materials produced primarily in Ukrainian, English where required) - Activities and performance data; - Reach of 3–4 million net unique users verified through platform analytics; - Documentation of the national flagship event and KPI monitoring results | July - August 2026, Kyiv |
| - Final campaign report (incl. performance analysis, reach verification, media results and lessons learned), Task 2.1.5 | Language: English - Report with supporting analytics data and documentation of the flagship event (PDF and editable format) | September 2026, Kyiv |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer shall describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

If the Contractor provides fewer experts than the number of positions described, the experts will be assessed for all requirements and qualifications for all positions they are intended to cover.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): university degree (master’s degree or equivalent) in journalism, media and communication, education/philology, social sciences or any related field, allowing the expert to perform the tasks

- Language (2.1.2): C1-level language proficiency in English.

- General professional experience (2.1.3): 10 years of professional experience in the PR, Communications, Marketing, including Digital Marketing sector

- Specific professional experience (2.1.4): 5 years in development and implementation of nation-wide communication campaigns, in particular strategies, plans, and creative concepts for the communication campaigns:

  - Proven experience of expertise in conducting of nation-wide information campaign

  - 5 weblinks/PPT, presenting the portfolio of the responsible expert in the relevant area.

- Leadership/management experience (2.1.5): 4 years of management/leadership experience as project team leader or manager in a company

- Development cooperation (DC) experience (2.1.7): 3 years of experience in DC projects, including international cooperation (with donor organisations, international agencies, or cross-border projects), in particular in the area of education, vocational training; cooperation with ministries (e.g. MoEEA, SES, etc.), embassies, stakeholders in educational sector, creative industries.

## Short-term expert pool with minimum 3, maximum 5 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 10 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- Overall responsibility for implementation of the tasks indicated in the assignment during the whole implementation period

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

Qualifications of the short-term expert pool

- Education/training (2.6.1): all experts with university qualification (master’s degree or equivalent) in journalism, media and communication, social sciences, education/philology, or any related field, allowing the experts to perform the tasks

- Language (2.6.2): all experts with B2-level language proficiency in English

- General professional experience (2.6.3): all experts with 7 years of professional experience in the communication sector, PR and marketing as well as digital marketing sector

- Specific professional experience (2.6.4): all experts with 5 years of professional experience in areas covering the tasks indicated in the assignment

- Development cooperation (DC) experience (2.6.6): all experts with 2 years of experience in DC projects, in particular with the projects in area of education, vocational training; cooperation with the ministries (e.g. MoEEA, SES, etc.), embassies, stakeholders in educational sector; creative industries.

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations and reporting documents are to be observed. See Annex 2 to these Terms of Reference.

| Travel expenses | Unit of measurement | Quantity |  | Comments (if any) |
| --- | --- | --- | --- | --- |
| Fixed travel budget | UAH | 100.000 |  | A budget is earmarked for travel to the following countries: Ukraine. A fixed budget of UAH 100.000 is earmarked for settling travel expenses against evidence/performance. This amount includes accommodation, per diems, travel costs (train, compensation for own transport 13,71 UAH/km, taxi, bus)., Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. Travel under this Contract may be required solely for the purpose of providing the following services in Ukraine, subject to prior written approval by the responsible GIZ project representative. |

## Specification of inputs

## The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

## Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| Milestones/partial works | Estimated expert days for orientation | Anticipated deadline/place/person responsible |
| --- | --- | --- |
| - Campaign Strategy & Creative Concept Development | - | June 2026, Kyiv, Contractor |
| - Production of Commu-nication Materials | - | June - July 2026, Kyiv, Contractor |
| - Landing Page Development | - | July 2026, Kyiv, Contractor |
| - Campaign implementation | - | July - August 2026, Kyiv, Contractor |
| - Final Reporting & Evaluation | - | September 2026, Kyiv, Contractor |

# Inputs of GIZ or other actors

GIZ and the MoEEA are expected to make the following available:

- Ongoing support on request of the Contractor on GIZ specific requirements during the contract implementation.

- Financial provisions

  - Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, but excl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

The allocated budget for the Campaign Strategy & Creative Concept Development (acc. milestones #1) shall not exceed 20% of the overall budget of the financial bid (price schedule).

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance of each Working Package;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works (“up to”), on the ground of original invoices, acts of acceptance and service entry sheet (LERF) submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment.

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance and service entry sheet (LERF) shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

- Each invoice and act of acceptance shall contain the Project Number, contract number and the percentage for cost split as follows:

- G-011831-004 – 50 %;

- G-011831-006 – 50 %.

- By submitting the Invoice, the Contractor should indicate (in the invoice) whether the Contractor is a Single Taxpayer (e.g. 5%, 2%) or a VAT Payer (20%).

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH  published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _______ (indicate name/-s, surname/-s, phone/-s, e-mail/-s).

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

The given procurement of works upon the Contract shall be carried out at the funds of the funds of the Project of International Technical Assistance (Project ITA), PN: 2021.2045.7, 700002297, Project title “ Vocational Education in Ukraine/Skills4Recovery ”, registered by the Secretariat of the Cabinet of Ministers of Ukraine (registration card of the project (program) No. 5296-04  dated 29.01.2026) and complies with the category (type) of Services specified in the purchase plan available at address https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel

The above-mentioned ITA project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008.

The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, then the Contractor shall notify GIZ of such VAT registration in writing or in electronic form by means of submission of an e-mail with copy of the Excerpt from VAT Registration Registry to the GIZ’s e-mail address indicated in the details of the Contract. The Contractor shall submit the mentioned notification to the GIZ not later than 1 calendar day following the day of VAT registration.

At the same time the Parties agreed that the purchase of Services after the VAT registration of the Contractor shall be exempt from VAT in accordance with the abovementioned.

# Outsourced processing of personal data

The Contractor confirms its acceptance of personal data processing by the provisions of the EU General Data Protection Regulation (GDPR) and Law of Ukraine “About personal data protection” № 2297-VI dd. 01.06.2010.

The performance of the contract may be associated with the processing of personal data by the contractor, such as (but not limited to) names and contact information. In such cases, the contractor shall act as an independent DATA CONTROLLER and comply with ALL applicable data protection obligations, including those from regional and local laws. The contractor shall process personal data only when a given goal cannot be reasonably attained without such data. Data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, accountability, and the data subject's numerous rights must be paid attention to. The GDPR’s data transfer rules must be considered whenever personal data leaves the EU for a third country. The GIZ is NOT in any way responsible for such processing.

  - Deliverable-Specific Data Protection Requirements

The Contractor shall comply with applicable data protection legislation, including GDPR principles if relevant.

Key principles include:

- Lawfulness, fairness and transparency in data processing

- Purpose limitation and data minimisation

- Use of aggregated and anonymised performance data wherever possible

- Secure handling and transfer of master production files

- No independent collection or retention of personal data beyond contractual necessity

- Documented informed consent where identifiable individuals appear in published materials (excluding public officials acting in official capacity)

Platform-based anonymised targeting tools (Meta, Google, YouTube, etc.) shall be used for paid promotion. The Contractor shall not use independently collected personal data for advertising purposes.

- Upon handover of materials, responsibility for further storage and use shall transfer to the Contracting Authority in accordance with applicable regulations.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid shall correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid shall be legible (font size 11 or larger) and clearly formulated. It shall be drawn up in English.

The complete technical bid shall not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs shall be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They shall clearly show the position and job the proposed person held in the reference project and for how long. The CVs shall be drawn up in English.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Financial bid (Price schedule)

    - The commercial bid must include the costs associated with the implementation of the assignment and shall be provided according to the format provided in the tender documentation.

Financial bid (Price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provided according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Annexes

- Annex 1 – Communication strategy of the Ministry of Economy, Environment and Agriculture

- Annex 2 – Travel regulations

Annex 2 Travel regulations (hereinafter – Regulations)

1.Business trips of experts/consultants All experts/consultants who are travelling on behalf of and commissioned by GIZ should use these Travel regulations for calculation and compensation of costs if these costs are stipulated in the Contract. For the claim of travel expenses, the experts/consultants shall submit documents according to the terms of the Regulations, unless otherwise is expressly stated in the Contract. Compensation of travel expenses is carried out exclusively within the limits of the amounts for individual items fixed in the Contract. Payment of advances for business trips is possible only if it is expressly stated in the Contract.

2. Definition of a business trip A business trip, as defined by the GIZ’ general regulations governing the reimbursement of travel expense and accommodation, involves an expert/consultant temporarily working at a place other than his/her regular domicile and/or seat of business to conduct official business with GIZ's approval. The duration of a business trip (period of absence) shall be calculated as the time between departure from the place of residence or the principal place of work at the start of the business trip and the return to any of the above-mentioned places on completion of the business trip.

3. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – act of acceptance. Against evidance – copy of the original invoice from the hotel or other actual service provider with period of stay, names of guests, type and number of rooms, price per night, total amount, meals (if included). (Service fee of booking platforms is not to be reimbursed).

4. Per diem allowance The per-diem allowance covers the additional cost of subsistence to the expert/consultant during an assignment away from their regular domicile and/or seat of business and accrued if the condition of a one-day or more business trip is fulfilled. The minimum business trip time is a one-day business trip lasting 10 hours, including working hours and travel time. Per diems are paid within the amount specified in the Contract, as a lump sum. The reduced lump sum rate applies for one-day business trips lasting from 10 to 24 hours and depending on the type of meals at the hotel or the provision of meals from GIZ. The calculation of per diems for business trips depending on the type of meals is given in the Table 1 (see below). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – timesheets in accordance with GIZ limits Against evidence – not applicable

5. Currency of reimbursement of travel expenses Reimbursements of costs of business trips within Ukraine are paid in Ukrainian Hryvnia (UAH). Reimbursements of costs of international business trips are paid in Ukrainian Hryvnia (UAH). Reimbursement of travel expenses in foreign currency (not UAH) shall be made according to below mentioned: a) in accordance with the exchange rate that is indicated in bank account statement (for cashless transactions). b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued (for cash transactions when no bank statement is available for confirmation of the used exchange rate). c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates/ (on the date when the financial documents (proof of evidence) were issued)). (In case that invoiced foreign currency is not available at the European Commission site).

6. Flights / ground transportation (train, taxi, private vehicles, car hire/car-sharing/) Costs for transportation are reimbursed within the amount specified in the Contract, against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). The preferred mode of transport shall be economically efficient and environmentally friendly. GIZ is committed to the principles of resource conservation and environmental protection and therefore requires all partners to choose the most environmentally friendly means of transport. Experts/consultants shall take advantage of any price reductions (special rates etc.) that are available. If travel time by train is 5 hours or less, train transport shall be preferred for economic and environmental reasons

7.1 Flights Only economy class flight tickets can be reimbursed to experts/consultants. The choice of an airline company should be based on a comparison of ticket prices. The choice of a more expensive flight should be justified by an expert/consultant (e.g. a tight travel schedule combined only with the selected flight). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.2 Trains Train tickets shall be booked and purchased by the expert/consultant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.3 Taxis and group private transportation If the expert/consultant uses a taxi or a group private transportation during a business trip, abroad or in Ukraine, he\she should follow the principle of economic efficiency and necessity of usage this mean of transport. The justification for such a choice should be provided together with a financial document (proof of evidence). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - Taxi (not applicable); Group private transportation (route sheet with indication point of destination/point of arrival overall km). Against evidance – Taxi (bill or ride report or screenshot of order with price indication); Group private transportation (invoice from the actual service provider).

7.4 Private vehicles As a rule, business trips should be made by rail rather than using a private vehicle. Compensation for usage of private vehicles is allowed if such a category of costs is stipulated in the Contract. In the case of using private vehicles, GIZ compensates for such costs at a fixed rate per kilometre, using the shortest possible route (according to the calculation of the Google Maps navigator). For journeys with a one-way distance of more than 200 km, the expert/consultant shall provide evidence that using a motor vehicle is more economical than other means of transport. The basis for reimbursement and for determining which means of transport is more economical is the cost of a second-class rail ticket. If a private motor vehicle is used for other important reasons (e.g. to carry heavy luggage, documents or materials, or if local transport connections are poor), convincing and adequate reasons shall be set out by the expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - needs evidence by internal based calculation of route planner like Google-map or similar (13,71 UAH per 1 km which includes all expenses without exception, such as fuel etc.) Against evidance - not applicable

7.5 Buses Bus tickets shall be booked and purchased independently by an expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication

Table 1 / Таблиця 1

The calculation of per diems for business trips per Travel Day

Ages 16–35