| Study Monitoring and Evaluation of Psychological Services for Veterans | Project number/ cost centre: G-012436-001 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

WG		     Working Group

- Context

The project “Gender-responsive approaches to mental health and psychosocial support in Ukraine” (MH UA), commissioned by the German Federal Ministry for Economic Cooperation and Development (BMZ) is implemented until March 2029 and aims to improve the accessibility, quality, and effectiveness of mental health and psychosocial support services for war-affected populations in Ukraine.

The MH UA project is grounded in the recognition that the full-scale war has generated diverse and complex mental health needs, and that different target groups, particularly women, men, children, veterans, and persons with disabilities, experience, process, and cope with trauma in different ways. Accordingly, the project applies a trauma-sensitive and gender-responsive approach, ensuring that MHPSS services are inclusive, needs-oriented, and adapted to intersecting factors such as gender, age, disability status, displacement history, and regional context.

The project focuses on three interlinked areas:

- Context-specific capacity development of professionals working in MHPSS and related sectors;

- Improving the quality and tailoring of MHPSS services, including the development of innovative and digital therapeutic interventions; and

- Enhancing access to services and strengthening existing structures at national, oblast, and hromada levels.

Exemplary activities include training for MHPSS professionals such as psychologists, medical personnel, family doctors, and social workers; development and piloting of innovative, including digital, therapy formats; and promotion of community-level initiatives aimed at strengthening social cohesion and resilience among families, youth, and children. In addition, advisory services, analytical studies, and targeted capacity-building measures contribute to identifying systemic patterns and gaps, with the aim of improving service provision and embedding gender-sensitive and trauma-informed standards across the MHPSS system.

Currently, the MH UA project supports more than 25 civil society organisations across seven oblasts (Kyivska, Dnipropetrovska, Kharkivska, Kirovohradska, Cherkaska, Chernihivska, and Zhytomyrska). These organisations work with a broad range of key groups, including war veterans and their families, internally displaced persons, returnees, host community members, women, older persons, and persons with disabilities. MHPSS professionals providing direct psychological and psychosocial support constitute another core target group, ensuring a holistic and inclusive approach to mental health care.

The specific objective of the services to be tendered is to systematically assess the current state of psychological service provision for veterans, identify structural and practical barriers to access, and generate actionable, evidence-based recommendations to improve service delivery, coverage, and quality. By applying a trauma-sensitive and gender-responsive analytical lens, the study will contribute to a deeper understanding of how psychological services respond to the differentiated needs of veterans and their families, and how these services can be strengthened within the national veteran care ecosystem. This study will be embedded within the broader national effort to strengthen the psychological support system for war veterans and their families in Ukraine. The scale and duration of the war have resulted in a significant and growing population of veterans with diverse mental health needs, including exposure to combat-related trauma, prolonged stress, injuries, loss, and challenges related to reintegration into civilian life. Despite notable progress in policy development and service expansion, veterans continue to face barriers to accessing timely, high-quality, and appropriate psychological support, including uneven geographical coverage, limited service capacity, varying quality standards, and insufficient tailoring of services to veterans’ specific needs.

The study will align with state policies and regulatory frameworks, particularly the Government of Ukraine’s regulations governing the allocation and use of public funds for veteran support and the provision of psychological assistance, as approved by the Cabinet of Ministers of Ukraine. Within this framework, the research serves as a component of the broader monitoring and evaluation system, aimed at ensuring that psychological services meet established standards of accessibility, quality, effectiveness, and inclusiveness. Ultimately, the findings of this MHPSS study will support informed decision-making by state institutions, service providers, and development partners, contributing to more effective, inclusive, and sustainable psychological support for veterans in Ukraine.

To ensure a comprehensive and holistic understanding of the psychological support system for veterans in Ukraine, the study will examine both veterans and their family members as users of psychological services and the service providers responsible for delivering MHPSS, including psychologists, psychotherapists, medical staff, social workers, and managers of service-providing organisations. Addressing these two perspectives allows the study to capture veterans’ lived experiences of accessibility, quality, relevance, and effectiveness of psychological support, while simultaneously analysing the institutional, professional, and systemic conditions under which services are provided.

In consultation with the Ministry of Veterans Affairs of Ukraine, GIZ proposes that the contractor initially focus the assessment on Kyivska, Zaporizka, Lvivska, Chernihivska, and Mykolaivska oblasts, as these regions are considered to provide a broadly representative reflection of different geographical, socio-economic, and service delivery contexts across Ukraine. Applicants may propose and justify an alternative selection of oblasts, provided that the proposed sample ensures sufficient regional diversity and supports the representativeness of the overall analysis.

In addition to the analytical components described above, the study will produce a dedicated policy-oriented recommendations paper addressed to the Ministry of Veterans Affairs of Ukraine. This paper will translate the empirical findings of the assessment into concrete, actionable recommendations aimed at strengthening the psychological support system for war veterans and their families.

- Tasks to be performed by the contractor

  - Tasks

The contractor is responsible for providing the following services:

- Inception and start-up phase

- Select, prepare, contract, and manage experts (short- and long-term) involved in advisory, analytical, and research tasks throughout the contract period, including task allocation, quality assurance, and performance oversight.

- Provide methodological guidance, onboarding, and coordination to all assigned experts to ensure consistency of approach, adherence to ethical standards, and alignment with the agreed methodology and objectives.

- Establish project management, internal coordination, and quality control mechanisms, including timelines, reporting workflows, and communication protocols with the commissioning party.

- Manage all financial and administrative processes related to project implementation, including budgeting, expenditure tracking, accounting, invoicing, and financial reporting, in full compliance with GIZ requirements and the applicable General Terms and Conditions (AVB) of GIZ.

- Provide all necessary equipment, software, and consumables required for project implementation and assume all associated operational and administrative costs.

- Submit all required reports, including inception, interim, quarterly, and final analytical and progress reports, in accordance with the agreed schedule and to the satisfaction of the commissioning party.

## Data collection and mapping phase

- Conduct comprehensive monitoring and evaluation of psychological services provided to war veterans, their families, and relatives of the fallen, with a focus on accessibility, quality, effectiveness, and barriers to service uptake.

- Collect and analyse quantitative data on service coverage, demographics of service users, service provider distribution, and key performance indicators, including consultation frequency and session duration.

- Conduct qualitative research, including in-depth interviews with mental health professionals and online surveys with service users, to assess satisfaction levels, supervision practices, and perceived service effectiveness.

- Map and evaluate the geographical accessibility of psychological services, including:

  - Per-region mapping of service providers and organizations (governmental, non-governmental, private, and international);

  - Types of services offered (e.g. individual therapy, group therapy, trauma-focused care, hotlines, rehabilitation, family counselling, telehealth);

  - Coverage and reach (number of people served, disaggregated by veterans, family members, relatives of the fallen, gender, age, disability status; waiting times and user demographics);

  - Proximity of services to veterans and availability of barrier-free environments (physical accessibility, rural versus urban distribution, transport links);

  - Identification of key barriers (geographical distance, financial constraints, cultural stigma, systemic fragmentation);

  - Existing partnerships with local veteran hubs, municipalities, rehabilitation centres, and other community-level actors.

## Analysis and synthesis phase

- Identify gaps in the professional training of mental health specialists and assess the availability, quality, and effectiveness of supervision systems and professional support mechanisms.

- Prepare regular analytical and progress reports, including triangulation and correlation analyses between quantitative and qualitative data, identification of regional disparities in service provision, and synthesis of key findings.

- Develop evidence-based recommendations and a practical implementation roadmap for improving the psychological support system for veterans, aligned with national policies, strategies, and quality standards.

## Data management phase

- Develop, maintain, and regularly update a structured statistical Excel database compiling all collected quantitative and qualitative data, organised by region, organisation, service type, coverage, accessibility, barriers, and relevant economic indicators.

- Ensure that the database is analysis-ready, including disaggregated variables, standardized coding, pivot tables, and clear documentation to facilitate reporting, analysis, and future use by the GIZ.

As part of the implementation of the assignment, the contractor shall engage with a Working Group (WG) established to support coordination, quality assurance, and policy relevance of the study. The Working Group will comprise representatives of GIZ, the Ministry of Veterans Affairs of Ukraine, and the Coordination Centre for Mental Health. The contractor shall present key milestone deliverables to the Working Group, including the inception report, interim analytical outputs, and the final report and policy recommendations. The Working Group will provide consolidated feedback on these deliverables, which the contractor shall duly consider and, where relevant, integrate. The Working Group will have an advisory role and will not interfere with the analytical independence of the contractor. The inclusion of governmental stakeholders aims to ensure alignment with national policies and to facilitate the uptake of evidence-based recommendations on improving psychological services for veterans and their families.

The contractor shall ensure full compliance with the national data protection legislation of Ukraine and applicable international standards on personal data protection and research ethics throughout the implementation of the assignment. All personal and sensitive data collected during the study, including information related to veterans, their family members, and service providers, shall be processed solely for the purposes of this assignment and handled in a secure and confidential manner. The contractor shall establish and implement appropriate technical and organisational measures to prevent unauthorised access, disclosure, loss, or misuse of data, including secure storage, restricted access, anonymisation and/or pseudonymisation of datasets where applicable. Informed consent procedures shall be applied for all research participants, clearly explaining the purpose of data collection, use, storage, and rights of participants. No personally identifiable information shall be shared with third parties or included in public reports without explicit consent. All data shall be stored and, where required, transferred to GIZ in accordance with agreed protocols and securely deleted or archived upon completion of the assignment, in line with contractual and legal requirements.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Formation of Working Group and kick-off call | 15.06.26/Project manager & GIZ team |
| Submission of Inception Report Content: Study approach, methodology, work plan including detailed timeline, tools, and frameworks for data collection and analysis. Feedback by Working Group in one week. | 30.06.26/Research contractor |
| Submission of Interim Report Content: Updated analysis based on expanded data, feedback from the working group on the first iteration, refined recommendations, and progress against the work plan. Feedback by Working Group in one week. | 31.08.26/ Research contractor |
| Draft Final Report Preparation Content: Finalised comprehensive report incorporating Working Group feedback, including executive summary, detailed findings, recommendations, and implementation of roadmap. | 15.09.26/Research contractor |
| Final Working Group review and feedback | 21.09.26/Project Manager & Working Group |
| Submission of Final Report and recommendations for Ministry of Veterans Affairs paper | 30.09.26/ Research contractor |
| Presentation of Results to Stakeholders | 05.10.26/Research contractor |

Period of assignment is from is from 15.06.26 till 01.11.26.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Inception Report | Minimum 10 pages (excl. annexes); detailed methodology, timeline, tools Language: Ukrainian and English The report is to be prepared in Times New Roman, 12 pt font, 1.5 spacing, with clear section numbering, page numbering, and a consistent citation and referencing style throughout the document. | By 30 June 2026 |
| Interim Report (incl. annexes (database, mapping) | Minimum 20 pages (excl. annexes); data analysis from 1st iteration Language: Ukrainian and English The report is to be prepared in Times New Roman, 12 pt font, 1.5 spacing, with clear section numbering, page numbering, and a consistent citation and referencing style throughout the document. | By 31 August 2026 |
| Final Report (executive summary and recommendations paper) | Minimum 55 pages (excl. annexes); finalised report incorporating feedback, and maps, excel databases and other materials used for the project. Language: Ukrainian and English The report is to be prepared in Times New Roman, 12 pt font, 1.5 spacing, with clear section numbering, page numbering, and a consistent citation and referencing style throughout the document. | By 30 September 2026 |
| Presentation materials | PowerPoint slides summarising key findings and recommendations Language: Ukrainian and English All materials are to be prepared in Times New Roman, 12 pt font, 1.5 spacing, with clear section numbering, page numbering, and a consistent citation and referencing style throughout the document. | By 30 September 2026 |

- Concept (Technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer shall present a coherent and justified strategy for monitoring and evaluation of psychological services provided to war veterans, their families, and relatives of the fallen, based on a mixed-methods research design. The strategy will integrate quantitative and qualitative data collection and analysis in order to assess accessibility, quality, effectiveness, and barriers to service uptake in a systematic and evidence-based manner. Quantitative data will be collected through structured data extraction from service providers and, where relevant, standardised surveys, covering indicators such as service volumes, number of unique service users, demographic and geographic distribution, average number and duration of consultations, and distribution of service providers by region. In parallel, qualitative data will be gathered through semi-structured interviews with MHPSS professionals and managers of service-providing organisations, as well as online surveys and selected interviews with service users, capturing supervision practices, remuneration and workload patterns, trends in service provision, perceived service quality, and accessibility constraints.

The study design will ensure systematic integration of quantitative and qualitative findings through triangulation and correlation analysis, enabling identification of regional disparities in access to services and links between service delivery patterns and user and provider experiences. All data collection tools will be designed in line with gender-responsive and trauma-sensitive principles. Questionnaires and interview guides will allow for gender-disaggregated and intersectional analysis, taking into account factors such as age, disability status, displacement history, and family roles, while avoiding re-traumatising language or direct elicitation of traumatic experiences. Ethical safeguards, including informed consent, the option to skip sensitive questions, and referral information for psychosocial support, will be embedded throughout the research process to ensure the safety and well-being of participants.

Actors and Cooperation:

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer shall identify all relevant actors involved in the implementation and coordination of the research, including GIZ, ministry partners, veterans’ organizations, service providers, and the Working Group. The tenderer shall describe mechanisms for cooperation and communication among these actors to ensure effective data collection, validation, and feedback integration. Cooperation will be structured through regular coordination meetings, clear roles and responsibilities, and data-sharing arrangements. Safeguarding and ethical referral pathways will be integrated to ensure safe participation of service users.

Steering and Monitoring:

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer shall describe their approach to steering the study jointly with the project partners, particularly the roles and responsibilities for coordination, quality assurance, and timely delivery. This includes the integration into the results-based monitoring system to ensure transparency, accountability, and adaptive management of the research activities. Quality assurance will include tool pilots, regular spot checks, and data verification steps.

Processes and Operational Plan:

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer must detail all major work steps for data collection, analysis, reporting, and review in line with Chapter 2 tasks. These include preparatory activities, survey design, data gathering (quantitative and qualitative), iterative report drafts and feedback cycles, finalisation of reports, and presentation of findings. The operational plan shall specify timelines, milestones, and partner contributions clearly. An operational risk register will be maintained, and the toolchain will include digital data collection, a structured dataset with clear coding

Knowledge Management and Scaling-Up:

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

The tenderer shall outline measures for effective knowledge management to support learning by the partner institution and GIZ, including documentation, dissemination of results, and support for scaling-up evidence-based improvements to psychological support services for veterans.

## Project management of the contractor (1.6):

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

Backstopping Concept:

The tenderer is required to describe its backstopping concept. The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

- Process-oriented steering for implementation of the commission

- Securing the administrative conclusion of the project

- Embedding ethical and safeguarding protocols (Do No Harm, trauma-informed approaches) and ensuring referral pathways where needed

- Establishing a simple risk register and escalation mechanism to manage delays, data challenges, or contextual changes

The described project management and backstopping measures shall be included in the contractor’s fee calculations as per GIZ administrative and financial regulations.

Throughout the project phases (preparatory, research, analytical, and final) the contractor shall ensure close communication with GIZ and other partners, timely submission of deliverables, and responsiveness to feedback from the commissioning party and the Working Group.

## Further requirements (1.7)

The contractor shall ensure that the research and monitoring fully incorporate gender sensitivity principles throughout all phases of the study. This includes systematic consideration of gender differences in access to and quality of psychological services for veterans, their families, and relatives of fallen soldiers. The tenderer must apply gender-sensitive data collection and analysis methods, disaggregating all relevant indicators by gender and other relevant variables such as age, disability status, geographic location, displacement status, and socio-economic background to detect potential disparities.

Specific attention should be paid to:

- Identifying barriers faced disproportionately by women veterans in accessing MHPSS services, including social, cultural, and institutional factors, as well as compounded challenges faced by women with disabilities, widows, LGBTQ+ veterans, and those living in rural areas.

- Assessing differences in mental health outcomes and service satisfaction between genders, while ensuring that gender-specific and intersectional indicators (e.g., % of women veterans reporting stigma, % of widows accessing grief counseling, % of men accessing family therapy) are systematically tracked.

- Embedding ethical safeguards to protect participants, including confidentiality protocols, informed consent processes sensitive to gendered risks, and training of enumerators in Do No Harm and survivor-centered approaches.

- Ensuring that all qualitative research tools (interviews, surveys) incorporate gender-responsive language and approaches including the use of women-only focus groups, safe spaces, and trauma-informed facilitation methods

- Reflecting gender balance in the composition of experts conducting fieldwork and interviews where feasible and designating a clear gender focal point within the contractor team responsible for ensuring compliance with gender-sensitive standards.

- Providing recommendations to promote gender equality and inclusivity in psychological support services, aligned with international best practices and Ukraine’s gender policies.

By integrating a gender-sensitive lens, the study will contribute to a tailored and equitable mental health support system, ultimately improving outcomes for all veterans regardless of gender or intersecting identities.

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

Team Leader / Project Director

Role: Overall strategic, technical, and contractual lead of the assignment.

Tasks of the team leader

- Overall responsibility for delivery of the research project, ensuring quality assurance and adherence to timelines and ToR.

- Strategic leadership and oversight of all analytical outputs and recommendations.

- Coordination and communication with GIZ, Ministry of Veterans Affairs, Coordination Centre for Mental Health, and other stakeholders.

- Personnel management and steering of the expert team and short-term experts.

- Ensure alignment with national policies, reform priorities, and international standards.

- Lead reporting, stakeholder consultations, and presentation of findings to Working Group.

- Ensure translation of analytical findings into actionable policy recommendations and implementation roadmap.

Qualifications of the team leader

- Education/training (2.1.1): Master's degree in Psychology, Social Sciences, Economics, Law, Public Health, Public Policy, or related field relevant to the assignment.

- Language (2.1.2): C2-level language proficiency in Ukrainian (max. 5 points);  C1-level language proficiency in English (max. 5 points);

- General professional experience (2.1.3): 8 years of professional experience in the fields of psychological research, social services, healthcare, MHPSS, veterans’ policy, or related development/humanitarian sectors.

- Specific professional experience (2.1.4): 3 years in designing and implementing research/evaluation projects (max. 4 points) and 5 years of experience in conducting quality and accessibility assessments of public services in Ukraine, particularly in the fields of MHPSS, social services, and healthcare (max. 6 points).

- Leadership/management experience (2.1.5): 3 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 2 years of experience in projects in Eastern Europe, of which 1 year in projects in Ukraine

- Development cooperation (DC) experience (2.1.7): 2 years of experience in DC projects

- Other (2.1.8): 3 years of experience in qualitative and quantitative analysis, multi-stakeholder coordination with government institutions, NGOs, and international organisations, familiarity with fragile, conflict, or post-conflict environments, and experience in contract management and capacity-building approaches considered an asset.

Key expert 1 / Research and Methodology Expert

Role: Methodological and analytical lead of the study.

Tasks of key expert 1

- Lead design of mixed-methods research methodology and analytical framework.

- Develop sampling strategies, research tools, and validation frameworks.

- Oversee all quantitative and qualitative data collection and analysis.

- Conduct advanced statistical and qualitative analysis and triangulation.

- Design and manage structured database and analysis-ready datasets.

- Ensure ethical research standards, safeguarding, informed consent, and trauma-sensitive approaches.

- Coordinate methodological engagement with Working Group and integrate feedback.

- Lead drafting of analytical reports, visualisations, and evidence-based recommendations.

- Provide methodological guidance to field researchers.

Qualifications of key expert 1

- Education/training (2.2.1): Master’s degree in Social Sciences, Public Health, Statistics, Data Science, Psychology, or another related field relevant to the assignment.

- Language (2.2.2): C1-level language proficiency in Ukrainian (max.5 points); C1-level language proficiency in English (max. 5 points);

- General professional experience (2.2.3): 8 years of professional experience in the applied research, evaluation, and/or data analysis, including experience in public health, mental health, social services, or related sectors.

- Specific professional experience (2.2.4): 3 years in mixed-methods research design and implementation, including proven experience in survey design, qualitative research, statistical analysis, and reporting, as well as experience in designing trauma-sensitive methodologies for vulnerable and/or conflict-affected populations.

- Leadership/management experience (2.2.5): not applicable

- Regional experience (2.2.6): 2 years of experience in projects in Eastern Europe, of which 1 year in projects in Ukraine (country)

- Development cooperation (DC) experience (2.2.7): 2 years of experience in DC projects

- Other (2.2.8): 2 years of experience in preparing documentation for external ethics approval (IRB) is considered an asset; proficiency in Excel, SPSS, Stata, R, Python, NVivo, or equivalent analytical software required.

Key expert 2 / Field Expert

Tasks of key expert 2

- Lead the social and behavioural analysis component of the study, focusing on how veterans and their families experience, perceive, and navigate psychological services (trust, stigma, motivation, help-seeking, satisfaction, drop-out).

- Design and validate trauma-sensitive, gender-responsive qualitative and survey modules (service user survey sections, semi-structured interview guides), ensuring safe wording and avoidance of re-traumatising questions.

- Develop the sampling and recruitment approach for service users and community-level stakeholders, including strategies to reach under-served groups (women veterans, rural residents, persons with disabilities, relatives of the fallen, IDPs/returnees)

- Conduct and/or supervise qualitative data collection (in-depth interviews, focus groups where applicable) and ensure interviewer training on ethics, safeguarding, and informed consent.

- Analyse qualitative and mixed-method findings to identify structural and social barriers to access (stigma, gender norms, family dynamics, informational barriers, institutional trust, discrimination, economic constraints).

- Contribute to triangulation between qualitative insights and quantitative service data, highlighting regional disparities and patterns across different groups.

- Draft core sections of analytical outputs related to service user perspectives, barriers, equity, inclusion, and community-level dynamics; contribute to policy recommendations and implementation roadmap.

- Engage in Working Group consultations as needed and support presentation of findings in policy-relevant language.

Qualifications of key expert 2

- Education/training (2.2.1): Master’s degree in Sociology, Social Policy, Public Health, or another closely related field relevant to the assignment.

- Language (2.2.2): C1-level language proficiency in Ukrainian (max. 5 points); C1-level language proficiency in English (max. 5 points);

- General professional experience (2.2.3): 8 years of professional experience in the applied social research, programme evaluation, or needs assessments in Ukraine or comparable contexts.

- Specific professional experience (2.2.4): 3 years in designing and implementing mixed-methods studies (qualitative and quantitative), including instrument development, sampling, fieldwork management, rigorous qualitative analysis, and research with vulnerable and/or conflict-affected populations using trauma-sensitive and Do No Harm approaches.

- Leadership/management experience (2.2.5): not applicable

- Regional experience (2.2.6): 2 years of experience in projects in Eastern Europe, of which 1 year in projects in Ukraine.

- Development cooperation (DC) experience (2.2.7): 2 years of experience in DC projects

- Other (2.2.8): 2 years of experience  in gender-responsive and intersectional analysis, including disaggregation and interpretation by gender, age, disability status, geography, displacement history, and socio-economic background; proven skills in qualitative analysis and synthesis; familiarity with NVivo, Atlas.ti, MAXQDA, or structured coding in Excel considered an asset; practical experience applying informed consent, confidentiality protocols, referral and safeguarding procedures during fieldwork; ability to translate research findings into actionable recommendations and contribute to reporting in Ukrainian and English.

Expert pool 1 / Short-term expert pool (min 4– max. 5 experts)

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 10 Requirements on the format of the bid) for the assessment.

### Tasks of the short-term expert pool

- Conduct surveys, interviews, and focus groups in line with methodology.

- Support data entry, coding, and validation.

- Ensure adherence to ethical standards and safeguarding procedures.

- Provide contextual and regional insights.

- Support stakeholder engagement and logistics where required.

Qualifications of the short-term expert pool

- Education/training (2.6.1): 4 experts with university qualification (Bachelor’s) in Social Sciences, Psychology, Public Health, or another related field relevant to the assignment.

- Language (2.6.2): 4 experts with C1-level language proficiency in Ukrainian (max. 5 points); 4 experts with B2-level language proficiency in English (max. 5 points);

- General professional experience (2.6.3): 4 experts with 2 years of professional experience in the field research.

- Specific professional experience (2.6.4): 4 experts with 2 years of professional experience in supporting data collection and field research activities in social research, public health, MHPSS, or related sectors.

- Regional experience (2.6.5): 4 experts with 2 years of experience in Eastern Europe, 4 experts with 1 year of experience in Ukraine;

- Development cooperation (DC) experience (2.6.6): 1 year of experience in projects funded by international development cooperation partners, humanitarian organizations, or donor-funded programmes in social policy, public health, MHPSS, protection, or related sectors.

- Other (2.6.7): 1 year of experience working with veterans or conflict-affected populations considered an asset.

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations and reporting documents are to be observed. See Annex 1 to these Terms of Reference.

Specification of inputs

## Contracts for services:

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Team Leader / Project Director | Fee days | 1 | 70 | Oversight across whole project |
| Key experts 1 Research & Methodology Expert | Fee days | 1 | 85 | Continuous analytical lead throughout project |
| Key experts 2 Field / Social Research Expert | Fee days | 1 | 85 | Fieldwork-heavy period June-July, 2026 |
| Short-term Experts | Fee days | min 4 – max 5 experts | 120 | Regional data collection |
| Travel expenses | Unit of measurement | Quantity |  | Comments (if any) |
| Travel expenses within Ukraine | Fixed budget | 400 000,00 UAH | N/A | A fixed budget of UAH 400 000,00 is earmarked for settling travel expenses against evidence/performance. This amount includes accommodation, per diems, travel costs (train, compensation for own transport 13,71 UAH/km, taxi, bus)., Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

- Inputs of GIZ or other actors  - Not Applicable

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, incl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments on monthly basis.

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF) and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- - Each invoice and act of acceptance shall contain the Project Number, contract number

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor is _____

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

8.2 VAT Exemption – not applicable

- Outsourced processing of personal data

The data protection and information security provisions set out in the most recent GIZ AVB (section 1.10 Data Protection) apply.

The performance of the contract may be associated with the processing of personal data by the contractor, such as (but not limited to) names and contact information. In such cases, the contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including those stemming from regional and local laws. The contractor shall process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GIZ is NOT in any way responsible for such processing.

Whenever the contractor executes the instructions of a partner to the GIZ with regard to such processing, the partner shall be the data controller, and the data processing shall be carried out in accordance with the partner’s instructions as well as laws and standards to which it is subject.

If the contractor is not subject to the GDPR and the applicable laws do not contain any explanation on the data protection principles and rights mentioned here, the definitions and meanings provided by the GDPR (Regulation (EU) 2016/679) should be considered.

Unless explicitly requested by Deutsche Gesellschaft für Internationale Zusammenarbeit, assessments, reports, surveys or other data and information shared with Deutsche Gesellschaft für Internationale Zusammenarbeit must be provided on a strictly anonymous basis, which means that any information relating to an identified or identifiable natural person ("data subject") must be excluded.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- tentative work plan, outlining the timing and sequencing of activities;

- personnel (team) concept, describing the organisation of the team and qualifications of proposed experts.

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs shall follow a standardised format and clearly indicate academic background, years of professional experience, thematic expertise, language skills, and relevant reference assignments. The CVs shall not exceed 5 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

Annex 1 Travel regulations (hereinafter – Regulations)

1.Business trips of experts/consultants All experts/consultants who are travelling on behalf of and commissioned by GIZ should use these Travel regulations for calculation and compensation of costs if these costs are stipulated in the Contract. For the claim of travel expenses, the experts/consultants must submit documents according to the terms of the Regulations, unless otherwise is expressly stated in the Contract. Compensation of travel expenses is carried out exclusively within the limits of the amounts for individual items fixed in the Contract. Payment of advances for business trips is possible only if it is expressly stated in the Contract.

2. Definition of a business trip A business trip, as defined by the GIZ’ general regulations governing the reimbursement of travel expense and accommodation, involves an expert/consultant temporarily working at a place other than his/her regular domicile and/or seat of business to conduct official business with GIZ's approval. The duration of a business trip (period of absence) shall be calculated as the time between departure from the place of residence or the principal place of work at the start of the business trip and the return to any of the above-mentioned places on completion of the business trip.

3. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – act of acceptance. Against evidance – copy of the original invoice from the hotel or other actual service provider with period of stay, names of guests, type and number of rooms, price per night, total amount, meals (if included). (Service fee of booking platforms is not to be reimbursed).

4. Per diem allowance The per-diem allowance covers the additional cost of subsistence to the expert/consultant during an assignment away from their regular domicile and/or seat of business and accrued if the condition of a one-day or more business trip is fulfilled. The minimum business trip time is a one-day business trip lasting 10 hours, including working hours and travel time. Per diems are paid within the amount specified in the Contract, as a lump sum. The reduced lump sum rate applies for one-day business trips lasting from 10 to 24 hours and depending on the type of meals at the hotel or the provision of meals from GIZ. The calculation of per diems for business trips depending on the type of meals is given in the Table 1 (see below). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – timesheets in accordance with GIZ limits Against evidence – not applicable

5. Currency of reimbursement of travel expenses Reimbursements of costs of business trips within Ukraine are paid in Ukrainian Hryvnia (UAH). Reimbursements of costs of international business trips are paid in Ukrainian Hryvnia (UAH). Reimbursement of travel expenses in foreign currency (not UAH) must be made according to below mentioned: a) in accordance with the exchange rate that is indicated in bank account statement (for cashless transactions). b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued (for cash transactions when no bank statement is available for confirmation of the used exchange rate). c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates/ (on the date when the financial documents (proof of evidence) were issued)). (In case that invoiced foreign currency is not available at the European Commission site).

6. Flights / ground transportation (train, taxi, private vehicles, car hire/car-sharing/) Costs for transportation are reimbursed within the amount specified in the Contract, against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). The preferred mode of transport shall be economically efficient and environmentally friendly. GIZ is committed to the principles of resource conservation and environmental protection and therefore requires all partners to choose the most environmentally friendly means of transport. Experts/consultants shall take advantage of any price reductions (special rates etc.) that are available. If travel time by train is 5 hours or less, train transport must be preferred for economic and environmental reasons

7.1 Flights Only economy class flight tickets can be reimbursed to experts/consultants. The choice of an airline company should be based on a comparison of ticket prices. The choice of a more expensive flight should be justified by an expert/consultant (e.g. a tight travel schedule combined only with the selected flight). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.2 Trains Train tickets shall be booked and purchased by the expert/consultant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.3 Taxis and group private transportation If the expert/consultant uses a taxi or a group private transportation during a business trip, abroad or in Ukraine, he\she should follow the principle of economic efficiency and necessity of usage this mean of transport. The justification for such a choice should be provided together with a financial document (proof of evidence). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - Taxi (not applicable); Group private transportation (route sheet with indication point of destination/point of arrival overall km). Against evidance – Taxi (bill or ride report or screenshot of order with price indication); Group private transportation (invoice from the actual service provider).

7.4 Private vehicles As a rule, business trips should be made by rail rather than using a private vehicle. Compensation for usage of private vehicles is allowed if such a category of costs is stipulated in the Contract. In the case of using private vehicles, GIZ compensates for such costs at a fixed rate per kilometre, using the shortest possible route (according to the calculation of the Google Maps navigator). For journeys with a one-way distance of more than 200 km, the expert/consultant must provide evidence that using a motor vehicle is more economical than other means of transport. The basis for reimbursement and for determining which means of transport is more economical is the cost of a second-class rail ticket. If a private motor vehicle is used for other important reasons (e.g. to carry heavy luggage, documents or materials, or if local transport connections are poor), convincing and adequate reasons must be set out by the expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - needs evidence by internal based calculation of route planner like Google-map or similar (15,49 UAH per 1 km which includes all expenses without exception, such as fuel etc.) Against evidance - not applicable

7.5 Buses Bus tickets must be booked and purchased independently by an expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication

Table 1 / Таблиця 1

The calculation of per diems for business trips per Travel Day