| Development and implementation of an information campaign to build awareness of the “Dodomu” digital platform | Project number/ cost centre: 2023.2165.1-180/ G-012342-180 |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

YOUA   Project “Centers for Migration and Development (ZME), National Component –

Ukraine  “YOUA – Shaping New Paths, Building the Future of Ukraine” title

- Context

In the context of large-scale displacement of Ukrainians abroad, the issue of return and reintegration has become one of the key priorities for Ukraine’s recovery. At the same time, the decision to return is an individual one and requires access to reliable information and support mechanisms at both local and national levels.

The digital platform developed within the YOUA project by GIZ Ukraine in cooperation with the Ministry of Social Policy, Family and Unity of Ukraine provides structured information on return opportunities, access to services, employment, and interaction with communities.

The information campaign within the YOUA project is aimed at disseminating information about the digital platform containing information on the pathways for the return of Ukrainians from abroad and its functionalities among Ukrainians living abroad.

- Tasks to be performed by the contractor

The Contractor is responsible for the development and implementation of an information campaign aimed at:

- building awareness of the “Dodomu” digital platform brand;

- anchoring the brand in association with the theme of return to Ukraine;

- establishing a meaningful link between maintaining connection with Ukraine and potential return;

- informing about the test version of the platform;

- engaging Ukrainians in its testing.

The Contractor shall establish the “Dodomu” brand and enrich it with meaning through real stories.

The campaign shall communicate two key narratives:  the first being “Dodomu” with return stories, while the second focuses on maintaining connection with Ukraine (YOU+Ukraine).

All materials related to maintaining the connection of Ukrainians abroad with Ukraine  shall incorporate the YOUA project concept  -  “YOU + Ukraine”.  This concept shall ensure a unified narrative framework, where maintaining a connection with Ukraine is present as a precondition for considering return in the long term.

Principles of the Campaign:

- the campaign shall focus on the promotion of the digital platform, with the “Dodomu” platform brand serving as the central brand of the campaign;

- the campaign shall apply the YOU + Ukraine principle as a cross-cutting element across all activities;

- the campaign shall ensure a non-prescriptive approach, avoiding pressure on individuals regarding return;

- the campaign shall ensure mandatory verification of audience reach for all communication channels.

All materials produced within the campaign shall be approved by the GIZ prior to publication.

All intellectual property rights to any materials created within the campaign shall belong to the GIZ.

KPI and Performance Indicators to be achieved:

Reach among Ukrainians in Germany: at least 500,000

Reach among Ukrainians in EU countries other than Germany: at least 500,000

Reach in Ukraine: at least 5,000,000

At least 20 media publications;

At least 1,500,000 cumulative reach of media publications;

At least 500,000 video views and podcast listens

At least 3,000,000 social media reach

Average frequency of audience contact: at least 2 (each individual should be exposed to

- two or more campaign messages)

Audience engagement rate: at least 8–10%

At least 100,000 digital platform visits

At least 10,000 testers

At least 1,000 feedback responses

The above indicators shall be achieved through combined implementation of all Work Packages.

The indicators “Reach among Ukrainians in Germany”, “Reach among Ukrainians in  EU other than Germany”, “Reach in Ukraine” refer to audience groups based on the country of their current residence. The remaining indicators (including social media reach, video views, and podcast listens) reflect total campaign reach across channels and are not limited by geographic segmentation. These indicators are not cumulative and shall not be added together.

Achievement of these KPIs is a mandatory condition for the acceptance of deliverables under the contract. The Contractor provides clear and realistic approaches to achieve these results in the technical bid.

  - Tasks

The Contractor is responsible for providing the following works:

Work Packages

Work Package 1 - Development a unified creative concept for the communication campaign of the digital platform brand “Dodomu” and connection with Ukraine (YOU+ Ukraine):

•	development of the campaign concept that integrates the themes of return and connection with Ukraine (YOU +Ukraine) with the presentation of the platform’s functionalities;

•	integration of the YOU + Ukraine = YOUA principle into all stages and activities of the campaign;

•	development of key messages;

•	development of tone of voice;

•	definition of storytelling approaches and narrative frameworks;

•	development of a positioning  approach for platform testing as a joint effort between the state and its citizens;

•	development of approaches for promoting the platform after the release of its final version.

Work Package 2 - Preparation and implementation of media special projects

2.1. Preparation and implementation of media special projects (media for Ukrainians in Germany in the Ukrainian language): return stories “Dodomu”

•	selection of five protagonists (with focus on women with children; three stories from Germany and two from other countries) who have returned to Ukraine after staying abroad and are willing to share their experiences;

•	organisation and conduct of interviews;

• preparation of written materials, including mandatory reference to the YOUA project in each publication;

•	preparation of visual content to accompany publication;

•	editorial support and coordination with media outlets;

•	ensuring publication of five stories in media outlets in Germany targeting Ukrainian audiences, with a minimum audience reach of a least 10,000 per publication;

•	confirmation of audience reach, including media kits, official media data, or analytical data (SimilarWeb, Google Analytics, or equivalent).

2.2. Preparation and implementation of media special projects (Ukrainian media): connection with Ukraine - YOU+Ukraine:

•	selection of five protagonists (preference for women with children; two stories from Germany and two to three from other countries) who left Ukraine after February 2022 but implement initiatives supporting Ukraine or organise activities for Ukrainians abroad to maintain Ukrainian identity;

•	organisation of interviews;

•	preparation of written materials, including ensuring a mention of the YOUA project in each publication;

• clear linkage with the theme of return;

• inclusion of the question “What does connection with Ukraine (YOU + Ukraine) mean to you?” in each story;

•	preparation of visual content;

•	editorial support;

•	ensuring publication of five stories in leading online media in Ukraine (Top 5 by audience reach);

•	confirmation of audience reach, including media kits or official media data, analytical data (SimilarWeb, Google Analytics, or other).

Work Package 3 - Implementation of special projects with popular Ukrainian podcasts

•	selecting of five Ukrainian podcasts with an audience of at least 100,000 listeners each;

•	ensuring the production and placement of content by the podcasts: 5 popular Ukrainian podcasts will produce two episodes each. The first episode will focus on stories of returning to Ukraine under the title “Dodomu,” and the second will focus on stories of women who have been living abroad since 2022 and are implementing initiatives that help maintain connections with Ukraine or support Ukraine (YOU+Ukraine), including ensuring a mention of the YOUA project in each episode;

• selection of 10 protagonists: 5 women for stories of returning to Ukraine; 5 women who have been living abroad since 2022 and are implementing initiatives that help maintain connections with Ukraine or support Ukraine;

•	producing 10 episodes (two per podcast), including selection of speakers, preparation of  episode outlines, and integrating the YOU+Ukraine theme into each episode;

•	development and implementation of a promotion strategy for podcast content, including  targeted outreach to Ukrainians living abroad and distribution through social media and partner channels;

•	monitoring and reporting of podcast performance, including audience reach and number of listens.

Work Package 4 - Development and implementation of the digital segment of the campaign in social media

4.1. Development and implementation of the digital segment of the campaign in social media - first part (return stories + connection with Ukraine stories):

•	development of a two-month content strategy for Facebook, Instagram, and TikTok including content formats, key messages, and posting schedule;

•	creation of “Dodomu” branded social media pages and content formats for Facebook and Instagram;

•	development of TikTok content formats under the “Dodomu” brand;

•   regular publication of content, including at least one post per week per platform, with a total of no fewer than 20 content units during the phase; initial posts may include return stories, followed by calls for users to submit their own stories and publication of verified user stories for the Ukrainian audience;

•	targeting and promotion of posts to Ukrainians in Germany;

•	development  and implementation of a user-generated content mechanism;

•	including mandatory reference to the YOUA project in each publication.

4.2. Development and implementation of the digital segment of the campaign in social media - second part (digital platform promotion):

•	development and implementation of a three-month content strategy for platform promotion (Facebook, Instagram, and TikTok);

•	development and production of content, including instructional video series on how to use the platform and videos encouraging participation in testing and submission of feedback;

•	planning and implementation of targeted digital advertising campaigns aimed at Ukrainians in Germany;

•	including mandatory reference to the YOUA project in each publication.

4.3. Ensuring Feedback Collection from Platform Testing:

•	development and implementation of a system for collecting user feedback;

•	analysis of collected feedback data;

•	preparation of an analytical report with key findings and recommendations.

Work Package 5 - Organization and implementation of media outreach about the digital  platform:

•	selection of two media outlets in Germany, each with an audience of at least 50,000 Ukrainians; five Ukrainian-language media outlets in Ukraine (from the Top 10 by audience reach), three English- language media outlets in Ukraine (from the Top 5 by audience reach);

•	preparation of communication materials about the platform, including explanation of its functionality, user guidance, and calls to participate in testing;

•	ensuring publication of materials, including mandatory reference to the YOUA project in each publication;

•	confirmation of audience reach using media kits, official media data, and analytical tools (SimilarWeb, Google Analytics, or other).

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| WP# | Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- | --- |
| WP1 | Approved unified creative concept document including campaign logic, key messages, tone of voice, storytelling approaches, and post-launch communication approach. | Withing 20 calendars days from the date of contract signing/ remote/Contractor | Approved concept document covering campaign logic combining return to Ukraine and connection with Ukraine (YOU + Ukraine) with presentation of platform functionalities. |
| WP2 | Publication of media special projects, including at least 10 publications with accompanying visual content. | Within first three months from the date of contract signing/ remote/ Contractor | Published materials, including at least 10 publications (5 – German media, 5 – Ukrainian media), accompanying visual content, and confirmed audience reach. Reach contribution: at least 50,000 Ukrainians in Germany and at least 500,000 in Ukraine, analytical confirmation; approval by YOUA project team. |
| WP 3 | ## Production and publication of 10 podcast episodes across selected podcasts | Within first three months from the date of contract signing/ remote/ Contractor | 10 episodes produced and published; at least 500,000 listens; analytical confirmation of performance; approval by YOUA project team. |
| WP 4 | Implementation of the first part of social media the campaign, including publication of at least 20 content units across platforms. | Within first three months from the date of contract signing/ remote/ Contractor | At least 20 content units (posts, visuals, and videos) published across Facebook, Instagram, and TikTok; at least 1,000,000 reach; at least 50,000 reach among Ukrainians in Germany; engagement at least 8–10%; analytical confirmation of reach and engagement; approval by YOUA project team. |
|  | Implementation of the second part of social media the campaign for digital platform promotion with defined performers indicators. | Within five months from the date of contract signing/ remote/ Contractor | At least 2,000,000 total reach; at least 350,000 reach among Ukrainians in Germany; at least 500,000 reach among Ukrainians in EU countries other than Germany; at least 100,000 digital platform visits; at least 10,000 users engaged in platform testing; engagement at least 8–10%; analytical confirmation of reach and engagement; approval by UA project team. |
|  | Submission of an analytical report based on collected user feedback. | Within five months from the date of contract signing/ remote/ Contractor | At least 1,000 feedback responses; analytical report based on collected feedback, including key findings and recommendations, submitted and approved by YOUA project team. |
| WP 5 | ## Publication of media outreach materials for the digital platform (minimum 10 publication) | Within four months from the date of contract signing/ remote/ Contractor | At least 10 publications (2 in media outlets targeting Ukrainians in Germany, 5 in Ukrainian-language media in Ukraine, and 3 in English-language media in Ukraine); reach contribution: at least 50,000 Ukrainians in Germany and at least 1,000,000 in Ukraine; analytical confirmation supposed by media kits, official media data, or analytical tools; approval by YOUA project team. |

Period of assignment is from 22.06.2026 till 01.12.2026.

- 2.2          Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| ## 1. Unified creative concept document in English and Ukrainian, including campaign logic, key messages, tone of voice, storytelling approaches, integration of the YOU + Ukraine principle, and post-launch promotion approach; structured, clearly formatted, and ready for implementation. | PDF file at least 15 pages | Within 20 calendar days from the date of contract signing |
| 2. Media publications package (special projects), including at least 10 published media materials and justification on the share of Ukrainian audience within the total audience | Links to publication, screenshots, visual materials (JPEG, PNG, MP4) and supporting analytical data (media kits, SimilarWeb, Google Analytics or equivalent). | Within the first three months from the date of contract signing |
| ## 3. Podcast content package, including 10 published podcast episodes and analytical data on listens and audience reach | 10 audio files and links to published episodes, and supporting analytical data (media kits, SimilarWeb, Google Analytics or equivalent) | Within the first three months from the date of contract signing |
| ## 4. Social media campaign package (Part 1) including a content strategy document in English and Ukrainian, published content (minimum 20 units across platforms), advertising campaign implementation and performance data (reach and engagement). | PDF file at least 10 pages (content strategy and reports); links and screenshots of published content, visual and video files (JPEG, PNG, MP4). | Within the first three months from the date of contract signing. |
| ## 5. Social media campaign and platform promotion package (Part 2) including a ## content strategy document in English and Ukrainian, promotional and instructional content (including video), advertising campaign implementation and performance data (reach and engagement). | PDF file at least 10 pages (strategy and reports), links and screenshots of content; visual and video files (JPEG, PNG, MP4). | Within five months from the date of contract signing |
| ## 6. Analytical report on platform user feedback in English and Ukrainian, including description of feedback collection methodology, dataset of collected feedback (minimum 1,000 responses), analysis of user behaviour and insights, and recommendations for platform improvement. | ## PDF file at least 20 pages | Within five months from the date of contract signing |
| ## 7. Media outreach package for the digital platform, including at least 10 published media materials, audience reach data. | Links to publications, screenshots, communication materials (texts and visuals) and supporting analitacal data (media kits, SimilarWeb, Google Analytics or equivalent), including justification of Ukrainian audience share. | Within four months from the date of contract signing |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1).

Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

Achievement of KPIs is a mandatory condition for the acceptance of deliverables under the contract. The tenderer shall propose clear and realistic approaches how to achieve the results in their technical proposal.

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

The tenderer is required to describe its backstopping concept. The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

- Process-oriented steering for implementation of the commission

- Securing the administrative conclusion of the project

## Further requirements (1.7)

The Contractor shall demonstrate vision in the design and implementation of socially relevant communication campaigns, including campaigns addressing public interest topics and behavioural or perception change objectives.

The Contractor shall also demonstrate vision in the development and implementation of digital communication campaigns with targeted audience outreach, including:

- audience segmentation and targeting, including diaspora or geographically dispersed audiences;

- use of social media platforms such as Facebook, Instagram, and TikTok for campaign implementation;

- planning and execution of paid digital campaigns with defined performance indicators;

- experience in engaging specific audience groups through tailored messaging and content formats.

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs, the range of tasks involved and the required qualifications. If the Contractor provides fewer experts than the number of positions described, the experts will be assessed for all requirements and qualifications for all positions they are intended to cover.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

- Overall responsibility for the implementation of all Work Packages (WP1–WP5), including quality assurance and adherence to deadlines;

- Coordination and ensuring effective communication with GIZ (YOUA project team), partners, and other stakeholders;

- Management of the project team, including planning, allocation of tasks, and coordination of short-term experts;

- Oversight of subcontractors and ensuring alignment with contractual requirements;

- Ensuring timely reporting and submission of deliverables in accordance with agreed timelines;

- Steering of project implementation and ensuring achievement of expected results.

Qualifications of the team leader

- Education (2.1.1): university degree (Master) in Social and Behavioral Sciences, Management and Administration or other related spheres.

- Language (2.1.2): B2-level language proficiency in English

- General professional experience (2.1.3): 8 years of professional experience in the communications, media, or related fields.

- Specific professional experience (2.1.4): 5 years in managing communication campaigns or projects  with a similar scope of tasks as listed in paragraph 2.1.Task of this ToR.

- Leadership/management experience (2.1.5): 3 years of management/leadership experience as project team leader or manager in a company

- Other (2.1.8):  1 year of Experience in projects funded by international organisations.

## Key expert 1- Communications Strategist Expert

## Tasks of key expert 1

- Development of the unified creative concept for the communication campaign (WP1);

- Formulation of key messages, tone of voice, and narrative framework (YOU + Ukraine);

- Development of storytelling approaches and campaign logic;

- Ensuring consistency of messaging across all Work Packages;

- Strategic guidance on positioning of platform testing and post-launch promotion;

Qualifications of key expert 1

- Education/training (2.2.1): university degree (Master) in Social and Behavioral Sciences, Management and Administration or other related spheres;

- Language (2.2.2): B2-level language proficiency in English;

- General professional experience (2.2.3): 5 years of professional experience in communication strategy development;

- Specific professional experience (2.2.4): 3 years in developing communication campaigns, including socially relevant campaigns;

- Other (2.2.8): 2 years of experience in storytelling, brand positioning, and development of integrated communication campaigns.

## Key expert 2 - Digital Campaign Manager

## Tasks of key expert 2

- Overall coordination of the digital campaign (WP4.1–WP4.3);

- Development and implementation of social media strategies;

- Planning and supervision of targeted digital campaigns and paid advertising;

- Coordination of digital content production and adaptation for platforms;

- Monitoring of campaign performance and optimisation;

- Ensuring achievement of KPIs related to reach, engagement, and platform usage.

Qualifications of key expert 2

- Education (2.3.1): university degree Bachelor in Culter and Art, Social and Behavioral Sciences, Management and Administration or other related spheres;

- Language (2.3.2): C1-level language proficiency in Ukrainian.

- General professional experience (2.3.3): 5 years of professional experience  in digital marketing or communication sector

- Specific professional experience (2.3.4): 3 years in implementing digital campaigns with targeted audience outreach

- Other (2.3.8): 2 digital campaigns completed in performance-based digital campaigns, including audience targeting and analytics.

## Key expert 3 – Communication & Partnerships Manager

Tasks of key expert 3

- Planning and implementation of media special projects (WP2, WP5);

- Identification and engagement of media outlets in Germany and Ukraine;

- Coordination of media publications (pitching, briefing, follow-up);

- Coordination of podcast collaborations (WP3);

- Management of relationships with media and content partners;

- Ensuring integration of YOUA messaging in all publications;

- Monitoring and documentation of media and podcast reach.

Qualifications of key expert 3

- Education (2.4.1): university degree Bachelor in journalism, Social and Behavioral Sciences, Management and Administration or other related spheres;

- Language (2.4.2): B2-level language proficiency in English.

- General professional experience (2.4.3): 5 years of professional experience in the  communications, media, or related fields

- Specific professional experience (2.4.4):  2 years of experience in implementation of media campaigns;

- Other (2.4.8): 2 years of Experience in cooperation with international and national media outlets, podcast or media partnerships.

## Short-term expert pool with minimum 3, maximum 5 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 11 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- development and adaptation of content (text, visual, and audiovisual);

- production of communication materials, including video, design, and digital content;

- support to social media management and community engagement;

- implementation of digital campaigns, including targeting and advertising activities;

- support to media outreach and preparation of communication materials;

- data collection, monitoring, and analysis of campaign performance;

- support to feedback collection and processing

Qualifications of the short-term expert pool (same for each member)

- Education (2.6.1): min 3 experts with university qualification Bachelor in Social sciences, Culture and Art, journalism, philology,  data analysis or other related fields;

- Language (2.6.2):  min 3 experts are C2 (native) in Ukrainian;

- General professional experience (2.6.3): min 3 experts with 5 years of professional experience with professional experience in communication, digital marketing, copywriting, media production, or analytics sector;

- Specific professional experience (2.6.4): min 3 experts with 3 years of professional experience in implementation of communication and digital campaigns

- Other (2.6.8): 2 years of experience in working with targeted audiences, including geographically dispersed or diaspora audiences.

# Costing requirements

## Assignment of personnel and travel expenses

## Not applicable.

Specification of inputs

## The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| Milestones/partial works | Estimated units | Anticipated deadline/place/person responsible |
| --- | --- | --- |
| 1. Approved unified creative concept for the communication campaign | 1 concept document including campaign logic, key messages, tone of voice, storytelling approaches and promotion approach. | Within 20 calendar days from the date of contract signing / remote / Contractor |
| 2. Publication of media special projects | 10 media publications (5 in media for Ukrainians in Germany, 5 in Ukraine) including written and visual materials | Within the first three months from the date of contract signing / remote / Contractor |
| 3. Publication of podcast content | 10 podcast episodes (2 per podcast) | Within the first three months from the date of contract signing / remote / Contractor |
| 4. Implementation of social media campaign (Part 1) with published content | 1 content strategy and at least 20 content units (posts, visuals, videos) | Within the first three months from the date of contract signing / remote / Contractor |
| 5. Implementation of social media campaign for platform promotion (Part 2) | 1 content strategy, published content, and digital campaign results (total reach, reach among Ukrainians in German, EU, platform visits, and users engaged in testing). | Within five months from the date of contract signing / remote / Contractor |
| 6. Submission of analytical report based on platform user feedback | 1 analytical report based on at least 1,000 responses | Within five months from the date of contract signing / remote / Contractor |
| 7. Publication of media outreach materials for the digital platform | 10 media publications (2 in media outlets targeting Ukrainians in Germany, 5 in Ukrainian-language media in Ukraine, and 3 in English-language media in Ukraine). | Within four months from the date of contract signing / remote / Contractor |

# Inputs of GIZ or other actors

YOUA project team will provide the Contractor with the following inputs necessary for the implementation of the assignment:

- background information on the concept of the digital platform

- existing communication materials and visual references related to the project, where available

- coordination and feedback from the YOUA project team during the development of the visual identity and design system

No additional logistical, technical or infrastructural support from GIZ is required for the implementation of this assignment.

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, incl. VAT (if applicable).

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

The Contractor shall be paid 100% post payment in instalments upon successful completion and acceptance of each Work Package stated in paragraph 2.1. Tasks.

Payments shall be made upon submission and approval of deliverables by the YOUA project team.

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF), submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF), etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

-        Each invoice and act of acceptance shall contain the Project Number, contract number;

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, and the given procurement of services/ works upon the Contract shall not be determined free from VAT,  the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor - ____________________________.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

Not Applicable.

# Outsourced processing of personal data

The Contractor confirms its acceptance of personal data processing in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and Law of Ukraine “About personal data protection” № 2297-VI dd. 01.06.2010.

The Contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including regional and local laws. The Contractor must process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GDPR’s data transfer rules must be considered whenever personal data leaves the EU for a third country. The Contractor shall comply with obligations under the applicable data protection legislation and general data privacy standards. This includes the informing the participants about the purposes of the data processing and obtaining their respective consent. The GIZ is NOT in any way responsible for such processing

# Intellectual Property Rights

All intellectual property rights to the results produced under this Contract, including but not limited to the visual identity concept, logo design, colour palette, typography, user interface elements, design system, brand book, graphic files for communication materials, and other related outputs developed within the YOUA project, shall belong to the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

The Contractor assigns to the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and to the German Federal Ministry for Economic Cooperation and Development (BMZ), free of charge, a non-exclusive and unlimited right of use for all materials and works created under this Contract.

This right of use includes the right to reproduce, distribute, publish, modify, store and communicate the works to the public, in whole or in part, including by means of electronic data processing and electronic dissemination in multimedia form, including publication on websites and digital platforms of GIZ and BMZ.

The Contractor guarantees that the works created under this Contract are original and that no rights of third parties conflict with the transfer of the rights of use.

The assignment of these rights does not require a separate agreement and becomes effective upon acceptance of the deliverables under this Contract.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

tentative work plan;

personnel (team) concept;

company portfolio demonstrating experience in similar assignments;

CVs of all experts with relevant work experience and qualifications (education, diplomas, certificates) in line with the requirements of Chapter 4 (Personnel concept).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in Ukrainian (language).

The complete technical bid must not exceed 20 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 3 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in Ukrainian (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provided according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.