CONFIDENTIAL

| Works and service contract for upgrading WASH facilities for female traders in Agbogbloshie market in Accra. | Project number/ cost centre: 21.0115.2-001.00 Tender number |
| --- | --- |

0.	List of abbreviations	2

1.	Context	3

2.	Tasks to be performed by the contractor	3

3.	Concept	4

Technical-methodological concept	5

Project management of the contractor (1.6)	5

Further requirements (1.7)	6

4.	Personnel concept	6

Team leader	7

Key expert 1	7

Short-term expert pool with minimum, maximum	8

5.	Costing requirements	8

Assignment of personnel and travel expenses	8

Sustainability aspects for travel	9

Alternative for contracts for works:	13

Workshops, events and trainings	14

6.	Inputs of GIZ or other actors	15

7.	Requirements on the format of the tender	15

8.	Option	15

Type and scope	16

Requirements	16

Quantitative requirements for the optional services	16

Requirements on the format of the tender for the option	19

9.	Outsourced processing of personal data	19

10.	Annexes	19

# List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General Terms and Conditions of Contract for supplying services and work

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

General information

- Brief information on the project

- The objective of the EAT Programme is as follows: Institutional and technical preconditions for intraregional agricultural trade are improved in selected countries in the ECOWAS region.

- Outcome 1 aims to strengthen the role of the ECOWAS Commission in coordinating sustainable and gender-sensitive agricultural trade policies. The underlying impact hypothesis is that a technically and organizationally strengthened ECOWAS Commission will be better able to coordinate and implement an intra-regional agricultural trade policy with the support of its member states.

- Outcome 2 aims to ensure that sustainable and gender-sensitive agricultural trade facilitation tools are available for coordination in ECOWAS bodies for implementation. The impact hypothesis is that participating stakeholders will benefit from agricultural trade facilitation for selected products using available services and collaboration with relevant authorities and groups at the borders of selected ECOWAS member states (as well as other checkpoints). As a result, trade will be simplified, faster in processing at borders and nodes, less costly, and more accessible and secure for women, which is a key requirement for intra-regional agricultural trade in the region.

- Outcome 3 aims to improve digital and analog services for formal and informal entrepreneurs and traders in the selected countries. The impact hypothesis is that by improving the provision of trade promotion and training services by regional and national organizations, it is possible to improve the working conditions of traders and commercial SMEs in domestic and cross-border agricultural trade.

- The target group of the project includes small and medium enterprises and trade actors in agri-food sector (agricultural producers' cooperatives, logistics companies, trade brokers, wholesalers, retailers, markets, consumers) in the ECOWAS region that are oriented towards regional trade. The project focuses on six countries, Nigeria, Niger, Benin, Côte d’Ivoire, Ghana, and Burkina Faso. The funding proposal is aimed at actors who trade, formally and informally, in agricultural commodities, semi-finished products, and finished products produced in the region, from the farm or warehouse to the consumer.

# Context

In 2023, the ECOWAS Gender Centre conducted an awareness campaign also known as the "Caravan" along selected corridors (EGDC, 2024). This initiative made it possible to gather relevant information on areas of intervention aimed at meeting the needs of women traders along the corridor.

Since 2023, the project has carried out several studies aimed at taking stock of regional trade on the Abidjan-Lagos corridor. These studies have also taken into account the state of infrastructure at the borders and in the major regional markets of the countries on the corridor.

The project also carried out a specific study on gender in 2024, focusing on the challenges faced by women traders in the regional agri-food trade.

These assessments and studies revealed a lack of infrastructure, including sheds in the markets, Water, sanitary and hygiene services (WASH) facilities at the borders and in the markets, and electricity supplies in the markets, to name a few.

The existing infrastructure in the markets is in a very poor state of repair, with little or no water supply and no roofs.

The project, therefore, aims to upgrade a WASH facility for female traders in the Agbogbloshie market in Accra with the following objectives:

- Provide gender specific convenience facilities for female traders where they can comfortably relieve themselves under hygienic and safe conditions.

- Accord women traders the ability to stay longer at the border crossings or local markets, thereby allowing them the opportunity to generate more sales without interruption from long trips back home during business hours.

- Reduce open defecation and the spread of diseases, especially among traders handling food items.

In September 2025, the EAT programme hired a consultant who produced a feasibility study on the selected site, submitted a bill of quantity (BoQ) with detailed design drawings, including the necessary permits. To this end, the project is seeking a consultant to support the physical upgrade of the WASH facility.

# Tasks to be performed by the contractor

The contractor is responsible for providing the following services:

Upgrade of the WASH facility by implementing the specifications of the BoQ provided by EAT.

Liaise with the EAT Technical Advisor and stakeholders identified in the feasibility report provided by EAT to ensure a successful implementation of the task.

Provide a timetable for completion and a detailed cost estimate using the attached BoQ excel template provided.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/partial works | Deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| Preparation and site visit | 17.05.2026/Consultant/GIZ | Site visit |
| Mobilisation, site preparation & Procurement of materials | 21.05.2026/Consultant | Materials secured |
| Complete structural upgrade of the WASH facility | 30.10.2026/Consultant | Completed facility |
| Handover of facility | 15.11.2026/ Consultant/GIZ | Certificate of completion |

Period of assignment: from May 10, 2026, until November 30, 2026.

# Concept

In the tender, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

# Personnel concept

The tenderer is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 7), the range of tasks involved and the required qualifications.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

Overall responsibility for the advisory packages of the contractor (quality and deadlines)

Coordinating and ensuring communication with GIZ, partners and others involved in the project

Personnel management, in particular, identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

Regular reporting in accordance with deadlines

Qualifications of the team leader

Education/training (2.1.1): university degree in civil engineering, building, or related disciplines

Language (2.1.2): C2-level language proficiency in English language

General professional experience (2.1.3): 7 years of professional experience in the industrial or agricultural building projects sector

Specific professional experience (2.1.4): 5 years in environmentally friendly construction

Leadership/management experience (2.1.5): 3 years of management/leadership experience as project team leader or manager in a company

Regional experience (2.1.6): 5 years of experience in projects in Ghana (region)

# Costing requirements

## Assignment of personnel and travel expenses

Per diem allowances are reimbursed as a lump sum up to the maximum amounts permissible under tax law for each country as set out in the country table in the circular from the German Federal Ministry of Finance on travel expense remuneration (downloadable from the German Federal Ministry of Finance – tax treatment of travel expenses and allowances for international business travel as of 1 January 2026 (GERMAN ONLY)).

Accommodation allowances are reimbursed as detailed in the specification of inputs below.

With special justification, additional Accommodation costs up to a reasonable amount can be reimbursed against evidence.

All business travel must be agreed in advance by the officer responsible for the project

## Sustainability aspects for travel

GIZ has undertaken an obligation to reduce greenhouse gas emissions (CO2 emissions) caused by travel. When preparing your tender, please incorporate options for reducing emissions, such as selecting the lowest-emission booking class (economy) and using means of transport, airlines and flight routes with a higher CO2 efficiency. For short distances, travel by train (second class) or e-mobility should be the preferred option.

CO2 emissions caused by air travel must be offset. GIZ specifies a budget for this, through which the carbon offsets can be settled against evidence.

There are many different providers in the market for emissions certificates, and they have different climate impact ambitions. The Development and Climate Alliance (German only) has published a list of standards (German only). GIZ recommends using the standards specified there.

Specification of inputs

| Fee days | Number of experts | Number of days per expert | Total | Comments |
| --- | --- | --- | --- | --- |
| Designation of TL/key expert/short-term expert pool | 1 | 30 | 30 | The TL is expected to lead the work and communicate with GIZ |

## Contracts for works:

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

In addition, the assessment of the financial bid is also based on the underlying daily rate. Please also provide the underlying daily rate. A breakdown of days is not required.

| Milestones/partial works | Estimated expert days for orientation | Deadline/place/person responsible |
| --- | --- | --- |
| Preparation and site visit | 2 | 17.05.2026/Consultancy firm/GIZ |
| Milestone 1 - Mobilisation, site preparation & Procurement of materials | 5 | 21.05.2026/Consultancy firm |
| Milestone 2 - Complete structural upgrade of the WASH facility | 22 | 30.10.2026/Consultancy firm |
| Milestone 3 – Handover of the facility | 1 | 15.11.2026/ Consultant/GIZ |

# Requirements on the format of the tender

The structure of the tender must correspond to the structure of the ToR. In particular, the detailed structure of the concept (Chapter 3) should be organized in accordance with the positively weighted criteria in the assessment grid (not with zero). The tender must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English.

The complete tender must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application. The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs can also be submitted in English.

Please calculate your financial tender based exactly on the parameters specified in Chapter 5 Quantitative requirements. The contractor is not contractually entitled to use up the days, trips, workshops or budgets in full. The number of days, trips and workshops and the budgets will be contractually agreed as maximum limits. The specifications for pricing are defined in the price schedule.

As the contract to be concluded is a contract for works, please offer a fixed lump sum price that covers all relevant costs (fees, travel expenses etc.). The price bid will be evaluated on the basis of the specified lump sum price. In addition, please also provide the underlying daily rate. A breakdown of days is not required. In this case, only a financial offer is required to be submitted.

# Annexes

ARCHITECTURAL DESIGN WASH FACILITY

PERMIT PROCEDURE

FINAL REPORT FOR THE PROPOSED WASH FACILITIES FOR FEMALE TRADERS – AGBOGBLOSHIE MARKET, ACCRA