| Digitalization of Single-Use Permits for International Road Transport and Data Exchange via the E-Permit System | Project number/ cost centre: G-012368-002 |
| --- | --- |

Terms of reference

- List of abbreviations

ToR	Terms of reference

GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit

UISC (ЄКІС)	Unified Information Systems Complex in the Field of Land Transport Safety (UISC) of the State Service of Ukraine for Transport Safety (Ukrtransbezpeka)

Ukrtransbezpeka	the State Service of Ukraine for Transport Safety

eQueue 	Electronic System “Electronic Border Crossing Queue” (State Agency for Restoration and Infrastructure Development of Ukraine)

E-Permit 	Digital Single-Use Transport Permit Project (Ministry of Transport and Infrastructure of the Republic of Türkiye)

E-Permit Ukraine 	E-Permit instance deployed and configured in Ukraine

E-Permit Azerbaijan	E-Permit instance of the Republic of Azerbaijan

Permit	Single-use permit for international road transport

BPMN	Business Process Model and Notation

UML	Unified Modeling Language

SDLC	Software Development Life Cycle

PKI	Public Key Infrastructure

CI/CD	Continuous Integration / Continuous Deployment (or Continuous Delivery)

API	Application Programming Interface

- Context

The project "Strengthening Sustainable and Digital Trade Routes and Logistics Concepts between Eastern Partnership Countries and the EU" (EasTnT) aims to facilitate digital transformation, promote green transport solutions, and enhance the efficiency of transport and logistics value chains in the Eastern Partnership countries (Armenia, Azerbaijan, Georgia, the Republic of Moldova, and Ukraine).

EasTnT supports the Ministry for Development of Communities and Territories of Ukraine (further referred as “the Ministry”) in digitalisation of the transport and logistics sectors to facilitate trade, create new business opportunities and strengthen regional cooperation between stakeholders in the Eastern Partnership region.

Memorandum of Understanding among the Member States of the Organization of Turkic States Regarding Cooperation and Use of Electronic Permit (e-Permit) in International Road Transport Operations (further referred as “the Memorandum”) establishes a framework for cooperation on the implementation and mutual use of electronic permits for international road transport operations between participating countries. Its purpose is to digitalise and simplify permit issuance and control procedures, enhance real-time data exchange between national systems, improve transparency and efficiency of cross-border transport, and reduce administrative and corruption-related risks. The Memorandum was signed by the Member States of the Organization of Turkic States, namely Azerbaijan, Kazakhstan, Kyrgyzstan, Türkiye, and Uzbekistan. In addition, Turkmenistan participates in the broader e-Permit initiative and is referenced in implementation and cooperation documents related to the system.

This project on the Digitalization of Single-Use Permits for International Road Transport and Data Exchange via the e-Permit System (further referred as “the Project”) aims to support Ukraine’s transition to digital single-use permits for international road transport and to introduce a mechanism for digital permit exchange using the e-Permit system between Ukraine and Azerbaijan as a pilot project, with the possibility of further scaling to other countries using the e-Permit system. The implementation of the project foresees the abandonment of paper permit forms and the automation of the processes for issuance, registration, and control of the use of digital single-use permits, as well as the provision of real-time interstate data exchange.

Currently, single-use permits for international road transport are issued and registered in paper form, which results in:

- lengthy administrative procedures;

- limited transparency in permit usage;

- risks of loss, forgery, or misuse of permit forms;

- logistical challenges related to the delivery of Ukrainian permits to other countries;

- corruption risks;

- additional costs for the state and Carriers.

Registration of paper single-use permits for international road transport issued to Ukrainian Carriers is maintained within the UISC of Ukrtransbezpeka. Control over the use of paper single-use permits for international road transport by Ukrainian Carriers is carried out through the eQueue system.

Registration of paper single-use permits for international road transport issued by Ukraine to foreign Carriers is currently not automated, and no centralized record of such data exists. Control over the use of paper single-use permits for international road transport issued by Ukraine to foreign Carriers is not automated, and no centralized record of such data exists.

At the same time, international practice (including the ECMT system and the e-Permit system) demonstrates the effectiveness of digital solutions in the field of international road transport.

The introduction of digital single-use permits is an objective necessity for:

- implementing registration, issuance, and control of the use of Ukrainian digital single-use permits by foreign Carriers;

- improving the registration, issuance, and control of the use of Azerbaijan’s digital single-use permits by Ukrainian Carriers as a pilot project;

- ensuring electronic interoperability with foreign information systems;

- increasing the effectiveness of state control;

- developing international transport and economic corridors;

- fulfilling Ukraine’s international obligations;

- supporting the digital transformation of the transport sector;

- increasing the effectiveness of state control;

- minimizing corruption risks;

- reducing the administrative burden on Carriers.

The Ministry is a final beneficiary of the works and respective deliverables specified in this ToR.

- Tasks to be performed by the contractor

A. General provisions and requirements

The objectives of the Project are as follows:

- modernization of the UISC of Ukrtransbezpeka to ensure the transition to digital single-use permits for international road transport in terms of their issuance, registration, and use by Ukraine;

- integration with the e-Permit system, including the deployment and configuration of e-Permit Ukraine to ensure the possibility of data exchange on digital single-use permits between Ukraine and countries using the e-Permit system; as well as ensuring the integration of the UISC of Ukrtransbezpeka with e-Permit Ukraine for the issuance, receipt, and use of digital single-use permits for international road transport;

- extension of electronic data exchange protocols with the eQueue system regarding the use of digital single-use permits for international road transport for departure from the territory of Ukraine by Ukrainian and foreign Carriers;

- launch of a pilot project on the digitalization of single-use permits for international road transport and data exchange via the e-Permit system with Azerbaijan concerning the issuance, registration, and use of digital single-use permits for international road transport by Ukrainian and Azerbaijani Carriers.

The Project shall provide for scalability to other countries, being parties of the Memorandum, using the e-Permit system.

B. Functional Requirements

The modernization of the UISC of Ukrtransbezpeka shall ensure the following:

For Ukrainian Carriers:

1. Registration of quotas of digital single-use permits of a foreign state for Ukraine

1.1 Receipt of the quantity of digital single-use permits of a foreign state from the e-Permit system
1.2 Calculation of the current remaining quantity of digital single-use permits of a foreign state in real time

2. Introduction of conditions and restrictions (if any), stipulated by applicable legislation, regarding the receipt of foreign permits by Ukrainian Carriers within the validity period of such permits

3. Ordering of a digital single-use permit of a foreign state by a Ukrainian Carrier

3.1 Creation of a new order

3.2 Verification of the quantity of digital single-use permits of a foreign state that may be ordered by the Carrier according to the remaining quota and applicable restrictions

3.3 Confirmation of the order by the Carrier

3.4 Payment by the Carrier for the order of the specified quantity of digital single-use permits of a foreign state

4. Issuance of a digital single-use permit of a foreign state to a Ukrainian Carrier

4.1 Receipt of numbers and electronic documents of digital single-use permits of a foreign state from integration services with e-Permit Ukraine

4.2 Entry into the order of the received numbers of digital single-use permits of a foreign state

5. Registration of issued digital single-use permits of foreign states for Ukrainian Carriers

5.1 Creation of a consolidated register of digital single-use permits of foreign states issued to Ukrainian Carriers

5.2 Display of the current status of each digital single-use permit (received, used, expired, etc.) according to data received from integration services with e-Permit Ukraine and data exchange with eQueue

6. Data exchange with eQueue regarding issued digital single-use permits of foreign states for Ukrainian Carriers

7. Use of digital single-use permits of a foreign state

7.1 Transmission by integration services with e-Permit Ukraine to the e-Permit Ukraine system of data regarding the border crossing upon departure from Ukraine by a Carrier using the specified digital single-use permit of a foreign state

7.2 Receipt from the foreign state of data regarding the border crossing upon entry by a Carrier using the specified digital single-use permit from the e-Permit Ukraine system through integration services with e-Permit Ukraine

8. Statistical reports on permit quotas, receipt, and use of digital single-use permits of foreign states by Ukrainian Carriers

8.1 Number of received and used digital single-use permits of foreign states by month/quarter
8.2 Number of ordered digital single-use permits of foreign states by Ukrainian Carriers by month/quarter
8.3 Number of received/used digital single-use permits of foreign states by Ukrainian Carriers by month/quarter

For Foreign Carriers:

9. Registration of quotas of digital single-use permits of Ukraine for a foreign state

9.1 Entry of quotas of digital single-use permits of Ukraine for a foreign state

9.2 Transmission of the quantity of digital single-use permits of Ukraine for a foreign state to the e-Permit Ukraine system through integration services with E-Permit Ukraine

9.3 Calculation of the current remaining quantity of digital single-use permits of Ukraine in real time

10. Issuance of a digital single-use permit of Ukraine to a foreign Carrier

10.1 Receipt of data (and verification of existing data) on foreign Carriers and Vehicles of foreign Carriers from integration services with e-Permit Ukraine

10.2 Verification of the quantity of digital single-use permits of Ukraine that may be received by the Carrier according to the remaining quota

10.3 Generation of numbers of digital single-use permits of Ukraine

10.4 Generation of an electronic document of the digital single-use permit of Ukraine
10.5 Transmission of numbers of digital single-use permits of Ukraine and electronic documents of digital single-use permits to the e-Permit Ukraine system through integration services with e-Permit Ukraine

11. Registration of issued digital single-use permits of Ukraine for foreign Carriers

11.1 Creation of a consolidated register of digital single-use permits of Ukraine issued to foreign Carriers
11.2 Display of the current status of each digital single-use permit of Ukraine (received, used, expired, etc.) according to data received from integration services with e-Permit Ukraine and data exchange with eQueue

12. Data exchange with eQueue regarding issued digital single-use permits of Ukraine for foreign Carriers

13. Validation/redeeming of digital single-use permits of Ukraine

13.1 Data exchange with eQueue regarding the departure from Ukraine of a foreign Carrier using the specified digital single-use permit of Ukraine

13.2 Transmission to the e-Permit Ukraine system through integration services with e-Permit Ukraine of data regarding the border crossing upon departure from Ukraine by a foreign Carrier using the specified digital single-use permit of Ukraine

13.3 Receipt from the foreign state of data regarding border crossing upon entry into the foreign state by a Carrier using the specified digital single-use permit of Ukraine from the e-Permit Ukraine system through integration services with e-Permit Ukraine

14. Statistical reports on permit quotas, receipt, and use of digital single-use permits of Ukraine by foreign Carriers

14.1 Number of issued and used digital single-use permits of Ukraine by month/quarter
14.2 Number of received/redeemed digital single-use permits of Ukraine by foreign Carriers by month/quarter

Integration with the e-Permit System Shall Ensure:

- Receipt of data regarding quotas of digital single-use permits of a foreign state for Ukraine

- Receipt of numbers and electronic documents of digital single-use permits of a foreign state

- Receipt of the status of a digital single-use permit of a foreign state

- Transmission of data regarding the border crossing upon departure from Ukraine by a Carrier using the specified digital single-use permit of a foreign state

- Receipt from the foreign state of data regarding the border crossing upon entry by a Carrier using the specified digital single-use permit

- Transmission of quotas of digital single-use permits of Ukraine for a foreign state

- Receipt of data on foreign Carriers and Vehicles of foreign Carriers

- Transmission of numbers of digital single-use permits of Ukraine and electronic documents of digital single-use permits

- Receipt of the status of a digital single-use permit of Ukraine

- Transmission of data regarding the border crossing upon departure from Ukraine by a foreign Carrier using a digital single-use permit of Ukraine

- Receipt of data regarding border crossing upon entry into a foreign state by a Carrier using a digital single-use permit of Ukraine

Extension of Electronic Data Exchange Protocols with the eQueue System Shall Ensure

- Receipt of the current status of a digital single-use permit of a foreign state

- Transmission of data regarding issued digital single-use permits of a foreign state to Ukrainian Carriers

- Receipt of the current status of a digital single-use permit of Ukraine

- Transmission of data regarding issued digital single-use permits of Ukraine to foreign Carriers

Launch of the Pilot Project on the Digitalization of Single-Use Permits for International Road Transport and Data Exchange via the e-Permit System with Azerbaijan

- Entry of test data into the UISC of Ukrtransbezpeka, within the subsystem “Centralized Registration of Permits for International Transport,” regarding both the group of functions for Ukrainian Carriers and the group of functions for foreign Carriers

- Inclusion of a pilot group of Ukrainian and foreign Carriers in the pilot project on the digitalization of single-use permits for international road transport and data exchange via the e-Permit system with Azerbaijan

- Launch into pilot operation of the groups of functions for Ukrainian Carriers within the subsystem “Centralized Registration of Permits for International Transport” of the UISC of Ukrtransbezpeka, as well as the groups of functions for foreign Carriers within the subsystem “Centralized Registration of Permits for International Transport” of the UISC of Ukrtransbezpeka

- Monitoring of the operation of the pilot project on the digitalization of single-use permits for international road transport and data exchange via the e-Permit system with Azerbaijan

C. Architecture Requirements

Figure 1. Architecture of the Project on the Digitalization of Single-Use Permits for International Road Transport and Data Exchange via the E-Permit System

The Project shall be implemented on the basis of the UISC of Ukrtransbezpeka through:

- modernization of the UISC of Ukrtransbezpeka, namely the subsystem “Centralized Registration of Permits for International Transport” of the UISC of Ukrtransbezpeka;

- integration with the e-Permit system, including the deployment and configuration of e-Permit Ukraine and the development of integration services with the E-Permit Ukraine system;

- extension of electronic data exchange protocols with the eQueue system;

- launch of the pilot project on the digitalization of single-use permits for international road transport and data exchange via the e-Permit system with Azerbaijan.

The modernization of the subsystem “Centralized Registration of Permits for International Transport” of the UISC of Ukrtransbezpeka shall be performed using the currently utilized UnityBase platform.

The UnityBase platform is a multitasking and open ECM (Enterprise Content Management) platform. The platform represents a ready-to-use full-featured toolkit for the creation of enterprise content and business process management systems, combining standard methodologies and technologies designed to address various tasks related to document management and unstructured information management.

The platform ensures high fault tolerance and security, the possibility of long-term functional development, a high level of integration with other applications, and ease of maintenance and deployment at Users’ workplaces.

Integration with the e-Permit system shall be carried out in accordance with the requirements of the e-Permit system through interaction between national systems via API using a Certificate Authority.

  - Tasks

The Contractor is responsible for providing the following works, grouped by phases:

2.1.1 Phase 1 – Preparatory Stage

- Organization and conduct of the initial kick-off meeting involving all Stakeholders;

- Development and approval, in accordance with the current requirements for the Project specified above (see Sections A, B, and C), of the Project technical documentation package:

  - the Technical Specification for the modernization of the UISC of Ukrtransbezpeka;

  - the Integration Regulation with the e-Permit system, including the description of integration services between the UISC of Ukrtransbezpeka and e-Permit Ukraine;

  - the Regulation on the Extension of Electronic Data Exchange Protocols with the eQueue system.

2.1.2 Phase 2 – Modernization of the UISC of Ukrtransbezpeka

- Modernization of the subsystem “Centralized Registration of Permits for International Transport” of the UISC of Ukrtransbezpeka regarding the group of functions for Ukrainian Carriers:

  - enhancement of the group of functions of the subsystem “Centralized Registration of Permits for International Transport” for Ukrainian Carriers in accordance with the Technical Specification for the modernization of the UISC of Ukrtransbezpeka developed under Phase 1;

  - preliminary testing of the upgraded subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for Ukrainian Carriers;

  - pilot operation of the subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for Ukrainian Carriers;

  - refinement of the subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for Ukrainian Carriers based on the results of pilot operation;

  - launch of the final version of the subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for Ukrainian Carriers.

- Modernization of the subsystem “Centralized Registration of Permits for International Transport” of the UISC of Ukrtransbezpeka regarding the group of functions for foreign Carriers:

  - enhancement of the group of functions of the subsystem “Centralized Registration of Permits for International Transport” for foreign Carriers in accordance with the Technical Specification for the modernization of the UISC of Ukrtransbezpeka developed under Phase 1;

  - preliminary testing of the integration with the e-Permit system for the upgraded subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for foreign Carriers;

  - pilot operation of the subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for foreign Carriers;

  - refinement of the subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for foreign Carriers based on the results of pilot operation;

  - launch of the final version of the subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for foreign Carriers.

- Development of User manuals for Carriers and Ukrtransbezpeka staff regarding operation of the modernized UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport”;

- Approval of the testing protocol for the modernized UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport”.

2.1.3 Phase 3 – Integration with the e-Permit System

- Deployment and configuration of e-Permit Ukraine (e-Permit instance);

- Development of the integration service of the UISC of Ukrtransbezpeka for connection to e-Permit Ukraine in accordance with the Integration Regulation with the E-Permit system developed under Phase 1;

- Development of integration services between the UISC of Ukrtransbezpeka and the e-Permit Ukraine system in accordance with the Integration Regulation with the e-Permit system developed under Phase 1;

- Testing of the integration services between the UISC of Ukrtransbezpeka and the e-Permit Ukraine system;

- Refinement of the integration services based on testing results and launch of the final version of the integration services between the UISC of Ukrtransbezpeka and the e-Permit Ukraine system;

- Approval of the testing protocol for integration with the e-Permit system.

2.1.4 Phase 4 – Extension of Electronic Data Exchange Protocols with the eQueue System

- Enhancement of the electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue in accordance with the Regulation on the Extension of Electronic Data Exchange Protocols with the eQueue system developed under Phase 1;

- Testing of the enhanced electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue;

- Refinement of the electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue based on testing results and launch of the final version of the electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue;

- Approval of the testing protocol for the extension of electronic data exchange protocols with the eQueue system.

2.1.5 Phase 5 – Launch of the Pilot Project with Azerbaijan

- Creation of a private key and publication of the certificate (public key) of e-Permit Ukraine;

- Entry of test data into the UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport,” regarding the group of functions for Ukrainian Carriers and the group of functions for foreign Carriers;

- Inclusion of a pilot group of Ukrainian and foreign Carriers in the pilot project on the digitalization of single-use permits for international road transport and data exchange via the e-Permit system with Azerbaijan;

- Launch into pilot operation of the group of functions for Ukrainian Carriers within the subsystem “Centralized Registration of Permits for International Transport” of the UISC of Ukrtransbezpeka;

- Launch into pilot operation of the group of functions for foreign Carriers within the subsystem “Centralized Registration of Permits for International Transport” of the UISC of Ukrtransbezpeka;

- Monitoring of the operation of the pilot project on the digitalization of single-use permits for international road transport and data exchange via the e-Permit system with Azerbaijan, including:

  - collection, analysis, and elimination of errors identified during the pilot project;

  - implementation of amendments/refinements to the project on the digitalization of single-use permits for international road transport and data exchange via the e-Permit system with Azerbaijan based on the results of the pilot launch (if required);

- Preparation of the report on the launch of the pilot project on the digitalization of single-use permits for international road transport and data exchange via the e-Permit system with Azerbaijan.

2.1.6 Phase 6 – Technical Support of the Pilot Project with Azerbaijan

Technical support of the pilot project shall include:

- provision of updates to the UISC of Ukrtransbezpeka released in connection with bug fixing;

- restoration of the UISC of Ukrtransbezpeka after failures/malfunctions caused by incorrect operation of the UISC of Ukrtransbezpeka;

- elimination of defects in the modernized UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport,” integration services with the E-Permit Ukraine system, and digital single-use data exchange protocols with eQueue;

- restoration of operability of the modernized UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport,” during operation, for example, in the event of failure of the subsystem “Centralized Registration of Permits for International Transport” as a whole or of its components as a result of updates or modifications implemented by the Contractor;

- restoration of operability of integration services with the e-Permit Ukraine system and digital single-use data exchange protocols with eQueue resulting from updates or modifications implemented by the Contractor;

- provision and installation of new functional versions of the UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport,” including updates of functions and data, as well as updates of user manuals for the subsystem “Centralized Registration of Permits for International Transport.” Performance of the above-mentioned actions shall be coordinated with the Technical Administrator;

- provision of consultations to responsible persons of the Technical Administrator regarding operation, use, installation, and configuration of the UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport.” Consultations shall be provided by telephone and e-mail.

The Contractor shall be responsible for regularly informing GIZ and the Ministry on the status of task implementation (at least once every two weeks), as well as for providing all necessary/requested information during reporting meetings on the status of the Project, which shall be conducted at the request of the Ministry.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones / partial works | Anticipated deadline / place / person responsible | Criteria for acceptance |
| --- | --- | --- |
| Phase 1 – Preparatory Stage |  |  |
| Stage 1. Kick-off Meeting between the Contractor, GIZ, and the Ministry | T1 = T0 (contract signing) + 1 week / online or offline at the premises of GIZ or the Ministry / Team Leader | A kick-off meeting has been conducted. |
| Stage 2. Development of the Project technical documentation package: - Technical Specification for the modernization of the UISC of Ukrtransbezpeka; - Integration Regulation with the E-Permit system; - Regulation on the Extension of Electronic Data Exchange Protocols with the eQueue system | T2 = T0 + 7 weeks (contract signing) / remote performance of the tasks / Team Lead | Project technical documentation package submitted to Ukrtransbezpeka and Ministry for review and approval. Project technical documentation package approved by Ukrtransbezpeka. |
| Phase 2 – Modernization of the UISC of Ukrtransbezpeka |  |  |
| Stage 1. Modernization of the subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for Ukrainian Carriers | T3 = T2 + 9 weeks (16 weeks from the contract signing) / remote performance of the tasks / Team Lead | The functional version of the modernized subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for Ukrainian Carriers has been deployed in the test environment at the server of Ukrtransbezpeka. |
| Stage 2. Modernization of the subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for foreign Carriers | T4 = T2 + 5 weeks (12 weeks from the contract signing) / remote performance of the tasks / Team Lead | The functional version of the modernized subsystem “Centralized Registration of Permits for International Transport” regarding the group of functions for foreign Carriers has been deployed in the test environment at the server of Ukrtransbezpeka |
| Stage 3. Development of User manuals for Carriers and Ukrtransbezpeka staff regarding operation of the modernized UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport” | T5 = T3 + 2 weeks (18 weeks from the contract signing) / remote performance of the tasks / Team Lead | User manuals has been provided to Ukrtransbezpeka and Ministry. |
| Stage 4. Approval of the Testing protocol for the modernized UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport” | T6 = T5 + 2 weeks (20 weeks from the contract signing) / remote performance of the tasks / Team Lead | The Testing protocol has been approved by Ukrtransbezpeka. |
| Phase 3 – Integration with the e-Permit System |  |  |
| Stage 1. Deployment and configuration of e-Permit Ukraine | T7 = T6 + 1 week (21 weeks from the contract signing) / remote performance of the tasks / Team Lead | Test and production environments of e-Permit Ukraine (e-Permit instances) have been deployed on Ukrtransbezpeka servers. |
| Stage 2. Development of the integration service of the UISC of Ukrtransbezpeka for connection to e-Permit Ukraine | T8 = T7 + 6 weeks (27 weeks from the contract signing) / remote performance of the tasks / Team Lead | Standardized and secure methods for digital single-use data exchange between information systems have been deployed in the test environment at the server of Ukrtransbezpeka |
| Stage 3. Development of integration services between the UISC of Ukrtransbezpeka and the e-Permit Ukraine system | T9 = T8 + 4 weeks (31 weeks from the contract signing) / remote performance of the tasks / Team Lead | Integration services between the UISC of Ukrtransbezpeka and the e-Permit Ukraine system have been deployed in the test environment at the server of Ukrtransbezpeka |
| Stage 4. Testing of the integration services between the UISC of Ukrtransbezpeka and the e-Permit Ukraine system | T10 = T9 + 1 week (32 weeks from the contract signing) / remote performance of the tasks / Team Lead | Preliminary testing protocol has been submitted to Ukrtransbezpeka and Ministry for review. |
| Stage 5. Refinement of integration services and launch of the final version | T11 = T10 + 1 week (33 weeks from the contract signing) / remote performance of the tasks / Team Lead | The final version of the integration services between the UISC of Ukrtransbezpeka and the e-Permit Ukraine system has been deployed in the test environment at the server of Ukrtransbezpeka |
| Stage 6. Approval of the testing protocol for integration with the e-Permit system | T12 = T11 + 2 weeks (35 weeks from the contract signing) / remote performance of the tasks / Team Lead | The Final testing protocol for integration with the e-Permit system has been submitted to Ukrtransbezpeka and Ministry for review and approval. The Final testing protocol for integration with the e-Permit system approved by Ukrtransbezpeka. |
| Phase 4 – Extension of Electronic Data Exchange Protocols with the eQueue System |  |  |
| Stage 1. Enhancement of electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue | T13 = T6 + 2 weeks (22 weeks from the contract signing) / remote performance of the tasks / Team Lead | Enhanced electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue have been deployed in the test environment at the server of Ukrtransbezpeka. |
| Stage 2. Testing of enhanced electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue | T14 = T13 + 1 week (23 weeks from the contract signing) / remote performance of the tasks / Team Lead | Preliminary testing protocol has been submitted to Ukrtransbezpeka and Ministry for review. |
| Stage 3. Refinement of electronic data exchange protocols and launch of final version | T15 = T14 + 1 week (24 weeks from the contract signing) / remote performance of the tasks / Team Lead | The final version of the enhanced electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue has been deployed in the test environment at the server of Ukrtransbezpeka. |
| Stage 4. Approval of the testing protocol for extension of electronic data exchange protocols with the eQueue system | T16 = T15 + 2 weeks (26 weeks from the contract signing) / remote performance of the tasks / Team Lead | The Final testing protocol for the extension of electronic data exchange protocols with the eQueue system has been approved by Ukrtransbezpeka. |
| Phase 5 – Launch of the Pilot Project with Azerbaijan |  |  |
| Stage 1. Launch of pilot project: deployment in the production environment of the groups of functions for Ukrainian and foreign Carriers of the UISC of Ukrtransbezpeka and launch into pilot operation, including integration services of the UISC of Ukrtransbezpeka with the e-Permit Ukraine system and electronic data exchange protocols between the UISC of Ukrtransbezpeka and eQueue for the selected pilot group of Carriers using test data. | T17 = T16 + 6 weeks (32 weeks from the contract signing) / remote performance of the tasks / Team Lead | The groups of functions for Ukrainian and foreign Carriers of the UISC of Ukrtransbezpeka have been deployed in the production environment at the servers of Ukrtransbezpeka and launched into pilot operation. |
| Stage 2. Preparation of the report on the launch of the pilot project on the digitalization of single-use permits for international road transport and data exchange via the E-Permit system with Azerbaijan (Pilot project launch Report) | T18 = T17 + 2 weeks (34 weeks from the contract signing) / remote performance of the tasks / Team Lead | The Pilot project launch Report has been submitted to Ukrtransbezpeka and Ministry for review and approval. The Pilot project launch Report approved by Ukrtransbezpeka. |
| Phase 6 – Technical Support of the Pilot Project with Azerbaijan | T19 = T18 + 18 weeks (52 weeks from the contract signing) / remote performance of the tasks / Team Lead | Technical Support Completion Report (containing incident and resolution log, list of deployed updates, consultations provided, and confirmation of stable operation of the modernized UISC of Ukrtransbezpeka, e-Permit integration services, and eQueue data exchange protocols during the support period) submitted to Ukrtransbezpeka and Ministry. Technical Support Completion Report approved by Ukrtransbezpeka. |

The contract duration is from 15 August 2026 till 31 December 2027.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| # | Reporting/ Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| 1 | Project technical documentation package (3 documents) Phase 1, Stage 2 | Documentation in .docx format in Ukrainian and English. Minimum 10 pages. | T2 = T0 + 7 weeks from the contract signing |
| 2 | User manuals for Carriers and Ukrtransbezpeka staff regarding operation of the modernized UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport” Phase 2, Stage 3 | Documentation in .docx format in Ukrainian and English. Minimum 10 pages. | T5 = T3 + 2 weeks (estimated as 18 weeks from the contract signing) |
| 3 | Testing protocol for the modernized UISC of Ukrtransbezpeka, subsystem “Centralized Registration of Permits for International Transport” Phase 2, Stage 4 | Documentation in .docx format in Ukrainian and English and paper version signed by all relevant parties and approved by Ukrtransbezpeka. Minimum 2 pages. | T6 = T5 + 2 weeks (estimated as 20 weeks from the contract signing) |
| 4 | Final testing protocol for integration with the e-Permit system Phase 3, Stage 6 | Documentation in .docx format in Ukrainian and English and paper version signed by all relevant parties and approved by Ukrtransbezpeka. Minimum 2 pages. | T12 = T11 + 2 weeks (estimated as 35 weeks from the contract signing) |
| 5 | Final testing protocol for the extension of electronic data exchange protocols with the eQueue system Phase 4, Stage 4 | Documentation in .docx format in Ukrainian and English and paper version signed by all relevant parties and approved by Ukrtransbezpeka. Minimum 2 pages. | T16 = T15 + 2 weeks (estimated as 26 weeks from the contract signing) |
| 6 | Pilot project launch Report Phase 5, Stage 2 | Documentation in .docx format in Ukrainian and English and paper version signed by all relevant parties and approved by Ukrtransbezpeka. Minimum 2 pages. | T18 = T17 + 2 weeks (estimated as 34 weeks from the contract signing) |
| 7 | Technical Support Completion Report Phase 6 | Documentation in .docx format in Ukrainian and English. Minimum 2 pages. | T19 = T18 + 18 weeks (estimated as 52 weeks from the contract signing) |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept).

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) and provide its interpretation of the objectives in this ToR and critical examination of the tasks (1.1.1).

Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the strategy of establishing the cooperation with and between the actors/stakeholders relevant for the services for which it is responsible (1.2.2).

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

Team Leader

Tasks of the Team Leader

- Overall responsibility for performance of the Tasks by the Contractor, including planning, project coordination, preparation of required documentation, oversight of activities, timeline adherence, quality assurance, and delivery of all project outputs

- Organisation and coordination of communication with/between GIZ, the Ministry and other Stakeholders involved in the project

- Personnel management, allocation of tasks and supervision of project team members

- Risk management, issue escalation, and resolution of project delivery issues

- Ensuring compliance with project methodology, governance, and quality standards

- Regular reporting to GIZ and the Ministry in accordance with milestones and deadlines

- Regular (on a biweekly basis) communication to GIZ and the Ministry on progress and status of performed tasks

Qualifications of the Team Leader

- Education (2.1.1): university degree (Master or equivalent) in Engineering, Computer Sciences, Software Engineering or similar.

- Language (2.1.2): B2-level proficiency in English

- General professional experience (2.1.3): 7 years of professional experience as IT project manager

- Specific professional experience (2.1.4): 3 years of experience in stakeholder management with public authorities in Ukraine

Business Analyst (Key expert 1)

Tasks of the Business Analyst

- Lead development of technical documentation including Technical Specifications, integration regulations, and related project documentation

- Support analysis, modelling, and optimisation of business processes related to digitalisation of transport permits

- Conduct analysis of data sources used for monitoring and performance assessment, including data quality, frequency, ownership, and processing methods

- Define and document business and functional requirements for system modernisation and integrations

- Support development and implementation of integration solutions and APIs between all systems involved in the project

- Propose recommendations for optimisation of business processes and transition from paper-based to digital workflows

- Support preparation of user manuals, training materials, and user guidance documentation

- Perform other tasks assigned by the Team Leader within project scope

Qualifications of the Business Analyst

- Education (2.2.1): university degree (Master or equivalent) in Information Technology, Computer Sciences, Telecommunications, Automation or similar

- Language (2.2.2): B2-level proficiency in English

- General professional experience (2.2.3): 4 years of professional experience as Business Analyst, Data Analyst or similar role in IT projects

- Specific professional experience (2.2.4): 3 years of experience in business process modelling and analysis using BPMN, UML, use cases, functional decomposition, or prototyping

Solution Architect (Key expert 2)

Tasks of the Solution Architect

- Develop and define solution architecture for system modernisation and integration between UISC of Ukrtransbezpeka, e-Permit and related systems

- Design integration architecture including APIs, data exchange models, and interoperability mechanisms

- Define data structures, data flows, and rules for data lifecycle management (versioning, archiving, updates)

- Participate in development and implementation of integration services and system components

- Ensure compliance with security, PKI infrastructure, performance, and interoperability requirements

- Analyse and document information flows, data structures, and system interactions

- Cooperate with technical teams to ensure proper integration of system components across platforms

- Provide technical recommendations for optimisation of system architecture and data processes

- Store and maintain technical documentation in accordance with project requirements

- Perform other tasks assigned by the Team Leader within project scope

Qualifications of the Solution Architect

- Education (2.3.1): university degree (Master or equivalent) in Computer Sciences, Software Engineering or similar

- Language (2.3.2): B2-level proficiency in English

- General professional experience (2.3.3): 5 years of professional experience in software/system architecture design

- Specific professional experience (2.3.4) (the maximum number of points are specified after each specific experience):

- 1 year of experience in design and implementation of API-based integrations between enterprise information systems (3 points)

- 1 year of experience working with PKI (Public Key Infrastructure) solutions and digital certificate infrastructure (3 points)

- 1 year of experience with UnityBase platform or similar enterprise application platforms (4 points)

- Other (2.3.8): Certification upon completion of the “Megapolis3.UnityBase” training

DevOps Engineer (Key Expert 3)

Tasks of the DevOps Engineer

- Support development, deployment, and integration of UISC of Ukrtransbezpeka and e-Permit systems

- Participate in design and implementation of system architecture and integration components

- Manage deployment, configuration, and environment setup (test, staging, production)

- Support development of APIs and integration services

- Ensure system availability, stability, and performance during development and pilot phases

- Implement and support data lifecycle procedures (versioning, backup, archiving)

- Collaborate with technical teams to ensure integration across platforms

- Maintain technical documentation and deployment procedures

- Provide operational and technical support during system implementation and pilot operation

- Perform other tasks assigned by the Team Leader within project scope

Qualifications of the DevOps Engineer

- Education (2.4.1): university degree (Master or equivalent) in Information Technology or similar

- Language (2.4.2): B2-level proficiency in English

- General professional experience (2.4.3): 4 years of professional experience in DevOps or system engineering

- Specific professional experience (2.4.4) (the maximum number of points are specified after each specific experience):

- 1 year of experience in CI/CD implementation and deployment automation (3 points)

- 1 year of experience in API-based integration and deployment of enterprise information systems (3 points)

- 1 year of experience working with PKI (Public Key Infrastructure) solutions (2 points)

- 1 year of experience with cloud or hybrid infrastructure environments (Azure or similar) (2 points)

UnityBase Developer (Key Expert 4)

Tasks of the UnityBase Developer

- Participate in development and integration of UISC of Ukrtransbezpeka and e-Permit systems on UnityBase platform

- Implement backend functionality, business logic, and system modules

- Support development of integration services and APIs

- Participate in system architecture implementation and refinement

- Implement data structures, workflows, and system configurations on UnityBase platform

- Support integration with external systems and registries

- Participate in testing, debugging, and optimisation of system components

- Maintain technical documentation of implemented solutions

- Perform other tasks assigned by the Team Leader within project scope

Qualifications of the UnityBase Developer

- Education (2.5.1): university degree (Master or equivalent) in Computer Sciences, Software Engineering or similar

- Language (2.5.2): B2-level proficiency in English

- General professional experience (2.5.3): 4 years of professional experience in software development

- Specific professional experience (2.5.4) (the maximum number of points are specified after each specific experience):

- 1 year of experience in development and configuration of systems on UnityBase platform (4 points)

- 1 year of experience in development of enterprise backend systems using .NET/C#, JavaScript or Node.js (3 points)

- 1 year of experience in API development and integration of enterprise information systems (3 points)

- Other (2.5.8): Certification upon completion of the “Megapolis3.UnityBase” training

Backend Developer (Key Expert 5)

Tasks of the Backend Developer

- Participate in development and integration of system modules, APIs, and backend services

- Develop and maintain integration services between UISC of Ukrtransbezpeka, e-Permit and related systems

- Support implementation of system architecture and technical solutions

- Implement data processing, business logic, and system workflows

- Participate in testing, debugging, and optimisation of backend components

- Collaborate with other developers and technical teams on system integration

- Support documentation of developed solutions

- Perform other tasks assigned by the Team Leader within project scope

Qualifications of Backend Developer

- Education (2.6.1): university degree (Master or equivalent) in Computer Sciences, Software Engineering or similar

- Language (2.6.2): B2-level proficiency in English

- General professional experience (2.6.3): 4 years of professional experience in software development

- Specific professional experience (2.6.4) (the maximum number of points are specified after each specific experience):

- 1 year of experience in development and configuration of systems on UnityBase platform (3 points)

- 1 year of experience in development of enterprise backend systems using .NET/C#, JavaScript or Node.js (4 points)

- 1 year of experience in API development and integration of enterprise information systems (3 points)

- Other (2.6.7): Certification upon completion of the “Megapolis3.UnityBase” training

QA / Test Engineer (Key Expert 6)

Tasks of the QA / Test Engineer

- Identify defects and create bug reports during development, testing, and implementation of system and integration services

- Develop test plans, test cases, and test documentation ensuring full coverage of system functionality

- Perform functional, integration, regression, end-to-end, and performance testing

- Analyse test results and provide recommendations for system improvements

- Support preparation and execution of system acceptance testing

- Participate in analysis of business logic of integrated systems (UISC, e-Permit, eQueue)

- Support user training and preparation of training materials

- Maintain test documentation and related project artefacts

- Perform other tasks assigned by the Team Leader within project scope

Qualifications of the QA / Test Engineer

- Education (2.7.1): university degree (Master or equivalent) in Information Technology or similar

- Language (2.7.2): B2-level proficiency in English

- General professional experience (2.7.3): 4 years of professional experience in QA/testing in IT projects

- Specific professional experience (2.7.4) (the maximum number of points are specified after each specific experience):

- 1 year of experience in testing of client-server and integrated IT systems (5 points)

- 1 year of experience with defect tracking and test management tools (e.g. Jira, Redmine or similar) in multi-system integration projects (5 points)

Security Engineer (Key Expert 7)

Tasks of the Security Engineer

- Participate in development and integration of system modules, APIs, and backend services to assess potential attack vectors

- Integration of security tools into integration services between Ukrtransbezpeka's UISC, e-Permit, and related systems

- Support implementation of system architecture and technical solutions

- Implement data processing, business logic, and system workflows

- Collection, correlation, and analysis of security event logs to identify anomalies and suspicious activity

- Support documentation of developed solutions

- Perform other tasks assigned by the Team Leader within project scope

Qualifications of Security Engineer

- Education (2.8.1): university degree (Master or equivalent) in Computer Sciences, Information Security, Applied Mathematics, Systems Engineering or similar

- Language (2.8.2): B2-level proficiency in English

- General professional experience (2.8.3): 4 years of professional experience in cybersecurity, information security, or system administration

- Specific professional experience (2.8.4) (the maximum number of points are specified after each specific experience):

- 1 year of experience with security monitoring and protection technologies, including SIEM, IDS/IPS, firewalls (including WAF), antivirus or access control solutions (4 points)

- 1 year of experience in securing, assessing, or monitoring API-based integrations and enterprise information systems (3 points)

- 1 year of experience with network security, including TCP/IP, VPN, DNS, routing, and switching (3 points)

# Costing requirements

## Assignment of personnel and travel expenses

No business travel activities are foreseen for this assignment.

Specification of inputs

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| Milestones / Partial Works | Estimated expert days for orientation | Anticipated deadline / place / person responsible |
| --- | --- | --- |
| Phase 1 – Preparatory Stage | ## Team Leader – 5 ## Solution Architect – 10 ## Business Analyst – 20 ## UnityBase Developer – 5 | 7 weeks from the contract signing / remote performance of the tasks / Team Lead |
| Phase 2 – Modernization of the UISC of Ukrtransbezpeka | ## Team Leader – 10 ## Solution Architect – 20 ## Business Analyst – 50 ## UnityBase Developer – 70 ## Backend Developer – 50 ## DevOps Engineer – 20 ## QA / Test Engineer – 5 ## Security engineer – 5 | Estimated as 20 weeks from the contract signing / remote performance of the tasks / Team Lead |
| Phase 3 – Integration with the e-Permit System | ## Team Leader – 10 ## Solution Architect – 20 ## Business Analyst – 30 ## UnityBase Developer – 35 ## Backend Developer – 30 ## DevOps Engineer – 20 ## QA / Test Engineer – 5 ## Security engineer – 10 | Estimated as 35 weeks from the contract signing / remote performance of the tasks / Team Lead |
| Phase 4 – Extension of Electronic Data Exchange Protocols with the eQueue System | ## Team Leader – 5 ## Solution Architect – 10 ## Business Analyst – 10 ## UnityBase Developer – 15 ## DevOps Engineer – 15 ## QA / Test Engineer – 5 | Estimated as 26 weeks from the contract signing / remote performance of the tasks / Team Lead |
| Phase 5 – Launch of the Pilot Project with Azerbaijan | ## Team Leader – 10 ## Solution Architect – 10 ## Business Analyst – 20 ## UnityBase Developer – 20 ## Backend Developer – 15 ## DevOps Engineer – 15 ## QA / Test Engineer – 10 ## Security engineer – 5 | Estimated as 34 weeks from the contract signing / remote performance of the tasks / Team Lead |
| Phase 6 – Technical Support of the Pilot Project with Azerbaijan | ## Team Leader – 5 ## Solution Architect – 5 ## Business Analyst – 15 ## UnityBase Developer – 15 ## Backend Developer – 5 ## DevOps Engineer – 10 ## QA / Test Engineer – 5 ## Security engineer – 5 | Estimated as 52 weeks from the contract signing / remote performance of the tasks / Team Lead |
| TOTAL | ## 660 expert days |  |

# Inputs of GIZ or other actors

Ministry is expected to make the following available:

- ensuring the legal framework for implementation of the project, including signing of an intergovernmental Memorandum between Ukraine and Azerbaijan

- ensuring the meaningful participation and coordination with relevant public authorities, agencies and stakeholders involved in implementation of the project

- support in organisational and regulatory matters related to implementation of the pilot project, including international cooperation with Azerbaijan and other foreign stakeholders

- organisation of review all interim documents (including by relevant stakeholders) and validation of deliverables

Ukrtransbezpeka is expected to make the following available:

- provision of an exhaustive list of documentation relevant to all related systems and provision of access to existing relevant documentation (regulatory materials, architectural artefacts, process descriptions, previous documentation, etc)

- provision of software and hardware infrastructure required for deployment, testing, and operation of the project components

- access to existing information systems, interfaces, test environments, and technical documentation necessary for implementation of the project

- creation of a private cryptographic key and publication of the certificate (public key) for E-Permit Ukraine

- technical coordination and participation of responsible specialists during implementation, testing, and pilot operation phases

- support in testing and acceptance of developed functionality, integrations, and data exchange protocols

State Agency for Restoration and Infrastructure Development of Ukraine is expected to make the following available:

- extension and adaptation of electronic data exchange protocols with the eQueue system related to the use of digital single-use permits for international road transport operations by Ukrainian and foreign Carriers leaving the territory of Ukraine

- technical coordination regarding integration and interoperability with the eQueue system

- participation in testing and pilot operation of electronic data exchange mechanisms between systems

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, incl. VAT (if applicable).

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments:

- Instalment 1 comprising payment for Phases 1 and 2 on the basis of accepted Deliverables 1 - 3

- Instalment 2 comprising payment for Phases 3 - 5 on the basis of accepted Deliverables 4 - 6

- Final Instalment comprising payment for Phase 6 on the basis of accepted Deliverable 7

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF), submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF), etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

- Each invoice and act of acceptance shall contain the Project Number (G-012368-002), contract number.

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, and the given procurement of works upon the Contract shall not be determined free from VAT,  the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor

__________________________________

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

Not applicable.

# Outsourced processing of personal data

Not applicable.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CVs of all experts with relevant work experience, qualifications.

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English.

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English.

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provided according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.