| Development of model educational programs within the agricultural study profile | Project number/ cost centre: G-011831-009 (21.2145.7-009.00) 50%; G-011831-011 (21.2145.7-011.00) 50% |
| --- | --- |

Terms of reference

- List of abbreviations

VET	Vocational education and training

NQA	National Qualification Agency of Ukraine

BMZ	Federal German Ministry for Economic Cooperation and Development

MEPs	model educational programs

MoES	Ministry of Education and Science of Ukraine

MoEEA Ministry of Economy, Environment and Agriculture of Ukraine

NQA State Employment Centre, National Qualification Agency

SES	State employment service of Ukraine

EU	European Union

MDI	Multi-donor initiative

S4R	Vocational Education and Training in Ukraine / Skills4Recovery program of GIZ

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

ToRs	Terms of reference

WP	Working package

GIS	Geographic Information System

- Context

The ongoing war in Ukraine has led to more than six million people leaving the country. An equally large number have been internally displaced. A consequence of the mass migration is the drastic shortage of skilled labour in key sectors of economy.

Ukraine currently needs around 100,000 skilled workers and demand is growing. Based on forecasts, the country will need up to 4.5 million additional skilled workers by 2033. The problem is further compounded by the training and qualifications, which often do not match job requirements. Jobseekers are increasingly expected to have green and digital skills. This skills gap is especially evident in the key sectors of economy. Crucial to the effort is a VET system that prepares workers specifically for the job market.

In 2023 the Federal German Ministry for Economic Cooperation and Development (BMZ) assigned GIZ to develop the project “Skills4Recovery”. The EU, Poland, and Estonia have joined the Multi Donor Initiative Skills4Recovery in autumn 2024 to enhance training opportunities for young people and adults in Ukraine. Since 2025 the Danish co-financing is being integrated one-to-one into the existing outputs (content integration) and used to scale the value addition with special focus on agricultural sector and aimed on helping vulnerable groups such as women, ex-combatants, people with disabilities, IDPs for inclusive economic recovery.

The MDI’s objective is to increase the availability of qualified workforce for the Ukrainian recovery process. The provision of qualified labour in sufficient numbers is based on creating adequate educational opportunities for all people of working age – this includes initial education for young people and further education for adults. The educational system must activate different population groups, such as internally displaced persons, former combatants, returnees, and women in order to exploit the required potential.

Key outputs of the Multi Donor Initiative are:

- Institutional Strengthening of training providers

- Implementation of training programmes

- Support of transition to labour market

- Development of political and strategic concepts according to labour market needs

- Replication of best practices throughout Ukraine

Key partners of the MDI Skills4Recovery are the Ministry of Education and Science (MoES), the Ministry of Economy, Environment and Agriculture of Ukraine (MoEEA), State Employment Centre, National Qualification Agency (NQA), regional state/military administrations, VET schools and VET training providers, employment organizations.

While Ukraine is undergoing a large-scale transformation of its education system and labour market caused by the consequences of the war, economic challenges, demographic changes, and the need for post-war recovery. One of the key sectors of the economy requiring modernization of its human resource capacity is the agricultural sector.

The modern agro-industrial complex of Ukraine is characterized by the active implementation of digital technologies, production automation, elements of precision agriculture, environmentally sustainable practices, and innovative solutions in the field of agricultural production. At the same time, the system of vocational and specialized secondary education requires updating the content of education in accordance with current labour market needs, European approaches to vocational education, and the requirements of the State Standard for Specialized Secondary Education.

The agricultural study profile has one of the largest numbers of students enrolled. Specifically, 25,568 learners are enrolled in vocational and professional pre-higher education programs. Therefore, within the framework of the reform of specialized secondary education being implemented in Ukraine from 2027, the development of model educational programs (hereinafter — MEPs) with a vocational focus specifically for this profile is highly relevant.

MEPs will ensure:

- the development of key and professional competencies;

- practice-oriented learning;

- the integration of digital and green skills;

- students’ career guidance and vocational orientation;

- bringing the educational process closer to the real conditions of modern agricultural production.

# The development of the MEPs is carried out in accordance with:

- the Laws of Ukraine “On Education,” “On Complete General Secondary Education,” “On Vocational Education,” and “On Professional Pre-Higher Education”;

- the State Standard for Specialized Secondary Education;

- typical educational program for Specialized Secondary Education;

- modern European approaches to competency-based learning;

- the principles of sustainable development and the digital transformation of education.

Skills4Recovery was requested by the Ministry of Education and Science of Ukraine to provide support in development of model educational programs (MEPs) for specialized upper secondary education with a vocational focus in the agricultural study profile for vocational education institutions and professional pre-higher education institutions.

Therefore, the aim of the contract is developing model educational programs for the agricultural profile. The process of revision and adjustment or designing of new curricula should be done by experts in relevant educational fields (secondary education school practitioner level) and experts on professional education, in close cooperation with the MoES and in compliance with the State Standard. Prepared curricula should be approved or recognized by MoES and recommended for consideration among relevant VET institutions. After a new or adjusted curricula has been approved, the Contractor should develop training materials that would help VET school teachers in implementation of an updated curricula into their daily teaching practices.

- Tasks to be performed by the contractor

# The contractor shall ensure the implementation of a comprehensive set of tasks for the development of 11 model educational programs within the agricultural study profile across 8 educational fields in accordance with the professional standard: language and literature, mathematics, natural sciences (biology, geography, chemistry, physics, astronomy), technology, arts, informatics, social and health education, and civic and historical education.

  - Tasks

The Contractor is responsible for providing the following work:

Working package 1 – Organizational and preparatory stage

Assess the expectations of the Ministerial partners and the gaps in educational programs within the agricultural study profile.

To assess the expectations and requirement of the MoES, the Contractor should take part in at least two meetings with the MoES on the topic of newly developed State Standard of professional education.

As a result of proper performance of the working package, the Contractor must submit a report containing a description of the assessment performed, and a conclusion on the future MEP concept, and the composition of the working groups from secondary education school and VET school level practitioners.

More detailed requirements for the report and the list of study directions recommended for further work are described below in WP 2 of this ToR.

Short Summary of the first Work package:

- Assessment of the expectations of the Ministerial partners and the gaps educational programs within the agricultural study profile

- formation of the expert group;

- preparation of the MEP concept

Working package 2 – Development stage

The contractor shall develop model educational programs for the agricultural profile.

Development of 11 model educational programs:

- Integrated language and literature course (Ukrainian language and literature, foreign literature) – 385 hours;

- Foreign language for professional purposes – 210 hours;

- Integrated course (algebra, geometry) – 210 hours;

- Integrated course (physics and astronomy components) – 168 hours;

- Chemistry – 84 hours;

- Biology – 84 hours;

- Geography – 63 hours;

- Integrated course (technology and arts educational fields) – 70 hours;

- Informatics – 84 hours;

- Integrated course of social and health education – 70 hours;

- Integrated course of history and civic education – 245 hours.

Educational Fields under the State Standard for Specialized Secondary Education:

1. Language and Literature Education Field (2 components)

2. Mathematics Education Field

3. Science Education Field (4 components)

4. Technology Education Field

5. Information Technology (ICT) Education Field

6. Social and Health Education Field

7. Civic and Historical Education Field

8. Arts Education Field

Indicative study directions:

- agrotechnologies;

- agroengineering;

- animal husbandry;

- poultry farming;

- aquaculture and fish farming;

- forestry;

- agricultural product processing;

- agricultural drone operator;

- precision agriculture;

- agricultural mechanization;

- repair and maintenance of agricultural machinery;

- agrologistics;

- greenhouse technologies;

- agroecology;

- landscape design;

- smart farming;

- GIS technologies in the agricultural sector.

The contractor assembles working groups and conducts meetings and necessary online communication among group members to develop model educational programs for the agricultural profile for specialized upper secondary education.

The Contractor must create one working group for each study field for creation or revision of MEPs. The working groups should:

  - Each include at least one expert in relevant educational field (secondary education school practitioner level) and at least one expert on professional education (VET school practitioner level), the detailed requirements for experts are stated in the paragraph 4. Personnel concept (proposed staff);

  - While developing MEPs the contractor shall use:

  - competency-based approach;

  - activity-based approach;

  - project- problem learning;

  - learner-centred approach;

  - integrated approach;

  - principles of lifelong learning;

  - work-based learning;

  - student-centred learning.

  - Special attention should be paid to:

  - the development of digital competencies;

  - the formation of green skills;

  - inclusivity;

  - gender equality;

  - psychosocial support for students;

  - adaptation to labour market needs.

At the beginning of the creation or revision process, the Contractor initiates one meeting of each of the mentioned working groups for each curriculum. The contractor will take over the organization of the working group meetings, the moderation, the methodological guidance and the documentation of results.

In the process of the creation or revision of MEPs, the groups should consider the incorporation of green and digital transition components into MEPs.

The aim of working groups will be to:

  - develop model educational programs for the agricultural profile according to the following indicative study directions:

- agrotechnologies;

- agroengineering;

- animal husbandry;

- poultry farming;

- aquaculture and fish farming;

- forestry;

- agricultural product processing;

- agricultural drone operator;

- precision agriculture;

- agricultural mechanization;

- repair and maintenance of agricultural machinery;

- agrologistics;

- greenhouse technologies;

- agroecology;

- landscape design;

- smart farming;

- GIS technologies in the agricultural sector.

Short Summary of second Work Package:

  - To set up Working Groups including at least one expert in relevant educational field (secondary education school practitioner level) and one expert on professional education (VET school practitioner level);

  - To develop model educational programs for the agricultural profile.

Working package 3 – evaluation, refinement of MEPs and development of educational materials

Evaluation and refinement of MEPs and development of educational materials for teachers. Once MEPs have been developed the Contractor can move to the final phase of current project – its evaluation by the Ministerial partners, refinement of MEPs and preparation of educational materials for teachers.

The evaluation of results will be carried out based on the following criteria:

•	compliance with the State Standard;

•	practical orientation;

•	integration of green & digital skills.

Short Summary of third Work Package

- Evaluation and refinement of MEPs and final approval from Ministerial partners

- Preparation of educational materials for teachers

Overall,

- the contractor is responsible for selecting, preparing, training and steering the short and long-term experts assigned to perform the development of MEPs

- the contractor provides equipment and supplies (consumables) for services provision and assumes the associated operating and administrative costs which occur during the service provision.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| WP# | Milestones/partial works | Anticipated deadline / place / person responsible | Criteria for acceptance |
| --- | --- | --- | --- |
| WP 1 | Assess the expectations of the Ministerial partners and the gaps educational programs within the agricultural study profile and preparation of the MEP concept | One month after contract start/remote/Contractor | Report on the assessment of expectations of the Ministerial partners |
| WP 2 | Identification of Working Group Members and Set-up of Groups | By the end of the 4th month after the Contract start date/remote/Contractor | List of Working Group participants per model educational program (PDF) |
|  | Development of 11 model educational programs within the agricultural study profile across 8 educational fields |  | Developed draft MEPs |
|  | Approval of Ministerial Partners |  | Feedback incoprorated into each of drafts of 11 model educational programs |
| WP 3 | Evaluation and refinement of MEPs | By the end of 6 months after contract start/remote/Contractor | Finalized versions of MEPs |
|  | Preparation of educational materials for teachers |  | An interactive guiding handbook |

During the implementation of the work, the contractor shall ensure:

- academic integrity;

- inclusivity and gender sensitivity;

- transparency of processes;

- compliance with personal data protection requirements;

- alignment with the policies of the Ministry of Education and Science of Ukraine and international partners;

- regular communication with the Ministry of Education and Science of Ukraine;

- participation in working meetings;

- incorporation of changes in accordance with the recommendations of the client and the expert group.

Period of assignment is till 31.12.2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| WP # | Reporting / Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| WP 1 | Result of assessment of the expectations of the Ministerial partners and the gaps in MEPs within the agricultural study profile - formation of the expert group; - preparation of the MEP concept | Report (in PDF format) up to 10 pages | One month after contract start |
| WP2 | Identification of Working Group Members and Set-up of Groups | List of Working Group members per model educational program (PDF) up to 3 pages | By the end of the 4th month after the Contract start date |
|  | Development of 11 model educational programs within the agricultural study profile across 8 educational fields | in PDF format. Number of pages for each of 11 models will be defined by contractor upon development |  |
|  | Feedback Provision of Ministerial Partners | email with approval of each MEP |  |
| WP3 | Preparation of material for teacher: the final version of an interactive guiding handbook | in PDF format. Number of pages for each of 11 models will be defined by contractor upon development and approval | By the end of 6th month after contract start |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

The tenderer is required to describe its backstopping concept. The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

- Process-oriented steering for implementation of the commission

- Securing the administrative conclusion of the project

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

If the Contractor provides fewer experts than the number of positions described, the experts will be assessed for all requirements and qualifications for all positions they are intended to cover.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Key Expert – Team leader

Tasks of the Team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

- Communication and negotiations with key stakeholders

Qualifications of the team leader

- Education/training (2.1.1): university degree (Master or equivalent) in Management and administration, Education/Pedagogy or related field

- Language (2.1.2): B2-level language proficiency in English

- General professional experience (2.1.3): 10 years of professional experience in the education sector

- Specific professional experience (2.1.4): 8 years of professional experience in Vocational Education and Training

- Leadership/management experience (2.1.5): 5 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 5 years of professional experience in Vocational Education and Training in Ukraine

- Development cooperation (DC) experience (2.1.7): 3 years of experience in DC related to education sector

- Other (2.1.8): 2 years of experience in managing of projects (activities) related to drafting of adjusting of curricula

## Key Expert – Expert in the agricultural study profile

Tasks of the expert

- Organization of working groups on development of model educational programs within the agricultural study profile

- Quality control of the results of work of the short-term expert pool

- Preparation of educational materials for revision within the working groups

- Overall responsibility for agricultural components in model educational programs

Qualifications of the expert

- Education/training (2.2.1): university degree (Master or equivalent) in Agricultural Sciences and Food or related field

- Language (2.2.2): B2-level language proficiency in English

- General professional experience (2.2.3): 10 years of professional experience in the education sector

- Specific professional experience (2.2.4): 8 years of professional experience in Vocational Education and Training

- Regional experience (2.2.6): 5 years of professional experience in Vocational Education and Training in Ukraine

- Development cooperation (DC) experience (2.2.7): 2 years of experience in DC related to education sector

## Key Expert – Expert in educational product development

Tasks of the expert

- Organization of working groups on development of model educational programs within the agricultural study profile

- Quality control of the results of work of the short-term expert pool

- Preparation of educational materials for revision within the working groups

- Overall responsibility for educational product components in model educational programs

Qualifications of the team leader

- Education/training (2.3.1): university degree (Master or equivalent) in Education/Pedagogy or Administration or related field

- Language (2.3.2): B2-level language proficiency in English

- General professional experience (2.3.3): 10 years of professional experience in design of educational materials

- Specific professional experience (2.3.4): 5 years of professional experience in the public education sector

- Regional experience (2.3.6): 5 years of professional experience in Vocational Education and Training in Ukraine

- Development cooperation (DC) experience (2.3.7): 2 years of experience in DC related to education sector

## Key Expert – Expert in design of educational materials

Tasks of the expert

- Ensuring quality of educational materials prepared by the working groups

- design of educational materials

- Overall responsibility for the design of model educational programs

Qualifications of the expert

- Education/training (2.4.1): university degree (Master or equivalent) in Education/Pedagogy, Audio-visual techniques and media production, Inter-disciplinary programmes and qualifications involving Information and Communication Technologies or related sphere

- Language (2.4.2): B2-level language proficiency in English

- General professional experience (2.4.3): 10 years of professional experience in design of educational materials

- Specific professional experience (2.4.4): 5 years of professional experience in the public education sector

- Regional experience (2.4.6): 5 years of professional experience in Vocational Education and Training in Ukraine

- Development cooperation (DC) experience (2.4.7): 2 years of experience in DC related to education sector

## Short-term non-key expert pool with minimum 22, maximum 33 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated.

Tasks of the expert pool

- Development of 11 model educational programs mentioned in 2.1

- Conduction and methodological guidance of working group meetings

- Communication with the stakeholders including sectoral specialists involved into VET sector on technical issues

- Negotiations with key stakeholders on approval matters along with or under supervision of the team leader

- Any other actions required for appropriate performance of the tasks (requirements) described in Chapter 2 in agreement with the team leader

Qualifications of the short-term expert pool

- Education/training (2.6.1): all experts with university qualification (at least Bachelor) in relevant field (pedagogical education or education in a field that corresponds to a MEP being developed)

- Language (2.6.2): all experts with C1 proficiency level in Ukrainian

- General professional experience (2.6.3): all experts with 5 years of professional experience in the education sphere including public or private sector

- Specific professional experience (2.6.4):

- 11 experts with 3 years of professional experience in professional education (5 points);

- 11 experts with 3 years of professional experience in teaching disciplines (subjects) relevant to the tasks (5 points).

- Regional experience (2.6.5): all experts with 5 years of professional experience in education in Ukraine

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference, the following travel regulations and reporting documents are to be observed. See Annex 1 to these Terms of Reference.

Specification of inputs

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your services at a lump sum price.

| WP# | Milestones/partial works | Estimated expert days for orientation | Anticipated deadline / person responsible |
| --- | --- | --- | --- |
| WP1 | Assessment of expectations of the Ministerial partners and the gaps educational programs within the agricultural study profile. preparation of the MEP concept | 20 (Which includes 20 expert days for team leader work and key experts) | 1 month after contract signing / Contractor |
| WP2 | Development of model educational programs for the agricultural profile | 180 (Which includes around 81 expert days for work of team leader and key experts and around 99 expert days for pool of experts) | By the end of the 4th month after the Contract signing date / Contractor |
| WP3 | Evaluation, refinement of MEPs and development of educational materials | 80 (Which includes around 14 expert days for work of team leader and key experts and 66 expert days for pool of experts) | By the end of the 6th month after the Contract signing date / Contractor |

# Inputs of GIZ or other actors

GIZ and/or other actors are expected to make the following available:

- Support in communication with representatives of MoES and partner VET schools

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, including. VAT (if applicable).

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance after completion of each work package in the agreed instalments:

- 1 Interim payment

- 2 Interim payment

- Final payment;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works, on the ground of original invoices, acts of acceptance, service entry sheet (LERF) within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment. Originals of Invoices, acts of acceptance etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance and service entry sheet (LERF), etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

- Each invoice and act of acceptance shall contain the Project Number, contract number and the percentage for cost split as follows (if applicable):

- Indicate project number and %: G-011831-009 (50%)

- Indicate project number and %: G-011831-011 (50%)

- By submitting the Invoice, the Contractor should indicate (in the invoice or in the e-mail) whether the Contractor is a payer of the Single Tax (e.g. 5%, 2%) or a VAT Payer (20%);

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH   published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, and the given procurement of services/ works upon the Contract shall not be determined free from VAT,  the cost of the Contract remains unchanged and is to be considered with VAT. The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _____________________.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

Not applicable.

# Outsourced processing of personal data

The Contractor confirms its acceptance of personal data processing in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and Law of Ukraine “About personal data protection” № 2297-VI dd. 01.06.2010.

The Contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including regional and local laws. The Contractor must process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GDPR’s data transfer rules must be considered whenever personal data leaves the EU for a third country. The Contractor shall comply with obligations under the applicable data protection legislation and general data privacy standards. This includes the informing the participants about the purposes of the data processing and obtaining their respective consent. The GIZ is NOT in any way responsible for such processing.

# Intellectual Property Rights

All intellectual property rights to the results produced under this Contract, including but not limited to the visual identity concept, logo design, colour palette, typography, user interface elements, design system, brand book, graphic files for communication materials, and other related outputs developed within the Skills4Recovery project, shall belong to the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

The Contractor assigns to the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and to the German Federal Ministry for Economic Cooperation and Development (BMZ), free of charge, a non-exclusive and unlimited right of use for all materials and works created under this Contract.

This right of use includes the right to reproduce, distribute, publish, modify, store and communicate the works to the public, in whole or in part, including by means of electronic data processing and electronic dissemination in multimedia form, including publication on websites and digital platforms of GIZ and BMZ.

The Contractor guarantees that the works created under this Contract are original and that no rights of third parties’ conflict with the transfer of the rights of use.

The assignment of these rights does not require a separate agreement and becomes effective upon acceptance of the deliverables under this Contract.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- tentative work plan;

- personnel (team) concept

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 3 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long, detailed experience stated in the Chapter 4. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Should be provided according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.