| Supervision on implementation works of construction grant agreement | Project number/ cost centre: G-011989-016 |
| --- | --- |

Terms of reference

- List of abbreviations:

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

- Context

The EU4ClimateResilience project, jointly co-financed by the European Union and the German Federal Ministry for the Environment, Climate Action, Nature Conservation and Nuclear Safety (BMUKN), aims to support Armenia, Azerbaijan, Georgia, the Republic of Moldova, and Ukraine in addressing the challenges posed by climate change. These countries, highly vulnerable to the adverse effects of climate change, face increasingly severe weather events, including heat waves, droughts, forest fires, heavy precipitation, and flooding, which threaten to exacerbate disaster risks, public health concerns, and economic losses. In response, the EaP countries are committed to reducing their carbon footprint and aligning with the European Union’s climate policies, while simultaneously building national capacities to implement the Paris Agreement.

To achieve these goals, the EU4ClimateResilience project focuses on supporting the green transition, enhancing decarbonization efforts, improving energy security, and boosting resilience to climate change impacts. The project’s specific objectives are as follows:

•Increase countries’ capacities to adequately measure and reduce national emissions and adapt to the impact of climate change and advance the implementation of the climate policy framework.

•Demonstrate the benefits of climate adaptation through specific projects.

•Support the establishment of credible regulatory frameworks on green finance in line with EU norms and to support the diversification and scaling-up of bond issuance.

As a part of Outcome 2 Benefits of climate adaptation demonstrated through specific projects, where 2 demonstration projects including on healthy ecosystems and biodiversity, established showing the benefits of climate adaptation will be implemented in two Ukrainian cities – Novovolynsk and Chernivtsi.

- Tasks to be performed by the contractor

Project is on the planning stage of 2 construction grants implementation:

- first with Executive Committee of the Novovolynsk City Council regarding eco-modernizing the Shakhtar Sports and Recreation Complex (SRC) in Novovolynsk City Territorial Community by implementing nature-based climate adaptation solutions, energy efficiency measures, and renewable energy generation.

- second with Department of Infrastructure and Landscaping of the Chernivtsi City Council regarding arrangement of public space of the territory of the monument of garden and park art of the «Zhovtnevuy» park, including measures on adaptation to the consequences of climate in the spheres of preservation of the natural reserve fund.

Both partners are responsible for the required design works and implementing of construction works by a certified Ukraine construction company.

For checking of compliance with requirement of construction grant agreements and fulfil internal quality regulations and standards of Project is required independent supervision consulter with strong technical background to provide quality and quantity control on construction sites during implementation and finish stages. Consulter needs to provide independent and unexpected site inspections. Consulted is acting as a third party with high level of technical experience in execution of construction works and relevant certificates for the supervision of construction work.

  - Tasks

The contractor is responsible for providing the following services:

- Technical suggestions for the project in general during the stage of implementation, what includes as well possible improvements of project to reach the overall aim of planned project based on provided by GIZ project technical information.

- 1 regular visit on each site per month on unexpected base.

- Participation in working group meetings with the Novovolynsk City Council and the Chernivtsi City Council

- Review technical terms of reference and technical design documentation (for Chernivtsi)

- Ensure alignment of planned construction works with the Ukrainian legislation.

- Assessment of performed works on each site in focus of quality accuracies and according to the contracted scope of works, what is including checking of used materials and equipment.

- Random check of the amount of work carried out, based on the last act of accepted works/invoice, weekly meeting minutes as well and compare with contracted quantities.

- Control of the additional work required by the contractor and changes to design and provided alternative construction materials.

- Reviewing construction site documentation, especially for areas of hidden installation work.

- Review of occupational safety measures on the construction site.

- Coordination meetings with the GIZ project.

- Narrative report of site inspections in Ukraine/English language in combination with photo report and findings and suggestions of improvement, if any.

- The consultant provides equipment and supplies (consumables) and assumes the associated operating and administrative costs.

- The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ. (The contractor reports regularly to GIZ in accordance with the current AVB of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

In addition to the reports required by GIZ in accordance with the AVB, the contractor submits the following reports:

- Brief quarterly reports on the implementation status of the project (not more than 10 pages with photo per site).

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| 1st round of site visits (2 sites) | 30.08.2026 |
| 2nd round of site visits (2 sites) | 30.09.2026 |
| 3rd round of site visits (2 sites) | 30.10.2026 |
| 4th round of site visits (2 sites) | 30.11.2026 |
| 5th round of site visits (2 sites) | 30.12.2026 |
| 6th round of site visits (2 sites) | 30.01.2027 |
| 7th round of site visits (2 sites) | 28.02.2027 |
| 8th round of site visits (2 sites) | 30.03.2027 |
| 9th round of site visits (2 sites) | 30.04.2027 |
| 10th round of site visits (2 sites) | 30.05.2027 |
| 11th round of site visits (2 sites) | 30.06.2027 |
| 12th round of site visits (2 sites) | 30.07.2027 |
| 13th round of site visit (1 site) | 30.08.2027 |
| 14th round of site visit (1 site) | 30.09.2027 |
| 15th round of site visit (1 site) | 15.10.2027 |

Period of assignment is from 25.08.2026 till 31.10.2027.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Report on 1st round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.09.2026 |
| Report on 2nd round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.10.2026 |
| Report on 3rd round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.11.2026 |
| Report on 4th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.12.2026 |
| Report on 5th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.01.2027 |
| Report on 6th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.02.2027 |
| Report on 7th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.03.2027 |
| Report on 8th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.04.2027 |
| Report on 9th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.05.2027 |
| Report on 10th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.06.2027 |
| Report on 11th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.07.2027 |
| Report on 12th round of site visits (2 sites) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.08.2027 |
| Report on 13th round of site visit (1 site) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.09.2027 |
| Report on 14th round of site visit (1 site) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 10.10.2027 |
| Report on 15th round of site visit (1 site) | Pdf file up to 50 pages A4 (UA/ENG), photo up to 500 per visit (jpeg) | 25.10.2027 |

- Concept (technical-methodological design) - Not Applicable

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The Contractor shall assign a team consisting of 2 technical experts, team with only 1 expert will be not accepted

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Key experts 1-2

Tasks of key experts 1-2

- Key experts 1-2 are responsible for the tasks described in Article 2.1, including participation in the analysis and summary of the experience of implementing modern solutions in the technical documentation as well as supervision on sites during performance of construction measures, including quality and quantity check of provided works and regular reporting in accordance with deadlines. They will be responsible for the oversight of the construction works implemented in Novovolynsk and Chernivtsi and be flexible with work for both location (replace each other in all relevant questions).

Qualifications of key experts 1-2

- Language (2.1.2 – 2.2.2): A2-level language proficiency in English Language (3 out of 10 points), C2-level (native) language proficiency in Ukrainian Language (7 out of 10 points)

- General professional experience (2.1.3 – 2.2.3): 8 years of professional experience in the design works and supervision of works construction on sites sector

- Specific professional experience (2.1.4 – 2.2.4): 2 years in energy efficiency measures, renewable energy generation and/or urban planning

- Other (2.1.9 – 2.2.9): Qualified expert in project design and supervision: design-engineer/architect and supervision of construction works (based on provided certificates).

In addition to their specialist qualifications, the following qualifications are required of team members:

•	Team skills

•	Initiative

•	Communication skills

•	Socio-cultural skills

•	Efficient, partner- and client-focused working methods

•	Interdisciplinary thinking

Due to the necessary activities to be carried out in parallel, it is necessary to maintain enough staff (Technical experts) that can also compensate for vacation times and sick leave. The replaced technical experts must have qualifications not lower than those specified in the requirements below. The replacement can be done only with GIZ approval via signing of Supplement to the Contract.

# Costing requirements

The contractor shall submit with each invoice an overview of the activities carried out with details of the person worked on, the project identification with an interval of 0.5 working days on the time sheets (minimal unit of measure for working days in time sheet - 0,5 day, not less).

Costs for transport will be reimbursed on evidence documents base and volume defined by the project - Project will provide Contractor locations for visits and dates for such visits.

The company can reimburse based on this budget line all necessary transport activities to fulfil the described tasks (on evidence). All kind of transports are accepted by GIZ on standard configuration (according to GIZ rules and procedures). For transportation by train (evidence by tickets) is using Second Class, for night trains – 4 bed compartments. Transport by company or private cars needs evidence by internet-based calculation of route planner like Google-map or similar (ride report) (reimbursement will be done based on fixed rate 0.3 EUR per 1 km which includes all expenses without exception, such as fuel, etc. in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date of trip).

The Contractor shall use the shortest possible route.

Due to far distances between sites GIZ also taking over costs for accommodation. Rate per night is setting up to 1500 UAH against evidence. For accommodation during business trips room category not higher than Standard (or equal) is to be booked.

Cost for phone calls, internet and IT equipment as well as consumable goods are included to expert’s day rate.

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations and reporting documents are to be observed. See Annex 1 to these Terms of Reference.

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of TL/ expert pool | man-day | 2 | 81 | not more than 3 man-days per 1 site per month |
| Transport | Unit of measurement | Quantity | Amount, UAH | Comments (if any) |
| Fixed travel budget | Travel cost |  | 200.000,00 | A budget is earmarked for travel to the following countries: Ukraine. A fixed budget of UAH 200.000 is earmarked for settling travel expenses against evidence/performance. This amount includes accommodation, per diems, travel costs (train, compensation for own transport with fixed rate 0.3 EUR per 1 km, taxi, bus)., Accommodation, train tickets, taxi, bus – are to be reimbursed against evidence, for per-diem, own transport – reimbursement is to be done against performance. Settlement is possible only until the budget is depleted. |
| Travel expenses | Unit of measurement | Quantity | Amount, UAH | Comments (if any) |
| Overnight allowance in country of assignment | night | Up to 27 nights with amount UAH up to 1500 |  | The budget contains the following costs Ukraine. A fixed budget of UAH 40.500,00 is earmarked for settling Overnight allowance expenses against evidence, in frames of GIZ limits and based on Invoice from Hotel, containing information on type of room number, nights of stay, possible meal and guest name. Settlement is possible only until the budget is depleted. |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors - Not Applicable

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, but excl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance on quarterly basis;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF) and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

- Each invoice and act of acceptance shall contain the Project Number, contract number

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

The given procurement of services/ works upon the Contract shall be carried out at the funds of the funds of the Project of International Technical Assistance (Project ITA), PN: G-011989-016/ 2021.9025.4, Project title “Promoting Green Deal Readiness in Eastern Partnership Countries (PROGRESS / EU4ClimateResilience)”, registered by the Secretariat of the Cabinet of Ministers of Ukraine (registration card of the project (program) No. 6213  dated 30.09.2025) and complies with the category (type) of Services specified in the purchase plan available at address https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel

The above-mentioned ITA project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008.

The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, then the Contractor must notify GIZ of such VAT registration in writing or in electronic form by means of submission of an e-mail with copy of the Excerpt from VAT Registration Registry to the GIZ’s e-mail address indicated in the details of the Contract. The Contractor must submit the mentioned notification to the GIZ not later than 1 calendar day following the day of VAT registration.

At the same time the Parties agreed that the purchase of Services after the VAT registration of the Contractor shall be exempt from VAT in accordance with the abovementioned.

# Outsourced processing of personal data - Not Applicable

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 10 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English/Ukrainian (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Option – Not Applicable

- Annexes