| Development of a Feasibility Study and Detailed Design Documentation (Stage DS) for the Technical Re-equipment of the existing boiler house with a 5 MW solid fuel boiler on biomass and RDF, Cherkasy, 8 Onoprienka Street. | Project number/ cost centre: G-010965-001 |
| --- | --- |

# Terms of reference

# List of abbreviations

| Abbreviation | Definition |
| --- | --- |
| AG | Auftraggeber / Commissioning party (GIZ) |
| AN | Auftragnehmer / Contractor |
| AVB | Allgemeine Vertragsbedingungen / General Terms and Conditions of Contract (GIZ Ukraine) |
| BoQ | Bill of Quantities |
| BIM | Building Information Modelling |
| CAPEX | Capital Expenditures |
| CO₂ | Carbon Dioxide |
| DBN | Державні будівельні норми України / State Building Codes of Ukraine |
| DOCX | Microsoft Word Document Format |
| DS | Design Stage (“Робоча документація”) |
| DWG | Drawing File Format (AutoCAD) |
| EBRD | European Bank for Reconstruction and Development |
| EUR | Euro |
| FS | Feasibility Study (“ТЕО”) |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH |
| HVAC | Heating, Ventilation and Air Conditioning |
| IEC | International Electrotechnical Commission |
| IFC | Industry Foundation Classes (open BIM standard) |
| IRR | Internal Rate of Return |
| ISO | International Organization for Standardization |
| kVA | Kilovolt-Ampere |
| MW | Megawatt |
| NEFCO | Nordic Environment Finance Corporation |
| NPV | Net Present Value |
| O&M | Operation and Maintenance |
| OPEX | Operational Expenditures |
| PDF | Portable Document Format |
| SCADA | Supervisory Control and Data Acquisition |
| TOR / ToR | Terms of Reference |
| UAH | Ukrainian Hryvnia |
| VAT | Value-Added Tax |

# Context

The Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH implements the project “Reforming the District Heating Sector of Ukraine” (ReWarm). The project supports the sustainable transformation of Ukraine’s district heating sector by contributing to the development of the national district heating framework, strengthening municipal energy planning, supporting municipal district heating utilities, and facilitating the preparation and implementation of technically, economically and environmentally viable modernisation measures.

ReWarm promotes improvements in energy efficiency, reduction of greenhouse gas emissions, diversification of energy sources, increased use of renewable and locally available fuels, and greater resilience of municipal heat supply systems. The project also supports Ukrainian municipalities and district heating utilities in developing practical investment measures that can contribute to the climate-friendly reconstruction and long-term modernisation of the heating sector.

Within the framework of ReWarm, GIZ is supporting the City of Cherkasy and the municipal district heating utility, Communal Enterprise of Heat Networks “Cherkasyteplokomunenergo”, in preparing priority measures for the modernisation and decarbonisation of the city’s district heating system.

Cherkasyteplokomunenergo operates a city-wide district heating system supplying heat to residential, public and commercial buildings. The utility manages a portfolio of boiler houses, most of which are gas-fired and were commissioned several decades ago. The system’s dependence on natural gas, exposure to fuel price volatility and supply risks, ageing infrastructure, and greenhouse gas emissions create significant technical, economic and environmental challenges for its long-term operation.

The subject facility is the gas-fired boiler house located at 8 Onoprienka Street, Cherkasy, commissioned in 1973. It currently has an installed thermal capacity of 24.86 MW and is equipped with three hot-water boilers — LOOS UT-M 54, VK-21 and TVG-8M — with an efficiency of approximately 95%, as well as a Caterpillar G3512E cogeneration unit. The connected peak heat load is approximately 10.57 MW, while the average annual heat load is approximately 4.8 MW. Annual natural gas consumption in 2022–2024 amounted to approximately 2.27–2.31 million m³. The existing district heating system operates with a temperature schedule of 95/70 °C and a system pressure of 6 bar.

The boiler house requires modernisation to improve energy security, diversify the fuel mix, reduce dependence on natural gas and decrease greenhouse gas emissions while maintaining reliable and affordable heat supply for consumers.

The proposed investment initially foresees the installation of a new 5 MW solid-fuel boiler designed to operate primarily on locally available biomass, including wood chips and crushed corn cobs, with a permissible fuel moisture content of up to 40%. The final technical configuration shall be confirmed through the Feasibility Study based on heat demand analysis, fuel availability, lifecycle costs, environmental impacts and operational requirements.

The anticipated modernisation measures may include:

– installation of a 5 MW solid-fuel boiler and associated auxiliary equipment;

– construction or adaptation of a covered fuel storage facility;

– installation of automated fuel receiving, handling, dosing and feeding systems;

– modernisation of circulation pumps and installation of variable-frequency drives;

– adaptation of the existing water-treatment system;

– installation of an appropriate flue-gas cleaning system and continuous emissions monitoring equipment;

– construction of a new chimney, where technically required;

– integration of automation and SCADA systems;

– adaptation of electrical supply, ventilation, fire safety and occupational health and safety systems; and

– implementation of the required civil and structural works.

The assignment shall also assess technically and economically reasonable alternatives, including different fuel and operating configurations, integration of heat pumps, use of thermal energy storage, opportunities for bioenergy cogeneration, reduction of district heating network temperatures, and utilisation of available waste heat.

The present assignment is implemented as part of the ReWarm project and constitutes an investment-preparation measure for the modernisation of Cherkasy’s district heating infrastructure. The Contractor shall prepare a Feasibility Study evaluating technically, economically and environmentally viable options and, following approval of the preferred option, develop Detailed Design Documentation (Stage “DS”) for its implementation.

The Feasibility Study shall quantify expected fuel substitution, energy savings, greenhouse gas emission reductions, capital and operating expenditures, lifecycle costs and financial performance. The Detailed Design Documentation shall cover the selected heat-generation technology and all related fuel supply, hydraulic, electrical, automation, emissions-control, civil, environmental and occupational safety systems.

All deliverables shall comply with applicable Ukrainian legislation and technical standards, including relevant DBN and DSTU requirements, as well as applicable international and European good practices. The design documentation shall be suitable for submission to the authorised State Expertise body and for use in subsequent procurement and investment-planning procedures.

The preparation of the Feasibility Study and Detailed Design Documentation under this assignment does not constitute a commitment by GIZ or the ReWarm project to finance the subsequent supply of equipment, construction works or implementation of the proposed investment. Potential sources and mechanisms for financing the investment shall be assessed separately on the basis of the results of the Feasibility Study.

# Tasks to be performed by the contractor

  - Tasks

The contractor is responsible for providing the following work:

The Contractor shall provide services for the development of a Feasibility Study (FS) and Detailed Design Documentation (Stage “DS”) for the reconstruction and technical re-equipment of the gas-fired boiler house at 8 Onoprienka Street, Cherkasy, through the installation of a new 5 MW solid-fuel boiler (wood chips and corn cobs).

The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ. The contractor reports regularly to GIZ in accordance with the current AVB of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

The Contractor shall ensure that all works are designed, documented, and prepared in full compliance with the current Ukrainian regulatory framework, including but not limited to:

- DBN A.2.2-3:2014 – Composition and content of project documentation for construction

- DBN V.2.5-77:2014 – Heat networks

- DBN V.2.5-39:2008 – Gas supply

- DBN V.2.5-23:2010 – Power supply

- DBN V.1.2-14:2018 – General principles of ensuring reliability and structural safety of buildings and structures

- DSTU ISO 50001:2020 – Energy management systems

- State Building Standards for Occupational Health and Safety and Fire Safety (OP, PB)

- Other applicable Ukrainian and international standards (IEC, EN).

Stage 1 – Feasibility Study (FS):

- Analysis of the current technical condition and thermal load profile; this includes a thorough heat demand analysis based on the previous years, including a 10 year forecasting on the existing consumers, their energy efficiency potential (e.g. by installation of individual heat substations, building refurbishment), the loss reduction potential in the grid and an estimate about additional heat demand from new consumers or connection to other grids as well as impact of global warming. Alternative cheaper heat supply options are evaluated, especially from industry waste heat. Modeling and comparative evaluation of at least 3 reconstruction options (fuel blends, operational modes) including one option with heat pumps, consideration of heat storage tanks and bioenergy cogeneration;

- Hydraulic and thermal calculations for the optimal solution (including analyses of changes of forward and return grid temperatures) and supply options (including cost estimates);

- Estimation of biomass fuel demand (≈ 11,700 t/year within 8–10 km supply radius);

- Estimation of natural gas substitution, CO₂ emissions reduction, CAPEX/OPEX, NPV, IRR;

- Specification of flue-gas cleaning system and stack dimensions according to BAT/EU-UA standards;

- Preparation of the FS report in line with the requirements of international financing institutions standard feasibility study structure (technical, economic, environmental and financial sections), financial model (CAPEX, OPEX, NPV, IRR, sensitivity analysis) and environmental and social safeguards.A preliminary “Environmental and Climate Safeguards Summary” for each scenario shall be integrated into the study report.

- Preparation and implementation of one multi-stakeholder workshop to present and discuss the findings of the study.

Stage 2 – Design Documentation (Stage “DS”):

- Technical specifications for dismantling obsolete equipment and preparing new foundations;

- Design and technical specifications for a 5 MW solid-fuel boiler (efficiency 85–88%, modulation 20–100%) (or the solution selected in stage 1);

- Design of a new covered fuel storage (3-day stock), conveyors, feeders, and dosing systems;

- Integration of hydraulic separation via plate heat exchanger (95/70 °C, 6 bar or the solution selected in stage 1);

- Technical specifications for new circulation pumps with frequency converters;

- Design of an automation and SCADA system (with remote monitoring and alarms);

- Design of a fuel-gas cleaning system (cyclones, bag filters, scrubbers, CEMS) and a new chimney (height and diameter per DBN);

- Electrical design (400 V integration with existing CHP), ventilation, noise protection, and occupational safety sections;

- Preparation of full design documentation for submission to state expertise.

- Preparation and implementation of one multi-stakeholder workshop to present the findings of the DS and the O&M of the selected solution with attendance lists.

- Findings and progress should be summarized in short monthly updates and two review meetings with GIZ and the utility;

- A short “Environmental and Climate Safeguards Summary” for the chosen scenario shall be integrated into the DS report.

Stage 3 – Submission to State Expertise

The contractor shall prepare and submit the complete set of design documentation to the authorized State Expertise authority (ДП «Укрдержбудекспертиза») or its regional department and provide full administrative and technical support during the registration and submission process.
This stage shall include:

- Compilation of all DS volumes, explanatory notes, drawings, cost estimates, and environmental documentation in both printed and electronic formats (XML/IMD if required by expertise rules);

- Preparation of a submission package checklist confirming completeness, proper signatures, and compliance with DBN A.2.2-3:2014 and other applicable norms;

- Coordination with the municipality and the utility for providing supplementary data (land documents, permits, letters of intent);

- Official submission of the documentation set to the expertise body and confirmation of receipt (registration letter / incoming stamp);

- Monitoring of the registration status and communication with the expertise body on any administrative or relevant technical remarks;

- Delivery to GIZ of a short submission note (max 2 pages) summarizing date of submission, content of package, and confirmation of acceptance by the expertise body.

Stage 4 – Support during Expertise and Obtaining of Positive Conclusion

The contractor shall provide technical and procedural assistance during the entire expertise review until the receipt of a positive expert report.

This stage shall include:

- Liaison with the State Expertise authority: coordination of clarifications, responses, and supplementary documents requested during review;

- Technical justifications and corrections: preparation of updated drawings, calculations, or cost tables to address reviewers’ comments, ensuring that all responses remain consistent with the approved design concept;

- Consultation with the utility and municipality to approve any proposed technical adjustments before resubmission;

- Maintenance of an issues and response log documenting each expert comment and corresponding correction;

- Submission of revised documents to the expertise authority and obtaining of the positive expertise report (official conclusion);

- Delivery to GIZ of the final expert report (PDF + scan of the signed original) and the finalized DS package reflecting all approved changes;

- Short Final Report (2–3 pages) summarizing key outcomes, recommendations for implementation, and lessons learned.

Deliverables:

- Positive expert report (scan + PDF)

- Final DS package (with implemented remarks)

- Final Summary Report (PDF + editable file)

Place of performance: Cherkasy city, 8 Onoprienka Street.
Additional technical requirements are indicated in Annex 1 – TECHNICAL SPECIFICATIONS for the development of a Feasibility Study (FS) and Design and Estimate Documentation (Stage ‘DS’) for the reconstruction of the boiler house at 8 Onoprienka Street, Cherkasy».

| Milestones/partial works | Anticipated deadline/ place/ person responsible | Criteria for acceptance |
| --- | --- | --- |
| Stage 1. Feasibility Study | Within 2 months from contract signing / Contractor | FS report delivered in PDF and DOCX; approved by GIZ; one workshop implemented with minutes, ppt and list of participants |
| Stage 2. Design Documentation | Within 2 months after FS approval / Contractor | Full DS package (incl explanatory notes) submitted to GIZ and approved by GIZ: complete set of drawings, explanatory note, technical specifications, BoQ/Cost estimate (Excel + XML/IMD), O&M outline, BIM/IFC files; one workshop implemented with minutes, ppt and list of participants |
| Stage 3. Submission to State Expertise | Within 1 month after completion of the DS package / Contractor | Package submitted to state expertise body (in hard copy and e-form); confirmation of receipt obtained. |
| Stage 4. Support during Expertise & Positive Conclusion | Within 2 months after submission to State Expertise / Contractor | Documentation formally accepted by state expertise body with positive expert review report. |

The contract duration is 7 months from contract signing. Indicatively, if the contract starts on 1 September 2026, all activities shall be completed by 31 March 2027.

2.2 Deliverables and Reporting:

The Contractor will be responsible for the following:

| # | Reporting/Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| 1 | Feasibility Study report with 3 options (technical, financial, environmental scenarios; biomass/RDF blends; flue-gas cleaning alternatives; CAPEX/OPEX, NPV, IRR) | PDF, DOCX; UA & EN; up to 40 pages incl. annexes | Within 2 months from contract signing |
| 2 | Detailed Design Documentation (Stage “DS”): complete package including drawings, explanatory note, technical specifications, O&M outline, automation & SCADA integration, environmental protection section, BIM/IFC | PDF, DWG; UA; scale 1:50; BIM/IFC files, explanatory notes in English. | Within 2 months after FS approval |
| 3 | Budget/Cost Estimate Package (BoQ) prepared for state expertise (Excel, XML/IMD; UA), including cost estimates for boiler, fuel handling, emission control, electrical and civil works | Excel, XML/IMD; UA | Together with DS |
| 4 | Final Approval and Expertise (Stage 4) – full set of documentation and evidence following the completion of the State Expertise process, including: • editable responses matrix (if comments were issued); • final positive expert conclusion issued by the State Expertise authority; • submission note (PDF); • final DS package with implemented remarks and integrated “Environmental and Climate Safeguards Summary.” | PDF; UA. | Upon receipt of final positive conclusion from the State Expertise body |

All deliverables must be provided in 4 (four) hard copies, signed and stamped by the Contractor, plus 1 (one) electronic copy on CD/DVD or USB flash drive in editable and PDF formats.

In addition to the specific tasks described under Stages 1–4, the contractor shall perform the following general activities to ensure efficient coordination, quality assurance, and transparent reporting throughout the assignment:

Coordination and communication

- Maintain regular coordination with GIZ, the municipality of Cherkasy, and the utility “Cherkasyteplokomunenergo” through online and in-person meetings as required.

- Prepare and share short meeting minutes or issues logs to document key decisions and actions agreed with project partners, primarily Cherkasyteplokomunenergo as the beneficiary utility and Cherkasy municipality

Progress monitoring and reporting

- The Contractor shall submit monthly progress reports to GIZ in English and Ukrainian. Reports may be shared with the beneficiary utility and other project stakeholders by GIZ where required.

- The Contractor shall present progress at two online review meetings with GIZ and the utility: one after FS completion and one before DS submission.

- Maintain a simple issues and decision log, updated monthly and shared with GIZ.

Quality assurance

- The Contractor shall ensure compliance with the requirements listed in this ToR and Annex 1, including applicable Ukrainian DBN/DSTU standards, IEC/EN standards where relevant, GIZ contractual requirements, and the technical specifications for the FS and DS.

- Ensure that all reports and drawings are internally verified for technical accuracy and formatting consistency.

Knowledge transfer

- Conduct two short knowledge-transfer sessions for the utility as part of Stage 1 and Stage 2 deliverables (presentation of FS findings and O&M training). The knowledge-transfer elements shall be integrated into the two workshops described under Stage 1 and Stage 2 and shall not constitute additional separate events.

- Submit attendance lists and training materials (in Ukrainian) together with the final report.

Final reporting

- After completion of all stages and receipt of the positive state expertise report, prepare a Final Summary Report (2–3 pages) summarizing:

  - achieved results and outputs;

  - lessons learned and replication recommendations;

  - any deviations from the initial plan and mitigation actions

# Concept (technical-methodological design)

## In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1)

Interpretation of the objectives in the ToR and critical examination of tasks (1.1.1)

The tenderer shall demonstrate a clear understanding of the objectives and scope of services described in this ToR, including the preparation of the Feasibility Study (FS) and Detailed Design Documentation (DS) for the reconstruction of the boiler house at 8 Onoprienka Street, Cherkasy.

The tenderer shall briefly analyse the key technical and organizational challenges, such as:
– limited space for new equipment installation,
– fuel logistics within a 50 km radius,
– ensuring compliance with DBN and environmental standards,
– coordination with the municipal utility and the state expertise body.

The interpretation shall confirm that the tenderer understands the expected outputs, milestones, and deliverables described in Chapter 2.

Description and justification of the contractor’s strategy for delivering the services (1.1.2)

The tenderer shall outline a concise, results-oriented strategy for providing the required services under this assignment, covering both stages – FS and DS.

The strategy shall focus on:
– a practical sequence of actions from data collection to expert approval;
– use of proven engineering methods and local regulatory compliance;
– efficient coordination with GIZ and Cherkasyteplokomunenergo;
– preparation of complete, consistent documentation ready for implementation.

The description shall highlight how the proposed approach ensures timely delivery, technical quality, and clear communication with all partners.

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them:

Presentation and interaction between the relevant actors (1.2.1)

The tenderer shall identify the main stakeholders involved in this assignment, including the municipality of Cherkasy, the municipal utility “Cherkasyteplokomunenergo”, grid operators (heat and electricity), and, where relevant, environmental and waste management authorities.

The tenderer shall briefly describe the roles of these actors and explain how communication and coordination will be maintained during project implementation – for example, through kick-off meetings, site visits, and regular coordination calls with GIZ and local partners.

Strategy for establishing and maintaining cooperation (1.2.2)

The tenderer shall outline a simple and practical strategy for cooperation with project partners during all stages (FS and DS), focusing on effective communication, transparency, and timely feedback.

The approach shall include:
– planning and documenting consultations with the municipality and utility;
– coordinating with grid operators and other relevant authorities when their inputs are required;
– keeping records of meetings and key decisions (minutes and short issues log) to be attached to monthly progress reports to GIZ.

The cooperation strategy shall show the tenderer’s ability to maintain close coordination with stakeholders and respond promptly to partners’ comments.

Steering and results-based monitoring (1.3)

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2):

The description shall outline how coordination with GIZ and partners will be ensured, how progress will be monitored against the agreed milestones and deliverables, and how transparency and risk management will be maintained throughout the assignment.

Operational plan (1.4)

The tenderer is required to describe the key processes for the services for which it is responsible and to create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 are to be provided.

In particular, the tenderer is required to describe the necessary work steps and, where applicable, take account of the milestones and contributions of other actors (1.4.2).
The operational plan shall show the logical sequence of the FS, DS, and State Expertise stages and demonstrate that resources will be managed efficiently and deadlines met.

Knowledge management and learning (1.5)

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ under learning and innovation.

Project management of the contractor (1.6):
The tenderer shall briefly describe its project management approach, confirming that it has the capacity, internal procedures, and qualified staff to implement the assignment efficiently, ensure coordination with GIZ and project partners, and deliver all outputs on time and with the required quality.
The description must address the following aspects in accordance with assessment criteria 1.6.1–1.6.3.

– Management and coordination structure (1.6.1)

The tenderer shall provide a clear organisational chart showing team members, reporting lines, and roles, including the Team Leader, key experts, and support staff.
The description shall specify who is responsible for day-to-day coordination, quality assurance, and communication with GIZ and the main project partners.

– Quality assurance, monitoring and reporting (1.6.2)

The tenderer shall briefly describe its internal quality assurance (QA) system and how it will ensure that all deliverables (FS, DS, and expert report) comply with Ukrainian norms and GIZ requirements.
The approach shall include regular internal checks and the submission of concise monthly progress reports summarizing activities, results, and next steps.

– Backstopping and administrative support concept (1.6.3)

The tenderer shall confirm that its organisation will provide adequate technical and administrative backstopping to the project team, ensuring timely support, quality control, and smooth coordination with GIZ.

The project management approach shall demonstrate the contractor’s ability to deliver coordinated, high-quality outputs, maintain transparency and accountability, and ensure reliable performance throughout the contract period.

Further requirements – Environmental and climate safeguards (1.7)

The tenderer is required to consider environmental and climate-related aspects during project implementation, including:
– fuel substitution and expected CO₂ reduction;
– compliance with Ukrainian and EU environmental standards;
– safe handling and disposal of dismantled equipment; and
– ensuring climate-resilient design solutions.

# Personnel concept (proposed staff)

The Contractor is required to provide personnel suited to filling the positions described, based on their CVs (see Chapter 10), the range of tasks involved, and the required qualifications.
If the Contractor provides fewer experts than the number of positions described in the ToR, the experts will be assessed for all requirements and qualifications for all positions they are intended to cover.
The qualifications below represent the requirements to achieve the maximum score in the technical assessment.

Team Leader

Tasks:

- Overall responsibility for the contractor’s advisory packages (quality and deadlines);

- Coordinating and ensuring communication with GIZ, partners, and all stakeholders involved in the project;

- Personnel management, including identifying the need for short-term assignments within the available budget, planning and steering assignments, and supporting local and international short-term experts;

- Regular reporting in accordance with deadlines, including monthly progress reports to GIZ, indicating the current stage of design, completed tasks, identified issues, and planned activities for the next month;

- Support during state expertise process, including responding to expert comments and preparing clarifications;

- Coordinate submission of documents to state expertise authorities;

- Coordination of cost estimation process and preparation of consolidated Bill of Quantities (BoQ);

- Review and approval of cost estimates from all engineering sections;

- Preparation of final cost documentation in Excel/XML/IMD format for state expertise;

- Ensure compliance with Ukrainian regulatory framework (DBN/DSTU/IEC standards).

- Coordinate the preparation and implementation of workshops, including agendas, presentation materials, minutes and participant lists.

Qualifications:

- Education/training (2.1.1): University degree Bachelor in Energy Engineering, Mechanical Engineering, Civil Engineering, or related technical field relevant to the assignment.;

- Language (2.1.2): B1 level in English (CEFR);

- General professional experience (2.1.3): 10 years in the energy infrastructure or utility sector;

- Specific professional experience (2.1.4): 8 years in technical project management related to biomass boiler houses, boiler conversions, or energy supply systems;

- Leadership/management experience (2.1.5): 5 years as team leader or project manager in infrastructure development or donor-funded projects;

- Regional experience (2.1.6): 5 years in Ukraine;

- Development cooperation (DC) experience (2.1.7): 5 years of experience in DC projects.

Key Expert 1: Heating System Design Engineer

Tasks:

- Conduct technical assessments and feasibility studies for boiler house modernization;

- Develop thermal and hydraulic calculations for the integrated system;

- Prepare technical specifications for 5 MW biomass boiler, fuel feeding, heat exchangers;

- Design boiler room layout, fuel warehouse integration, and piping schemes;

- Calculate energy savings potential and CO₂ reduction estimates;

- Preparation of detailed cost estimates for heating and mechanical equipment;

- Contribution to overall project cost estimation and BoQ preparation;

- Contribute to preparation of design documentation according to DBN/DSTU standards.

Qualifications:

- Education/training (2.2.1): University degree Bachelor in Thermal Power Engineering, Mechanical Engineering, Energy Efficiency, or related technical discipline. Valid Ukrainian professional certification/attestation in thermal power engineering or energy efficiency (required for design of heating systems in Ukraine);

- Language (2.2.2): B1 level in English (CEFR);

- General professional experience (2.2.3): 5 years in energy efficiency or utility infrastructure sector;

- Specific professional experience (2.2.4): 4 years in technical design, modernization, or audit of boiler houses (preferably solid-fuel/biomass);

- Regional experience (2.2.6): 3 years in Ukraine.

Key Expert 2: Automation and SCADA Specialist

Tasks:

- Design automation and control systems for the boiler house reconstruction;

- Develop SCADA system specifications with Modbus TCP/IP integration;

- Prepare technical specifications for variable frequency drives (VFDs), pumps, and boiler automation;

- Design automation sequences and control logic for solid-fuel boiler, conveyors, and emission control system;

- Contribute to preparation of operational manuals and commissioning procedures documentation.

Qualifications:

- Education/training (2.3.1): University degree Bachelor in Mechanical Engineering, Electromechanics, Energy Systems, or Industrial Automation. Valid Ukrainian professional certification/attestation in automation, electrical engineering, or industrial control systems;

- Language (2.3.2): B1 level in English (CEFR);

- General professional experience (2.3.3): 5 years in energy, industrial, or construction sector;

- Specific professional experience (2.3.4): 4 years in design of energy or heat supply systems (boilers, automation, switchboards, SCADA systems);

- Regional experience (2.3.6): 3 years in Ukraine.

Key Expert 3: Electrical Design Engineer

Tasks:

- Prepare electrical design documentation for boiler house reconstruction;

- Design power supply systems for new biomass boiler and auxiliary equipment;

- Develop specifications for electrical integration of VFDs, automation, SCADA and safety systems;

- Ensure electrical design compliance with DBN, DSTU, and IEC standards;

- Prepare electrical sections of bill of quantities and technical specifications;

- Support preparation of documents for state expertise (electrical sections).

Qualifications:

- Education/training (2.4.1): University degree Bachelor in Electrical Engineering or Power Systems. Valid Ukrainian professional certification/attestation in electrical engineering (required for electrical design work in Ukraine);

- Language (2.4.2): B1 level in English (CEFR);

- General professional experience (2.4.3): 5 years in the electrical engineering sector;

- Specific professional experience (2.4.4): 4 years designing electrical systems for industrial or municipal facilities;

- Regional experience (2.4.6): 3 year in Ukraine.

# Costing requirements.

Specification of inputs

The following basic calculations for the contract for works are a reference value based on the acceptance criteria for each partial work/milestone specified in Chapter 2 (Tasks to be performed by the contractor).

Since the contract to be concluded is a contract for works, we would ask you to offer your works at a lump sum price.

| Milestones/partial works | Expert | Expert days |  | Anticipated deadline/place/person responsible |  |
| --- | --- | --- | --- | --- | --- |
| Completion of the Feasibility Study (FS) | Team Leader (GIP) | 25 |  | Within 2 months from contract signing / Contractor |  |
|  | Key Expert 1: Heating System Design Engineer (TMK) | 15 |  |  |  |
|  | Key Expert 2: Automation and SCADA Specialist (ATMK) | 10 |  |  |  |
|  | Key Expert 3: Electrical Design Engineer (ETR) | 10 |  |  |  |
|  | Total | 60 |  |  |  |
| Completion of the Detailed Design (Stage “DS”) | Team Leader (GIP) | 34 |  | Within 4 months after FS approval / Contractor |  |
|  | Key Expert 1: Heating System Design Engineer (TMK) | 50 |  |  |  |
|  | Key Expert 2: Automation and SCADA Specialist (ATMK) | 30 |  |  |  |
|  | Key Expert 3: Electrical Design Engineer (ETR) | 30 |  |  |  |
|  | Total | 144 |  |  |  |
| Support during expertise process | Team Leader (GIP) | 6 |  | Within 1 month from Completion of the Detailed Design / Team Leader |  |
| Submission of documents for state expertise | Team Leader (GIP) | 1 |  | Until final decision / Contractor |  |
| Total |  |  | 211 |  |  |  |

# Note: The expert days provided are indicative estimates for orientation purposes only. The contract is based on deliverables completion regardless of actual time allocation.

# Inputs of GIZ or other actors

GIZ will provide the applicable contractual templates and instructions for technical and financial reporting, deliverable acceptance and contract administration.

Cherkasyteplokomunenergo and/or Cherkasy municipality are expected to facilitate access to the boiler house, provide available technical documentation and operational data, support coordination with local stakeholders, and review/confirm key technical inputs where required. The Contractor remains responsible for verifying the completeness and suitability of the provided data for the purposes of the FS and DS.

# Financial provisions

## 7.1 Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the bid. Payment terms will be defined in the contract and related procurement documents in accordance with GIZ procedures.

## The effort for Milestones 3–4 (submission and support during state expertise) is included in the lump-sum price and is not invoiced separately; it is covered by the Final payment tranche.

## 7.2 Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees incl. VAT (if the company is a VAT payer).

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

7.3 Payment Conditions

- The Contractor shall be paid upon acceptance of each separate Stage and   submission of the required original financial documents.

- All payments shall be made exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor.

- All activities shall be completed exclusively within the timeframe of the Contract.

- All payments shall be made exclusively for the actually performed works (“up to”), on the basis of original invoices, acts of acceptance, service entry sheet (LERF), submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ.

- The invoice shall be considered not accepted for payment in case of errors and/or provision of an incomplete package of documents required for payment.

7.4 Requirements to the submission of the financial reporting documents

- Originals of Invoices, Acts of Acceptance, service entry sheet (LERF), and other supporting financial documents shall be submitted to the address of the GIZ Project together with the technical documents (reporting/deliverables) as stipulated by the Contract.

- The Contractor shall submit monthly progress reports to GIZ, indicating the current stage of design, completed tasks, identified issues, and planned activities for the next month.

- Each invoice and act of acceptance shall contain:

  - the Project Number,

  - the Contract Number,

  - and the Number of Deliverables (according to Clause 2.2).

- By submitting the invoice, the Contractor shall indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%).

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

# Other Provisions

## 8.1 General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link  Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, and the given procurement of services/ works upon the Contract shall not be determined free from VAT, the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

## 8.2 VAT Exemption - not Applicable.

# Outsourced processing of personal data .

The performance of the contract may involve limited processing of personal data by the Contractor, such as names, positions, signatures and contact details of representatives participating in project coordination, workshops, reporting and contract administration. Such data shall be collected and processed solely to the extent necessary for performance of the Contract.

In this contract the contractor shall act as an independent DATA CONTROLLER and must alone comply with ALL applicable data protection obligations, including those stemming from regional and local laws. The contractor shall process personal data only when a given goal cannot be reasonably attained without such data. The data protection principles such as lawfulness, data minimization, accuracy, purpose limitation, storage limitation, transparency, integrity and confidentiality, and accountability, as well as the numerous rights of the data subject must be paid due attention. The GIZ is NOT in any way responsible for such processing.

Whenever the contractor executes the instructions of a partner to the GIZ with regard to such processing, the partner shall be the data controller, and the data processing shall be carried out in accordance with the partner’s instructions as well as laws and standards to which it is subject.

If the contractor is not subject to the GDPR and the applicable laws do not contain any explanation on the data protection principles and rights mentioned here, the definitions and meanings provided by the GDPR (Regulation (EU) 2016/679) should be considered.

# Requirements to the format of the bid

## 10.1 Documents to be submitted

### 10.1.1 Technical bid

The tenderer shall submit as part of the technical proposal the documents and descriptions specified in Chapter 3 “Concept (Technical-Methodological Design)”, which shall include the following key elements:

Work Plan & Schedule

- A detailed work plan for the execution of the assignment, broken down by project stages (e.g. data collection and site visits, preparation of the Feasibility Study (FS), development of Design Documentation (DS) where applicable, internal quality control, submission to state expertise, and finalization).

- The work plan shall include a Gantt chart or other suitable format indicating the timing, sequence, and interrelation of activities, as well as the allocation of resources and responsible experts.

Team Composition & Organisational Chart

- An organisational chart showing the structure of the project team, reporting lines, and relationship between the tenderer’s in-house staff and any subcontractors.

- Identification of all key experts listed in Chapter 4: Team Leader, Heating System Design Engineer, Automation and SCADA Specialist, and Electrical Design Engineer..

- A short description of each team member’s role and responsibilities, consistent with Chapter 4.

Methodology

- A concise description of the methodology and approach proposed for implementing the assignment, clearly linked to the identified tasks and milestones described in Chapter 2.

Note: In case of overlap, the level of detail in this section shall be aligned with the respective descriptions provided in Chapter 3 “Concept (Technical-Methodological Design)” to ensure consistency and avoid duplication.

General conditions

- The technical bid must be signed and stamped (if stamp is used).

- The structure of the technical bid must correspond to the structure of the ToRs. The concept shall generally follow the structure of Chapter 3 and should be organised in accordance with the positively weighted criteria in the assessment grid.

- The technical bid must be legible (font size 11 or larger) and clearly formulated.

- It must be drawn up in Ukrainian and English languages.

- The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

CV requirements

- The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted.

- The CVs shall not exceed 4 pages each.

- They must clearly show the position and job the proposed person held in the reference project and for how long.

- The CVs must be drawn up in Ukrainian and English languages.

Disqualification clause

- The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise the bid will be disqualified.

### 10.1.2 Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid must be signed and stamped (if stamp is used).

### 10.1.3 Registration documents of the tenderer

Shall be provided according to the requirements of tender documentation

10.1.4 Documents for tenderer’s eligibility confirmation

Eligibility confirmation documents shall be submitted in accordance with the separate eligibility requirements and forms provided as part of the tender documentation.

# 11. Annexes

- Annex 1 – Technical Specifications for the development of a Feasibility Study (FS) and Design and Estimate Documentation (Stage “DS”) for the reconstruction of the boiler house at 8 Onoprienka Street, Cherkasy.

Annex 1

TECHNICAL SPECIFICATIONS

for the development of a Feasibility Study (FS) and Design and Estimate Documentation (Stage ‘DS’)

"Technical re-equipment of the existing boiler house for a solid fuel boiler with a capacity of 5 MW on biomass and RDF"

1. GENERAL INFORMATION

1.1 Customer

Municipal Enterprise of Heat Networks "Cherkasyteplokommunenergo" of the Cherkasy City Council

- EDRPOU code: 02082522

- Form of ownership: communal

- Contact person: Head of MTS Kirnasovsky Ilya Oleksandrovych

- E-mail: illyakurnas91@ukr.net

- Phone: +380634791005

1.2 Design object

- Address: Cherkasy, st. Onoprienka, 8

- Year of commissioning of the building: 1973

- Current installed thermal capacity: 24.86 MW

1.3 Project goal

Technical re-equipment of the existing gas boiler house by installing a solid fuel boiler with a capacity of 5 MW for operation on biomass (wood chips and corn cobs) in order to:

- Fuel diversification and reduction of dependence on natural gas

- Reducing CO₂ emissions through the use of renewable energy sources

- Reduction of tariffs for consumers by 10%

2. CURRENT STATE OF THE OBJECT

2.1 Existing equipment

Boilers:

- LOOS UT-M 54

- VK-21

- TVG-8M

- Total quantity: 3 pcs.

- Efficiency of existing boilers: 95%

Additional equipment:

- Caterpillar G3512E Cogeneration Unit

2.2 Thermal characteristics

- Peak heat load: 10.57 MW

- Average annual heat load: 4.8 MW

- Mains water parameters: 95°C/70°C at 6 bar

2.3 Fuel consumption (last 3 years)

- 2022: 2,270,217.82 m³ of natural gas

- 2023: 2,308,396.06 m³ of natural gas

- 2024: 2,273,589.69 m³ of natural gas

2.4 Environmental performance

- CO₂ emission limit: 14,000 t/year (according to EIA approval)

- Sanitary protection zone: none

- Noise level requirements: 30-40 dBA

3. TECHNICAL REQUIREMENTS FOR NEW EQUIPMENT

3.1 Basic parameters of the boiler

- Rated Thermal Capacity: 5MW

- Boiler type: solid fuel with automatic fuel supply

- Design efficiency: 85-88% at rated power

- Modulation range: 20-100% rated power

3.2 Fuel base

Main fuel:

- Wood chips: 75% of the total volume or 100%

- Corn cob crushed: 25% of the total volume

- Permissible fuel moisture: up to 40%

- Annual fuel volume: 11,700 t/year

- Automatic dosing of fuel components

3.3 Coolant parameters

- Temperature Schedule: Support Existing 95°C/70°C

- System pressure: 6 bar

- Adjustment method: installation of a heat exchanger for circuit separation

- Power regulation: modulation in the range of 20-100%

3.4 Fuel Supply System

- Fuel Supply Adjustment: Changing the Speed of Conveyors/Augers

- Dosing system: automatic with the ability to mix different types of fuel

- Warehousing: own fuel warehouse with cover

4. AUTOMATION AND CONTROL SYSTEMS

4.1 ACS (Automatic Control System)

Main functions:

- Automatic boiler ignition

- Combustion Process Support and Safe Stop

- Adjusting the fuel and air supply depending on the heat load

- Maintaining coolant parameters (supply/return water temperature, pressure)

- Protection of the boiler from overheating, low water level, emergency modes

- Automatic switching of operating modes

4.2 Combustion Regulation

Air Supply:

- Control of primary air fans (shingle)

- Control of secondary air fans (grate)

- Automatic optimization of the fuel-to-air ratio

Process control:

- Controlling the temperature in the furnace

- Flue gas composition control (O₂, CO)

- Automatic traction adjustment

4.3 SCADA system

- Visualization of all technological parameters

- Archiving Operation Data

- Remote monitoring and management

- Alarm and Alarm System

5. AUXILIARY EQUIPMENT

5.1 Pumping Equipment

- Installation of new circulation pumps with frequency converters (primary circuit)

- The characteristics of the pumps are determined by hydraulic calculation

- Redundancy of the main pumps

5.2 Water treatment system

- Adaptation of the existing system to new needs

- Taking into account the chemical composition of the available water

- Water quality control system

6. FLUE GAS PURIFICATION SYSTEM

6.1 Emission requirements

- Compliance with Ukrainian emission standards

- Possibility of adjusting the existing emission permit

6.2 Cleaning System Components

Mandatory elements:

- Cyclone separators for ash separation

- Multi-section bag filters

- Acid Purification System

- Control of CO₂, NOₓ, SO₂, particulate matter emissions

6.3 Chimney

- Development of a solution for the construction of a new chimney

- Calculation of height and diameter according to the standards

- Providing natural or forced traction

7. CONSTRUCTION AND PLANNING SOLUTIONS

7.1 Boiler Room

- Dimensions are determined by the project

- Arrangement of a new foundation for the boiler

- Providing free access for maintenance

7.2 Fuel composition

- Designing your own warehouse with a cover

- Calculation of capacity for a 3-day fuel supply

- Fuel supply system to the boiler (conveyors, elevators)

7.3 Transport accessibility

- Gate height: unlimited

- Turning radius: 16.5 m

- Distance to fuel sources: 8-10 km

7.4 Power Supply

- Using an existing 400V mains

- Integration with an existing CHP plant

- Backup power supply

8. ENVIRONMENTAL ASPECTS

8.1 Emission reductions

- Calculation of CO₂ reduction compared to a gas boiler

- Use of renewable energies (biomass)

8.2 Permits

- Adjustment of the permit for emissions of pollutants

- Environmental expertise of the project

9. COMPOSITION OF PROJECT DOCUMENTATION

9.1 Main sections

- General explanatory note

- Technological solutions

  - Boiler equipment and auxiliary systems

  - Fuel supply and preparation system

  - Flue Gas Purification System

  - Automation and instrumentation

- Heating part

  - Boiler heat balance

  - Calculation of efficiency

  - Schemes of heating networks

- Construction part

  - Structural solutions

  - Foundations for equipment

  - Fuel composition

- Electrical part

  - Power Electrical Equipment

  - Automation systems

  - Lighting and grounding

- Sanitary and technical part

  - Boiler room ventilation

  - Water supply and sewerage

- Economic part

  - Estimate documentation

  - Technical and economic indicators

- Environmental protection

  - Emissions calculations

  - Environmental measures

- Occupational health and fire safety

- Energy efficiency measures

10. INITIAL DATA FOR DESIGN

10.1 Documents provided by the Customer

- Photo of the existing boiler room hall (min. 3 pcs.)

- Current schemes of heating networks (.plan / pdf)

- Last Annual Fuel and Heat Balance

- Emission Permit/EIA Conclusion

- Title documents for the land plot and building

- Technical passport of the building

- Measuring drawings of the boiler room (. DWG)

- Drawings of boiler room foundations

- Chimney drawing

- Topographic survey of scale 1:500, 1:2000

- Single-line diagram of the main switchboard

- Plan of the existing ventilation system

- Cogeneration plant information

- Specifications for gas and electricity

- Hydraulic diagrams of the heating network

- Ventilation and chimney passport

- Analysis of the chemical composition of water

- Hourly workloads for 2021-2024

10.2 Additional data for clarification

- Seasonal availability of different fuels

- Requirements for ash content and calorific value of fuel

- Specific dimensions of the boiler room

11. EXPECTED RESULTS

11.1 Technical indicators

- Installation of a 5 MW boiler with an efficiency of 85-88%

- Ensuring biomass operation

- Process automation with remote control

- Compliance with all environmental regulations

11.2 Economic indicators

- Reduction of tariffs for consumers by 10%

- Creation of 4-6 new jobs

- Project payback period: determined during the design process

11.3 Environmental performance

- Reducing CO₂ emissions through the use of biomass

- Municipal solid waste disposal

- Reducing dependence on fossil fuels

12. IMPLEMENTATION STAGES

12.1 Design

- Development of project documentation: 6-8 months

- Examinations: 2-3 months

- Obtaining permits: 1-2 months

12.2 Construction

- Start of work: spring 2026

- Installation duration: from November 2026

- Commissioning: determined by the construction schedule

12.3 Outage schedule

- Scheduled outage schedule agreed with local authorities

- Minimization of interruptions in heat supply

- Phased commissioning

13. REQUIREMENTS FOR THE CONTRACTOR

13.1 Eligibility Requirements

- Experience in designing solid fuel boiler houses with a capacity of 5 MW or more

- Licenses for the design of energy facilities

- Knowledge of Ukrainian and European standards in the field of energy

13.2 Warranty Obligations

- Warranty for design solutions

- Author's supervision during construction

- Maintenance during commissioning

Head of the military-technical cooperation of
the Municipal Enterprise "Cherkasyteplokommunenergo"
_______________ I.O. Kirnasovskyi

"___" _________ 2026

Note: The final technical parameters, economic indicators and detailed specifications of the equipment will be clarified and detailed in the process of developing project documentation based on additional initial data provided by the Customer.