| ToR for Legal and Regulatory Advisory Services for Development of the Unified Environmental Permitting and Implementation of IED 2.0 in Ukraine | Project number /cost centre: G-011970-001 |
| --- | --- |

Terms of reference

- List of abbreviations

| AG | Commissioning Party |
| --- | --- |
| AN | Contractor |
| AVB | General Terms and Conditions of Contract for supplying services and work |
| BAT | Best Available Techniques |
| BMUKN | Federal Ministry for the Environment, Climate Action, Nature Conservation and Nuclear Safety |
| CBAM | Carbon Border Adjustment Mechanism |
| FK | Expert |
| FKT | Expert days |
| IED | Directive 2010/75/EU on Industrial Emissions |
| IED 2.0 | Industrial and Livestock Rearing Emissions Directive (Directive 2010/75/EU, as amended by Directive (EU) 2024/1785) |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH |
| EU | European Union |
| IKI | International Climate Initiative |
| KZFK | Short-term expert |
| MEEA | Ministry of Economy, Environment and Agriculture of Ukraine |
| PAABS | Paris Agreement and Adaptation to the Impact of Climate Change in the Black Sea Region |
| SMEs | Small and medium-sized enterprises |
| ToRs | Terms of Reference |
| UEP | Unified Environmental Permitting |

- Context

Ukraine has been undertaking one of its most important environmental governance reforms in the context of its EU accession process – the implementation of the Directive 2010/75/EU Industrial Emissions Directive on Industrial Emissions (IED), which establishes an integrated approach to the prevention and control of pollution from large industrial installations. The reform fundamentally changes the approach to industrial environmental regulation by replacing fragmented environmental authorizations with a comprehensive permitting system covering all significant environmental impacts of industrial installations. A landmark was reached on 8 August 2025, when Law No. 3855-IX "On Integrated Prevention and Control of Industrial Pollution" entered into force. This is Ukraine's first comprehensive framework for integrated environmental permitting based on Best Available Techniques (BAT), fully aligned with EU and IED standards.

To support the practical transition toward an integrated environmental permitting system, the "Best Available Techniques (BAT) for Ukraine" Project has been providing technical assistance to the Government of Ukraine since 2019 through cooperation with the Ministry of Economy, Environment and Agriculture of Ukraine (MEEA). The project is implemented by the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH on behalf of the Federal Ministry for the Environment, Climate Action, Nature Conservation and Nuclear Safety (BMUKN) under the International Climate Initiative (IKI). The project has made a substantial contribution to establishing Ukraine's integrated permitting system, including support for the development of primary and secondary legislation, deployment of digital permitting solutions, strengthening of technical capacities among key stakeholders, and promotion of BAT-based industrial modernization.

The Supporting Ukraine in the implementation of the Paris Agreement and Adaptation to the impact of climate change in the Black Sea region (PAABS) Project implemented by GIZ, on behalf of the BMUKN, supports Ukraine in transitioning to low-carbon pathways and building a climate-resilient future by improving climate governance, supporting evidence-based policy making, and facilitating the implementation of the IED and adaptation practices. The PAABS Project is engaged in the IED implementation given the direct interdependence between industrial pollution control, greenhouse gas emission reduction, and Ukraine's obligations under Carbon Border Adjustment Mechanism (CBAM) and the EU Green Deal given the companies failing to comply with IED requirements face significant additional costs under CBAM. The project provides regulatory impact assessments, analytical support, and expert assistance for drafting key legal documents essential for IED implementation.

Despite the significant progress achieved in establishing an integrated permitting framework for large industrial installations, several regulatory and implementation challenges remain. First, the European Union has adopted substantial amendments to Directive 2010/75/EU on Industrial Emissions through Directive 2024/1785/EU, resulting in the revised Industrial and Livestock Rearing Emissions Directive (Directive 2010/75/EU, as amended by Directive (EU) 2024/1785) (IED 2.0). These amendments introduce new concepts, strengthened environmental performance requirements, enhanced transparency and public access provisions, updated permitting procedures, additional sector-specific obligations, and expanded digital reporting requirements. To maintain alignment with the EU acquis and support accession negotiations, Ukraine must assess the implications of these changes and identify the legislative and institutional measures required for their implementation.

Second, a significant regulatory gap remains for enterprises outside the scope of integrated permitting requirements — particularly small and medium-sized enterprises (SMEs) classified under Ukrainian legislation as Group II and Group III operators. These enterprises represent a substantial share of Ukraine's industrial base, contributing considerably to overall environmental emissions. The absence of a coherent, simplified, and legally enforceable permitting framework for these operators creates fragmentation across sector-specific procedures and limits the overall effectiveness of environmental governance. To address this, the MEEA seeks development of a Unified Environmental Permitting (UEP) complementing the integrated permitting system.

Addressing these challenges requires highly specialized legal, regulatory, and policy expertise combining knowledge of Ukrainian environmental legislation, EU environmental acquis, legislative drafting processes, industrial permitting systems, and stakeholder consultation mechanisms. Given the strong interconnection between the development of the UEP and continued approximation to the IED 2.0, the BAT for Ukraine and PAABS projects have agreed to implement a joint expert assignment. The assignment will provide coordinated expert legal and regulatory advisory support to the MEEA, ensure consistency across reform initiatives, avoid duplication of efforts, and support the development of a coherent and future-oriented environmental regulatory framework aligned with Ukraine's EU accession objectives.

- Tasks to be performed by the contractor

The Contractor shall provide expert legal and regulatory advisory support to assist the MEEA and GIZ with the development of legislative framework, implementation planning, stakeholder consultations, and negotiation support related to two parallel reform tracks: (1) approximation of Ukrainian legislation on integrated permitting with IED 2.0 provisions, (2) development of legislative framework for Unified Environmental Permitting

  - Tasks

The contractor is responsible for providing the following services:

Task 1. Provide expert legal and regulatory advisory support for the alignment of Ukrainian legislation with the Industrial and Livestock Rearing Emissions Directive (Directive 2010/75/EU, as amended by Directive (EU) 2024/1785) (IED 2.0), including:

- Assessment of legislative gaps between Ukrainian legislation and IED 2.0 requirements concerning the integrated permitting procedure.

- Development of a legislative approximation roadmap for transposition of IED 2.0 provisions related to the integrated permitting procedure.

- Drafting of amendments to primary legislation required for approximation to IED 2.0 related to the integrated permitting procedure.

- Legal advisory and negotiation support during governmental and parliamentary review of draft legislative amendments.

- Drafting of secondary legislation required for implementation of IED 2.0 provisions related to the integrated permitting procedure.

- Revision and finalization of secondary legislation and implementation measures following consultations and legislative review processes.

Task 2. Provide expert legal and regulatory advisory support to develop a unified environmental permitting framework for SMEs outside the scope of integrated permits and IED-regulated activities, including:

- Legal backup for amendments to the Concept and Operational Plan for the implementation of the state policy of Integrated Pollution Prevention and Control (IPPC) to accommodate the Unified Environmental Permitting into the existing industrial emission reform frame and distinguish it from registration procedures under environmental legislation.

- Development of a legislative roadmap for introducing the UEP into environmental permitting legislation.

- Drafting of amendments to primary legislation introducingt the UEP.

- Legal advisory and negotiation support during governmental and parliamentary review of draft legislative amendments.

- Drafting of secondary legislation required for implementation of the UEP.

- Revision and finalization of secondary legislation and implementation measures in line with stakeholder consultations and relevant EU acquis.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Task 1. Approximation of Ukrainian legislation on integrated permitting with IED 2.0 provisions |  |
| 1.1 Gap assessment of Ukrainian legislation against IED 2.0 and legislative approximation roadmap for transposition of amended IED 2.0 provisions prepared and submitted to GIZ and MEEA. - Review of IED 2.0 requirements concerning integrated permitting procedures, and identification of legislative and institutional gaps with existing Ukrainian legislation. - Identification of new concepts, terminology, permitting requirements, sectoral provisions, electronic systems, and implementation obligations introduced by IED 2.0. - Preparation and presentation of a gap assessment report with recommendations for legislative approximation. - Identification of legislative measures required for transposition of IED 2.0 provisions. - Mapping of amendments required to primary and secondary legislation. - Development of a legislative approximation roadmap, including sequencing of reforms and implementation priorities. - Consultation with relevant stakeholders and incorporation of comments. | 30.09.2026 / Contractor / Kyiv The Contractor shall report to BAT for Ukraine Project |
| 1.2 Draft law introducing amended IED 2.0 provisions into the integrated permitting framework prepared and submitted to GIZ and MEEA. - Preparation of draft amendments to relevant laws required for approximation to IED 2.0. - Preparation of explanatory materials and legal justification of proposed amendments. - Presentation of draft legislative amendments to stakeholders. - Revision of draft legislation following consultations (if necessary). | 31.12.2026 / Contractor / Kyiv The Contractor shall report to BAT for Ukraine Project |
| 1.3 Consultation and negotiation support provided to MEEA during governmental and parliamentary review of the IED 2.0 draft law. - Provision of legal advice during governmental, interagency, and parliamentary review procedures. - Preparation of legal opinions, briefing notes, and responses to stakeholder comments. - Participation in working groups, consultations, and negotiation meetings. - Revision of draft legislative amendments where necessary. | 30.09.2027 / Contractor / Kyiv The Contractor shall report to PAABS Project |
| 1.4 Draft secondary legislation package for implementation of amended IED 2.0 provisions prepared and submitted to GIZ ad MEEA. - Preparation of draft secondary legislation and implementing acts required for implementation of IED 2.0. - Development of procedural, institutional, and technical implementation measures. - Consultation with stakeholders and competent authorities (if necessary). | 30.09.2027 / Contractor / Kyiv The Contractor shall report to PAABS Project |
| 1.5 Finalized secondary legislation package and implementation roadmap for implementation of amended IED 2.0 submitted. - Revision of draft secondary legislation following consultations and legislative developments. - Alignment of implementation measures with adopted primary legislation. - Preparation of final versions of secondary legislation and implementation recommendations. | 30.11.2027 / Contractor / Kyiv The Contractor shall report to PAABS Project |
| Task 2. Development of legislative framework for Unified Environmental Permitting |  |
| 2.1 Amendments to the IPPC Concept and Operational Plan developed to integrate the UEP into the industrial emissions reform framework and legislative roadmap for introduction of the UEP prepared and submitted. - Legal analysis of the existing Concept and Operational Plan for IPPC implementation. - Development of proposals for integrating the UEP into the industrial emissions reform framework. - Preparation of amendments to the IPPC Concept and Operational Plan. - Consultation and presentation of proposed amendments to stakeholders. - Identification of legislative amendments required for establishment of the UEP framework. - Analysis of interactions between permitting and registration procedures. - Mapping of amendments required to primary and secondary legislation. - Development of a legislative roadmap for UEP implementation. | 31.12.2026 / Contractor / Kyiv The Contractor shall report to BAT for Ukraine Project |
| 2.2 Draft law introducing the UEP prepared and submitted to GIZ and MEEA. - Preparation of draft legislative amendments introducing the UEP. - Development of legal provisions governing permit applications, permit consideration, public participation, permit conditions, and review procedures. - Consultation with stakeholders and revision of draft legislation. | 30.12.2026 / Contractor / Kyiv The Contractor shall report to BAT for Ukraine Project |
| 2.3 Consultation and negotiation support provided to MEEA during governmental and parliamentary review of the UEP draft law. - Provision of legal advice during governmental and parliamentary review procedures. - Participation in consultations, working groups, and stakeholder meetings. - Preparation of legal opinions and responses to comments. - Revision of draft legislation where required. | 30.09.2027 / Contractor / Kyiv The Contractor shall report to PAABS Project |
| 2.4 Draft secondary legislation package for implementation of the UEP prepared and submitted to GIZ and MEEA. - Preparation of draft implementing regulations and secondary legislation necessary for operation of the UEP. - Development of procedural and administrative implementation mechanisms. - Consultation with relevant stakeholders. | 30.09.2027 / Contractor / Kyiv The Contractor shall report to PAABS Project |
| 2.5 Finalized secondary legislation package and implementation roadmap for the UEP submitted to GIZ and MEEA. - Revision of draft secondary legislation based on consultations and legislative developments. - Alignment of implementation measures with relevant EU acquis and adopted legislation. - Preparation of final implementation recommendations and legislative texts. | 30.11.2027 / Contractor / Kyiv The Contractor shall report to PAABS Project |

Period of assignment is from 10.08.2026 till 31.12.2027.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Task 1. Approximation of Ukrainian legislation on integrated permitting with IED 2.0 provisions |  |  |
| D1.1 IED 2.0 Gap assessment and Approximation roadmap package - Gap assessment table - Legislative approximation roadmap The Contractor shall report to BAT for Ukraine Project | Submitted as two separate documents: - Gap assessment report in Ukrainian and/or English, if appropriate and - (ii) Legislative approximation roadmap in Ukrainian both in editable (.docx, .pdf) formats. Gap assessment report shall comprise at least 3 pages and provide a comprehensive assessment supported by references to relevant provisions of IED 2.0 and Ukrainian legislation and shall be presented to MEEA and GIZ for review. Legislative approximation roadmap shall comprise at least 3 pages and provide a complete and coherent approach to transposition of IED 2.0 provisions related to integrated permit procedure and shall be revised following stakeholder consultations. | 30.09.2026 |
| D1.2 IED 2.0 Primary legislation package - Initial draft law on amendments to the primary legislation required for approximation to IED 2.0 provisions related to integrated permit procedure - Explanatory note(s) - Comparative tables and EU acquis reference table(s) The Contractor shall report to BAT for Ukraine Project | All deliverables shall be prepared in the Ukrainian language and in accordance with the legal drafting standards and procedures applicable in Ukraine. Submitted in Ukrainian, in editable (.docx, .pdf) formats; explanatory documentation shall comprise at least 2 pages (excluding legislative text and comparative/EU acquis tables. The Contractor shall ensure that comments received from MEEA, GIZ, public authorities, and other stakeholders are duly considered and reflected in the submitted documents, as appropriate. | 31.12.2026 |
| D1.3 IED 2.0 Negotiation support package - Conciliatory report(s) of comments received during governmental and parliamentary review - Proposed revisions to draft primary legislation based on consultation and negotiation outcomes (revised drafts of the draft law on amendments to the primary legislation) Legal advisory notes and supporting materials required during legislative review and adoption processes as appropriate The Contractor shall report to PAABS Project | Submitted in Ukrainian and/or English, if appropriate in editable (.docx, .pdf) formats. The Conciliatory report(s) shall comprise at least 3 pages. The Contractor shall maintain full traceability of revisions and demonstrate how comments received from MEEA, GIZ, public authorities, business representatives, civil society organizations, and other stakeholders have been addressed. | 30.09.2027 |
| D1.4 IED 2.0 Secondary legislation package - Initial drafts of secondary legislation and implementing acts required for approximation to IED 2 in relation to integrated permitting procedure The Contractor shall report to PAABS Project | Submitted in Ukrainian, in editable (.docx, .pdf) formats; accompanying documentation (if applicable) shall comprise at least 3 pages (excluding legislative texts). Initial drafts of legal documents shall be prepared in the Ukrainian language and in the format required for legal drafting, governmental review and legal implementation in Ukraine. | 30.09.2027 |
| D1.5 Final IED 2.0 approximation package and Interim narrative report - Final clean and track-changes versions of all legislative texts - Interim narrative report The Contractor shall report to PAABS Project | Final legislation package shall be prepared and submitted in a format suitable for further legislative adoption procedures. Submitted in Ukrainian, in editable (.docx, .pdf) formats; accompanying documentation (if applicable) shall comprise at least 2 pages (excluding legislative texts). The Interim narrative report shall be submitted in English in editable (.docx, .pdf) formats, comprise at least 2 pages and shall summarize activities implemented under the IED 2.0 component, deliverables completed, challenges encountered and planned activities. | 30.11.2027 |
| Task 2. Development of legislative framework for Unified Environmental Permitting |  |  |
| D2.1 UEP conceptual package - Proposals to the development of amendments to the IPPC Concept with a view to accommodating the unified permit approach into the existing frame of the industrial emission reform and differentiation of the unified permit approach with the registration procedure for other activities as appropriate - Proposals to the development of amendments to the Operational Plan as appropriate - Roadmap of legislative amendments for the introduction of the unified permit approach into the air emissions legislation and differentiation of the unified permit approach with the registration procedure for other activities The Contractor shall report to PAABS Project | Submitted in Ukrainian and/or English, if appropriate in editable (.docx, .pdf) formats. The Conceptual package shall comprise at least 5 pages. The documents shall demonstrate integration of the UEP into the industrial emissions reform framework, differentiation between permitting and registration procedures, mapping of affected legislation, implementation priorities and references to relevant EU acquis. | 31.12.2026 |
| D2.2 UEP primary legislation - Initial draft law on introduction of UEP into the air emissions legislation - Explanatory note(s) - Comparative tables and EU acquis reference table(s) The Contractor shall report to BAT for Ukraine Project | All deliverables shall be prepared in the Ukrainian language and in accordance with the legal drafting standards and procedures applicable in Ukraine. Submitted in Ukrainian, in editable (.docx, .pdf) formats; explanatory documentation shall comprise at least 2 pages (excluding legislative text and comparative/EU acquis tables. | 31.12.2026 |
| D2.3 UEP Negotiation support package - Conciliatory report(s) of comments received during governmental and parliamentary review - Proposed revisions to draft law based on consultation and negotiation outcomes (revised drafts (track-changes and clean versions) - Legal advisory notes and supporting materials required during legislative review and adoption processes as required The Contractor shall report to PAABS Project | Submitted in Ukrainian and/or English, if appropriate in editable (.docx, .pdf) formats. The Negotiation support package shall comprise at least 5 pages. The Contractor shall ensure that comments received from MEEA, GIZ, public authorities, and other stakeholders are duly considered and reflected in the submitted documents, as appropriate The Contractor shall maintain full traceability of revisions and demonstrate how comments received from MEEA, GIZ, public authorities, business representatives, civil society organizations, and other stakeholders have been addressed. | 30.09.2027 |
| D2.4 UEP secondary legislation package - Initial draft secondary legislation and implementing acts required for UEP implementation as appropriate - Explanatory notes and legal justifications; The Contractor shall report to PAABS Project | Submitted in Ukrainian, in editable (.docx, .pdf) formats; explanatory documentation shall comprise at least 2 pages (excluding legislative texts). Initial draft legal documents shall be prepared in the Ukrainian language and in the format required for legal drafting, governmental review and legal implementation in Ukraine. | 30.09.2027 |
| D2.5 Final UEP legislative package and Final narrative report - Finalized draft legislation revised following consultations - Final clean and track-changes versions of all legislative texts - Final narrative report The Contractor shall report to PAABS Project | Final legislation package shall be prepared and submitted in a format suitable for further legislative adoption procedures and shall include finalized legislation revised following consultations with MEEA, GIZ and stakeholders, implementation recommendations and a summary of comments received and addressed. Submitted in Ukrainian, in editable (.docx, .pdf) formats; accompanying documentation (if applicable) shall comprise at least 2 pages (excluding legislative texts). The Final narrative report shall be submitted in English in editable (.docx, .pdf) formats, comprise at least 3 pages and shall summarize all activities performed under the contract, delivered outcomes, key legislative proposals, implementation challenges, lessons learned. | 30.11.2027 |

3. Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

4. Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

The personnel must be provided for all positions, otherwise, the bid will be disqualified. Each expert can hold only one position, multiple position holding is not permitted.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team Lead

Tasks of the team leader

- Overall responsibility for the quality, coherence and timely delivery of all advisory services;

- Coordination of the expert team and ensuring consistent alignment between the two reform tracks;

- Primary point of contact with GIZ (BAT for Ukraine and PAABS project teams) and the MEEA;

- Regular reporting in accordance with contractual deadlines.

Qualifications of the team leader

- Education/training (2.1.1): University degree (Master’s or equivalent) in Economics, Law, Public Administration or other related fields.

- Language (2.1.2): C1-level language proficiency in English according to the Common European Framework of Reference for Languages.

- General professional experience (2.1.3): 15 years of professional experience in economic development, financial advisory, project management, regulatory reform or related fields.

- Specific professional experience (2.1.4): 7 years of experience in providing advisory services related to policy implementation, regulatory and legal strategies development, stakeholder engagement.

- Leadership/management experience (2.1.5): 5 years of management or leadership experience as team lead, project coordinator, senior consultant, advisory lead, or in a comparable management role.

- Regional experience (2.1.6): 10 years of experience in projects implemented in Ukraine and/or Eastern Europe.

- Development cooperation (DC) experience (2.1.7): 5 years of experience in donor-funded projects financed by international development partners or financial institutions.

- Other (2.1.8): 3 years of experience working with governmental institutions, experience in stakeholder coordination, Green Deal-related and/or EU integration initiatives, or related fields.

## Short-term expert pool with minimum 3, maximum 4 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 10 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- Provide expert legal and regulatory advisory support for the alignment of Ukrainian legislation with the Industrial and Livestock Rearing Emissions Directive (Directive 2010/75/EU, as amended by Directive (EU) 2024/1785) (IED 2.0).

- Provide expert legal and regulatory advisory support to develop a unified environmental permitting framework for SMEs outside the scope of integrated permits and IED-regulated activities.

Qualifications of the short-term expert pool

- Education/training (2.6.1): all experts with university qualification (Master’s or equivalent) in Law, International Law, Political Science or other related fields;

- Language (2.6.2): all experts with C1-level language proficiency in English according to the Common European Framework of Reference for Languages;

- General professional experience (2.6.3): all experts with 15 years of professional experience in legal, regulatory, policy development, legislative drafting or related sectors;

- Specific professional experience (2.6.4): all experts with 10 years of professional experience in providing legal and advisory services related to the approximation and implementation of the EU acquis, support to environmental reform processes;

- Regional experience (2.6.5): 7 years of experience in projects implemented in Ukraine and/or Eastern Europe;

- Development cooperation (DC) experience (2.6.6): 5 years of experience in donor-funded projects financed by international development partners or financial institutions;

- Other (2.6.7): 3 years of experience supporting Ukraine's EU accession process, experience working with ministries and regulatory authorities, experience in supporting IED implementation or related industrial pollution legislation.

# 5. Costing requirements

## Assignment of personnel and travel expenses – Not applicable

## Sustainability aspects for travel and travel regulations – Not applicable

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| Designation of Team Lead | Expert days | 1 | 145 |  |
| Designation of Short-term Expert Pool | Expert days | 3-4 | 413 | Pool of 3-4 local experts, number of expert days for pool in total |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# 6. Inputs of GIZ or other actors

GIZ is expected to make the following available:

- Access to available project documents, studies, legislative analyses, draft legal acts, and other relevant materials.

- Facilitation of consultations and meetings with MEEA, other public authorities, development partners, and relevant stakeholders.

- Technical feedback on draft deliverables and coordination with related reform initiatives.

- Support in organizing stakeholder consultations and expert meetings, where required.

- Available information and documentation related to the integrated environmental permitting system and ongoing environmental governance reforms.

The MEEA is expected to:

- Provide available policy and legislative documents relevant to the assignment.

- Designate focal points for coordination and consultation.

- Participate in the review of draft outputs and provide comments within reasonable timeframes.

7. Financial provisions

7.1 Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

7.2 Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, incl. VAT if applicable.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

7.3 Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments on quarterly basis.

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

7.4 Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF) and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- Each invoice and act of acceptance shall contain the Project Number, contract number and the percentage for cost split as follows:

- G-011970-001 – 50%

- G-011201-001 – 50%

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Service Entry Sheets (LERF) will be provided during contract implementation.

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

8. Other Provisions

8.1 General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, and the given procurement of services/ works upon the Contract shall not be determined free from VAT,  the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor Anna Bondarchuk, +380978858929, anna.bondarchuk@giz.de.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

8.2 VAT Exemption – n/a

# 9. Outsourced processing of personal data – n/a

# 10. Requirements to the format of the bid

10.1 Documents to be submitted

10.1.1 Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- tentative work plan,

- personnel (team) concept,

- CVs of all experts with relevant work experience.

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 3 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

10.1.2 Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

10.1.3 Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.