| PROCUREMENT OF COMMUNICATIONS AND VISIBILITY EXPERT SERVICES TO SUPPORT U-LEAD ACTIVITIES ACROSS FOUR OPERATIONAL TEAMS AND SELECTED THEMATIC AREAS | Project number/ cost centre: G-012306-002 |
| --- | --- |

Terms of reference

0.	List of abbreviations	2

1.	Context	3

2.	Tasks to be performed by the contractor	4

3.	Concept	8

Technical-methodological concept	8

Cooperation (1.2)	8

Further requirements (1.7)	8

4.	Personnel concept	8

5.	Costing requirements	9

Assignment of personnel and travel expenses	9

6.	Inputs of GIZ or other actors	9

7.	Financial provision 	10

8.	Requirements to the format of the bid	10

9.	Other provisions  	11

10.	Outsourced processing of personal data	13

11.	Annexes	16

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

RO	Regional Office

RVE	Regional Visibility Expert

FB	Facebook

- Context

In 2020, Ukraine finalized the implementation of the administrative and territorial reform aimed at building up a viable system of local self-government that shall contribute to positive changes in the life of citizens. In October 2020, local elections took place in the newly established municipalities many of which experienced significant territorial changes.

The Multi-Donor Action “Ukraine Local Empowerment, Accountability and Development Programme” is jointly co-financed by the European Union (EU), its member states Germany, Poland, Denmark, Slovenia and France and implemented by Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH. On 1 January 2025 the Programme turned to its Phase III, which will be running until 31 December 2027. The main beneficiary of the Programme at the central level is the Ministry for Development of Communities and Territories of Ukraine that receives support in progressing the decentralisation reform and aligning regional policy with the EU acquis. At the sub-national level, the Programme continues supporting municipalities in all regions by enhancing professional and administrative skills of municipal officials for strong local self-government and by enabling municipalities to implement regional and local development policies and reconstruction planning in the context of Ukraine's accession to the EU.

The Overall Objective of the Programme is to contribute to further advancement of multi-level governance in Ukraine, which is transparent, accountable and responsive to the needs of the population in the context EU integration and rebuilding Ukraine.

Within this overall context, U-LEAD with Europe’s activities throughout Phase III are designed to achieve three results:

Result 1: The Ukrainian government and the Parliament are increasingly capable of advancing the decentralisation reform and aligning regional policy with the EU acquis.

Result 2: The professional and administrative skills of municipal officials for strong local self-government in the context of Ukraine's accession to the EU are enhanced, taking into account, among other things, the special needs of vulnerable groups and gender equality.

Result 3: Ukrainian municipalities are enabled to implement regional and local development policies and reconstruction planning in the context of the EU accession process.

Main focus areas of U-LEAD in Phase III comprise:

•	Pillar 1: Policy and legal advice for strong local self-governments and regions,

•	Pillar 2: Capacity development for all municipalities,

•	Pillar 3: Support to local reconstruction and development.

Within Pillar 1, legal and policy advice is rendered to partners in adjustment of legislation and aligning it to EU acquis regarding multi-level governance. In the framework of Pillar 2, informational, consultative and capacity-development measures are offered to municipalities across Ukraine in a tailor-made and targeted way within 12 thematic support packages and reflecting LSG needs and EU integration. Within Pillar 3, U-LEAD’s expertise contributes to local reconstruction, formation of absorption capacity for EU structural instruments, development of UA-EU partnership projects and support of municipalities in digital transformation.

The management/implementation structure for U-LEAD with Europe comprises a horizontal Directorate and four Programme Units in Kyiv, and 24 Regional Offices which directly support local self-government bodies.

U-LEAD strengthens the capacities of key actors on national and local level to steer and shape the local self-government reform, including the harmonisation with regional policy and sector reforms, in the context of rebuilding Ukraine and preparing it for EU membership. U-LEAD’s activities include enhancing local project preparation capacities, utilising digital resources as well as facilitating partnership relations with EU municipalities.

U-LEAD focuses on enhancing the capacities of local officials throughout the entire country. The Programme has provided and continues to provide targeted consultations, information and trainings to municipalities struggling to adjust to the current war situation, working mostly with local government officials from municipalities under 50,000 inhabitants. U-LEAD provides support to local government officials in managing their municipalities in the wartime environment, complying with the changing legislative framework and engaging in a sustainable recovery process.

Capacity development measures cover the full scope of municipal responsibilities during the war of aggression and recovery and are mainly rolled out through 24 Regional Offices (ROs), each of them working with the municipalities of their geographic regions, and Thematic Working Groups covering relevant sectors of work important for municipal authorities.

The work of Regional Offices as well as relevant sectoral developments (especially in some thematic areas) need to be visible to make sure that relevant good practices are shared at the regional and national levels and to comply with the visibility requirements of the EU and other donors.

The purpose of this contract is to procure professional communications and visibility expertise to support the activities of U-LEAD/GIZ by maintaining media relations, strengthening U-LEAD’s social media presence, promoting the Programme’s achievements in the regions, and developing various communication and visibility materials commissioned by U-LEAD in the following oblasts of assignment within a respective Operational Team (group of U-LEAD regional offices):

LOT 1: Kharkiv, Rivne, Sumy and Volyn Oblasts

LOT 2: Dnipropetrovsk, Donetsk (only government-controlled areas), Vinnytsia and Zakarpattia Oblasts

LOT 3: Cherkasy, Chernivtsi, Kyiv and Zaporizhzhia Oblasts

LOT 4: Chernihiv, Khmelnytskyi, Luhansk (only goverment-controlled areas) and Poltava Oblasts

- Tasks to be performed by the contractor

U-LEAD shall conclude contract(s) with Contractor(s) corresponding to four LOTs. Each LOT represents a defined geographic cluster of oblasts covered by one Operational Team and foresees the engagement of one communications expert responsible for providing communications and visibility support within that geographic area of the Operational Team.

The experts will support communication activities in the respective regions by maintaining media relations, supporting U-LEAD’s social media presence, promoting the Programme’s achievements, and developing various communication and visibility materials commissioned by U-LEAD.

In total, four experts (one per LOT) will be contracted, with each LOT covering a defined group of oblasts withing the geographic area and sectoral priorities of one Operational Team.

The Bidder is able to apply for 1 or more LOTs. In case of application for more than 1 LOT Bidder should provide different expert for each LOT. Each LOT will be assessed individually.

2.1. Tasks (for each lot)

The contractor is responsible for providing the following services:

- Providing regional visibility support to U-LEAD through coordination with the respective Operational Team, Regional Offices and Communications Team, including preparation of original content and publication of communication materials on the Facebook pages of Regional Offices in 4 oblasts of assignment.

- Maintaining U-LEAD’s regional Facebook pages in 4 oblasts of assignment by publishing approved communication materials and reposting relevant content from U-LEAD’s official Facebook page, municipalities’ Facebook pages and other agreed sources.

- Collecting and preparing visibility content related to U-LEAD activities in 4 oblasts of assignment, including drafting social media posts, gathering visual materials, testimonials from municipalities and other communication materials for publication through U-LEAD communication channels.

- Preparing materials for publication on the U-LEAD website covering U-LEAD activities, achievements, events, success stories and other relevant developments in 4 oblasts of assignment.

- Preparing and publishing interviews with representatives of municipalities, Regional Offices and experts to present success stories, good practices and results of U-LEAD activities in 4 oblasts of assignment.

- Organization and conducting media engagement events (in close coordination with Regional Offices) aimed at improving the cooperation of U-LEAD with the local media and the cooperation between the local media and municipalities.

- Preparing and providing local and regional media outlets in 4 oblasts of assignment with press releases, comments, explanatory materials, announcements, interviews and other communication products covering U-LEAD activities.

- Preparing and publishing communication materials on the sectoral dimension of local self-government reform and related U-LEAD activities in 4 oblasts of assignment, including press releases, comments, explanatory materials, articles and other visibility products.

- Providing further communications and visibility support upon request of U-LEAD Operational Team and Communications Team.

Additional tasks applicable only to LOT 2 and LOT 3:

- Providing communication support aimed at raising awareness of European integration processes at the local level by highlighting relevant municipal initiatives and practical examples of alignment with EU standards and approaches in 4 oblasts of assignment.

- Highlighting best practices of municipalities in international cooperation, including partnerships, networking initiatives and cooperation with international stakeholders, in 4 oblasts of assignment.

The contractor shall present GIZ and U-LEAD in an appropriate and professional manner and shall not under any circumstances engage in political discussions or other delicate issues. The contractor cannot represent GIZ and/or U-LEAD, act on behalf of them, give unauthorised comments, statements or opinions attributed to GIZ and/or U-LEAD.

The contractor is not a GIZ staff member. Any personal statement or opinion of the contractor must be clearly separated from those attributed to GIZ and/or U-LEAD. The contractor will respect the U-LEAD visibility guidelines and other EU, BMZ and GIZ regulations as advised by U-LEAD Communications Team.

The contractor shall ensure that all obligations, responsibilities, and compliance requirements stipulated in this Terms of Reference (ToR) extend fully to any subcontractors, third-party service providers, employees, or consultants engaged in the execution of the contract. The contractor remains fully liable for the performance, compliance, and adherence to all contractual terms by such subcontractors and employees.

The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ. The contractor reports regularly to GIZ in accordance with the current AVB of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

The contractor shall have access to the relevant Regional Offices of U-LEAD and their information necessary for the delivery of commissioned outputs. The contractor shall use all the materials obtained from U-LEAD/GIZ in a confidential manner and solely for the purpose of this contract.

The services shall be rendered on the territory of Ukraine (with the exception of temporarily occupied territories and combat areas).

Additional  milestones, KPIs and deadlines are to be agreed with U-LEAD Communications Team during the regular exchanges when the contracts enter into force in frames of indicated man/days.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| Conducting debriefing with U-LEAD Communication Team and Operational Teams for formation of monthly media plan | Monthly within contract duration, MS Teams/online, contractor |
| Conducting debriefing with Deputy Head of RegOps Unit and Heads of relevant Working Groups/She-LEADs Initiative for formation of quarterly communication plans | Quarterly within contract duration, MS Teams/online, contractor |
| Regular exchange with U-LEAD Communication Team and Operational Teams for discussion of media/visibility activities | Monthly within contract duration, MS Teams/online, contractor |

Period of assignment is from 1 September 2026 till 31 December 2027.

2.2. Deliverables and Reporting (per one LOT):

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| Preparation of original posts for ROs FB pages | Posts, Up to 4 per each of 4 RO | Per month within contract duration |
| Posting of prepared information at ROs FB pages | Posts, Up to 3 per each of 4 RO | Per month Within contract duration |
| FB reposts from U-LEAD FB page | Reposts, Up to 6 per each of 4 RO (on average 2 reposts per week) | Per month within contract duration |
| FB reposts from municipalities FB pages | Reposts, Up to 2 per each of 4 RO | Per month within contract duration |
| Preparation of materials for the U-LEAD website | Materials, 1 per each R O | Per month within contract duration |
| Preparing and publishing comprehensive interviews with representatives of Regional Offices, municipalities, experts, or other relevant stakeholders | Interview, 1 per each of 4 RO | Per year within contract duration |
| Organisation and implementation of media engagement events | Events, up to 4 events upon request of the Operational Team and Communications Team | Per year within contract duration |
| Preparation of materials for regional media | Communication activity, 1 per each of 4 R O | Per month within contract duration |
| Preparation of communication materials on the sectoral dimension of local self-government reform | Publication, 1 per each of 4 RO or WGs | Per month within contract duration |
| Additional communication and visibility support | Communication materials, media coordination, content collection, and other related tasks upon request of Head of Operational Team or Communication Team | within contract duration |
| 1st Progress Report | Timesheets, Progress Reports in Ukrainian and English including Annexes | 15 November 2026 |
| 2nd Progress Report | Timesheets, Progress Reports in Ukrainian and English including Annexes | 3 February 2027 |
| 3rd Progress Report | Timesheets, Progress Reports in Ukrainian and English including Annexes | 24 April 2027 |
| 4th Progress Report | Timesheets, Progress Reports in Ukrainian and English including Annexes | 13 July 2027 |
| 5th Progress Report | Timesheets, Progress Reports in Ukrainian and English including Annexes | 1 October 2027 |
| Final report | Timesheets, Final report should outline: - activities performed during the course of assignment - inputs and main results of the assignment - main conclusions and lessons learnt from the performance of the assignment - recommendations regarding follow-up activities U-LEAD might undertake Annexes should include all documentary outputs. | 20 December 2027 |

All documents will be revised and approved by GIZ. The materials and documents elaborated shall be considered as GIZ property and shall not be used by the awarded Expert or any other legal entity or private person without prior written approval by U-LEAD Communications Team or other GIZ representative. GIZ receives an exclusive right on use of all materials, works and developments created by the contractor during the period of this contract assignment.

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept).

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

Cooperation (1.2): The tenderer is required to describe the establishing of cooperation and then cooperating with the actors relevant for the services for which it is responsible (1.2.2).

## Further requirements (1.7)

The tenderer shall demonstrate knowledge of Ukraine’s decentralization reform agenda in the field of local self-government by providing descriptions of 3 specific cases/examples of cooperation with Ukrainian municipalities. Proven knowledge of Ukraine’s decentralization reform agenda, demonstrated through relevant professional experience will be taken into account during the technical assessment.

- Personnel concept (proposed staff)

Personnel Concept (Proposed Staff)

The Contractor is required to provide 1 personnel who is suited to filling the positions described on the based on their CVs, including links to relevant publication, communication materials and other work samples demonstrating their professional experience and qualification, (see Chapter 10), the range of tasks involved and the required qualifications. Individual experts can apply for selected lot.

As the tender is divided into four 4 separate lots, each lot requires one 1 dedicated Expert.

Each expert may be proposed for 1 lot only and may hold only one position under this procurement. Multiple position holding or proposing the same expert for more than one lot is not permitted.

The proposed expert shall meet the qualification requirements described below. The qualifications specified represent the requirements for achieving the maximum score in the technical evaluation.

Regional Visibility Expert (one position per lot)

Regional Visibility Expert (4 positions/ lots)

Tasks of Regional Visibility Expert (RVE)

•	Refer to Clause 2

Qualifications of RVE

- Education/training (2.2.1): university degree (Master’s degree) in communications, journalism, public relations or a related field (essential) (assessed by CV)

- Language (2.2.2): professional written proficiency in Ukrainian (C2 level) (Assessed by CV, Portfolio of the expert)

- General professional experience (2.2.3): 2,5 years of professional experience in the communications/ media relations/PR sector/journalism (assessed by CV)

- Specific professional experience (2.2.4):

  - 3 years of proven experience in covering local and regional news as well as the reform agenda in the context of local self-government topics including the examples of success stories, reports from municipalities, coverage of local events related to the reform implementation. Assessed by CV, Portfolio of the expert, supported by links on the relevant publications or work samples referenced in the CV. (3 points)

  - 2 years of proven experience in media relations, including drafting press announcements and press releases, and organising press conferences or press trips. Assessed by CV, Portfolio of the expert, supported by links on the relevant publications or work samples referenced in the CV.(2 points)

  - Experience of 3 contents from different media platforms, demonstrating proven storytelling skills supported by the relevant publications or work samples referenced in the portfolio. (2 points)

  - 2 years of proven experience of work within the reform implementation sector in Ukraine (experience in coverage/visibility of events related to decentralization reform is an advantage) (Assessed by CV, Portfolio of the expert, supported by links to relevant communication products/ publications/ project references/other evidence of involvement in reform-related assignments included in the CV.) (1 point)

  - Proven social media and networking expertise, 5 publications (Assessed by CV, supported by links on the relevant publications) (1 point)

  - Experience in professionally captured photo or video production, demonstrated by two relevant examples (links) included in the Portfolio (1 point)

# Costing requirements

## Assignment of personnel and travel expenses

All business travel must be agreed in advance with the GIZ staff member responsible for the project.

## Sustainability aspects for travel and travel regulations

If applicable on ground of these Terms of Reference the following travel regulations and reporting documents are to be observed. See Annex 1 to these Terms of Reference.

Place of assignment:

LOT 1
Kharkiv, Rivne, Sumy and Volyn Oblasts of Ukraine – home-based, occasional business travels within 4 oblasts of assignment are foreseen.

LOT 2
Dnipropetrovsk, Donetsk (government-controlled areas), Vinnytsia and Zakarpattia Oblasts of Ukraine – home-based, occasional business travels within 4 oblasts of assignment are foreseen.

LOT 3
Cherkasy, Chernivtsi, Kyiv and Zaporizhzhia Oblasts of Ukraine – home-based, occasional business travels within 4 oblasts of assignment are foreseen.

LOT 4
Chernihiv, Khmelnytskyi, Luhansk (government-controlled areas) and Poltava Oblasts – home-based, occasional business travels within 4 oblasts of assignment are foreseen.

Each lot of services of Regional Visibility Expert: amounts to up to 255 expert days.

All business travel must be agreed in advance with U-LEAD Operational Team, respective Deputy Head of Regional Operations Unit and must be coordinated with the respective Regional Office of U-LEAD.

The following travel regulations are to be observed. See Annex 1 to these Terms of Reference.

Specification of inputs

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| LOT 1 Regional Visibility Expert - Kharkiv, Rivne, Sumy and Volyn Oblasts of Ukraine | Expert days | 1 | 255 |  |
| LOT 2 Regional Visibility Expert - Dnipropetrovsk, Donetsk (government-controlled areas), Vinnytsia and Zakarpattia Oblasts of Ukraine | Expert days | 1 | 255 |  |
| LOT 3 Regional Visibility Expert - Cherkasy, Chernivtsi, Kyiv and Zaporizhzhia Oblasts of Ukraine | Expert days | 1 | 255 |  |
| LOT 4 Regional Visibility Expert - Chernihiv, Khmelnytskyi, Luhansk (government-controlled areas) and Poltava Oblasts | Expert days | 1 | 255 |  |
| Travel expenses | Unit of measurement | Quantity |  | Comments (if any) |
| LOT 1 Fixed travel budget for business trips within Ukraine |  |  |  | Reimbursement of travel expenses: hotel accommodation and tickets (bus, train), taxi - in accordance with travel regulations (see Annex 1 to the ToR), subject to the provision of supporting documents. Reimbursement of hotel accommodation expenses is carried out based on a hotel invoice. The hotel invoice must specify the room type and the guest's name. Maximum reimbursement ceilings are specified in Table 1 (see Annex). Reimbursement of ticket expenses is carried out by providing GIZ with the originals (or copies) of the tickets. The price must be indicated on the tickets. The budget is allocated for travel within Ukraine. A fixed budget of up to UAH 64 000 per each expert is intended for the reimbursement of travel expenses, subject to the provision of supporting documents. Reimbursement is only possible against evidence until the budget is exhausted. |
| LOT 2 Fixed travel budget for business trips within Ukraine |  |  |  |  |
| LOT 3 Fixed travel budget for business trips within Ukraine |  |  |  |  |
| LOT 4 Fixed travel budget for business trips within Ukraine |  |  |  |  |

## There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors

Not applicable

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, but excl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance in the agreed instalments on quarterly basis.

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment.

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF) and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

- Each invoice and act of acceptance shall contain the Project Number, contract number

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

- In case the Contractor is a VAT Payer at the moment of the Invoice issuing, the VAT exemption clause shall be applicable and the Contractor should also submit the Tax Invoice to GIZ as soon as that is available.

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contract enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contract/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local)published on the link  Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing the Contract, the Contractor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication will be assigned after contract signing.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be liable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

The given procurement of services/ works upon the Contract shall be carried out at the funds of the funds of the Project of International Technical Assistance (Project ITA), PN: 2023.2122.2, «Supporting decentralization in the context of reconstruction and EU integration in Ukraine / UDU – U-LEAD with Europe: Phase III», registered by the Secretariat of the Cabinet of Ministers of Ukraine (registration card of the project (program) No.   5974      dated   21/04/2025  ) and complies with the category (type) of Services specified in the purchase plan available at address https://www.kmu.gov.ua/diyalnist/mizhnarodna-dopomoga/pereliki-zareyestrovanih-proektiv-z-planami-zakupivel

The above-mentioned ITA project is implemented within the Framework Agreement between the Government of Ukraine and the Government of the Federal Republic of Germany on Counselling and Technical Cooperation dated 29/05/1996 and Framework Agreement between the Government of Ukraine and the Commission of European Communities ratified by the Law of Ukraine № 360-VI of 03.09.2008.

The given procurement of services/ works upon the Contract shall be determined free from VAT under provisions of cl.197.11 Art. 197 of the Tax Code of Ukraine. Operations for providing services under this Agreement are subject to VAT exemption.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, then the Contractor must notify GIZ of such VAT registration in writing or in electronic form by means of submission of an e-mail with copy of the Excerpt from VAT Registration Registry to the GIZ’s e-mail address indicated in the details of the Contract. The Contractor must submit the mentioned notification to the GIZ not later than 1 calendar day following the day of VAT registration.

At the same time the Parties agreed that the purchase of Services after the VAT registration of the Contractor shall be exempt from VAT in accordance with the abovementioned.

# Outsourced processing of personal data

“Not applicable”

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- CV of each proposed expert, including relevant work experience, qualifications (education, certificates, where applicable), and references or links to publications, communication materials, links to photo/video examples, and other evidence demonstrating compliance with the qualification requirements for up to 3 pages;

- Portfolio of the expert (shall be submitted for each expert) shall include the list of work samples from the media platforms, photos and links to video production for up to 10 pages;

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in the Ukrainian (language).

The complete technical bid must not exceed 7 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 0 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 2 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in the Ukrainian and English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provided according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Option

Not applicable

- Annexes

- Annex 1 – Travel regulations

Annex 1 Travel regulations (hereinafter – Regulations)

1.Business trips of experts/consultants All experts/consultants who are travelling on behalf of and commissioned by GIZ should use these Travel regulations for calculation and compensation of costs if these costs are stipulated in the Contract. For the claim of travel expenses, the experts/consultants must submit documents according to the terms of the Regulations, unless otherwise is expressly stated in the Contract. Compensation of travel expenses is carried out exclusively within the limits of the amounts for individual items fixed in the Contract. Payment of advances for business trips is possible only if it is expressly stated in the Contract.

2. Definition of a business trip A business trip, as defined by the GIZ’ general regulations governing the reimbursement of travel expense and accommodation, involves an expert/consultant temporarily working at a place other than his/her regular domicile and/or seat of business to conduct official business with GIZ's approval. The duration of a business trip (period of absence) shall be calculated as the time between departure from the place of residence or the principal place of work at the start of the business trip and the return to any of the above-mentioned places on completion of the business trip.

3. Accommodation allowance Overnight accommodation costs are reimbursed to the extent agreed in the Contract against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). Limits for overnight accommodation shall be stipulated in the Contract. Hotel reservations are made by an expert/consultant by himself/herself. For accommodation during business trips room category not higher than Standard (or equal) is to be booked, unless otherwise is expressly stated in the Contract. Overnight accommodation costs during domestic and international business trips shall not be reimbursed for business trips to a place of residence during which the expert/consultant stays in his/her own home or place where he/she maintains his/her own household. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – act of acceptance. Against evidance – copy of the original invoice from the hotel or other actual service provider with period of stay, names of guests, type and number of rooms, price per night, total amount, meals (if included). (Service fee of booking platforms is not to be reimbursed).

4. Per diem allowance The per-diem allowance covers the additional cost of subsistence to the expert/consultant during an assignment away from their regular domicile and/or seat of business and accrued if the condition of a one-day or more business trip is fulfilled. The minimum business trip time is a one-day business trip lasting 10 hours, including working hours and travel time. Per diems are paid within the amount specified in the Contract, as a lump sum. The reduced lump sum rate applies for one-day business trips lasting from 10 to 24 hours and depending on the type of meals at the hotel or the provision of meals from GIZ. The calculation of per diems for business trips depending on the type of meals is given in the Table 1 (see below). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) – timesheets in accordance with GIZ limits Against evidence – not applicable

5. Currency of reimbursement of travel expenses Reimbursements of costs of business trips within Ukraine are paid in Ukrainian Hryvnia (UAH). Reimbursements of costs of international business trips are paid in Ukrainian Hryvnia (UAH). Reimbursement of travel expenses in foreign currency (not UAH) must be made according to below mentioned: a) in accordance with the exchange rate that is indicated in bank account statement (for cashless transactions). b) in accordance with European Commission’s official monthly accounting rate, published on https://commission.europa.eu/funding-tenders/procedures-guidelines-tenders/information-contractors-and-beneficiaries/exchange-rate-inforeuro_en on the date when the financial documents (proof of evidence) was issued (for cash transactions when no bank statement is available for confirmation of the used exchange rate). c) in accordance with the exchange rate of National Bank of Ukraine https://bank.gov.ua/ua/markets/exchangerates/ (on the date when the financial documents (proof of evidence) were issued)). (In case that invoiced foreign currency is not available at the European Commission site).

6. Flights / ground transportation (train, taxi, private vehicles, car hire/car-sharing/) Costs for transportation are reimbursed within the amount specified in the Contract, against proof of performance (in case of using lump sum) or against presentation of evidence (based on original financial documents). The preferred mode of transport shall be economically efficient and environmentally friendly. GIZ is committed to the principles of resource conservation and environmental protection and therefore requires all partners to choose the most environmentally friendly means of transport. Experts/consultants shall take advantage of any price reductions (special rates etc.) that are available. If travel time by train is 5 hours or less, train transport must be preferred for economic and environmental reasons

7.1 Flights Only economy class flight tickets can be reimbursed to experts/consultants. The choice of an airline company should be based on a comparison of ticket prices. The choice of a more expensive flight should be justified by an expert/consultant (e.g. a tight travel schedule combined only with the selected flight). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.2 Trains Train tickets shall be booked and purchased by the expert/consultant by himself/herself. The ticket purchase fee is not to be reimbursed. If required, first class tickets (abbreviation in Ukraine: Л – two-seater, soft-seated, М – deluxe, single-seater, three-seater) are possible in case your journey not less than 2 hours. The decision on the class tickets is in the responsibility of traveler and should be considered based on the cost-efficiency and security reasons (e. g. overnight trip). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication.

7.3 Taxis and group private transportation If the expert/consultant uses a taxi or a group private transportation during a business trip, abroad or in Ukraine, he\she should follow the principle of economic efficiency and necessity of usage this mean of transport. The justification for such a choice should be provided together with a financial document (proof of evidence). Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - Taxi (not applicable); Group private transportation (route sheet with indication point of destination/point of arrival overall km). Against evidance – Taxi (bill or ride report or screenshot of order with price indication); Group private transportation (invoice from the actual service provider).

7.4 Private vehicles As a rule, business trips should be made by rail rather than using a private vehicle. Compensation for usage of private vehicles is allowed if such a category of costs is stipulated in the Contract. In the case of using private vehicles, GIZ compensates for such costs at a fixed rate per kilometre, using the shortest possible route (according to the calculation of the Google Maps navigator). For journeys with a one-way distance of more than 200 km, the expert/consultant must provide evidence that using a motor vehicle is more economical than other means of transport. The basis for reimbursement and for determining which means of transport is more economical is the cost of a second-class rail ticket. If a private motor vehicle is used for other important reasons (e.g. to carry heavy luggage, documents or materials, or if local transport connections are poor), convincing and adequate reasons must be set out by the expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - needs evidence by internal based calculation of route planner like Google-map or similar (13,71 UAH per 1 km which includes all expenses without exception, such as fuel etc.) Against evidance - not applicable

7.5 Buses Bus tickets must be booked and purchased independently by an expert/consultant. Contractor should provide the following documents for specific reimbursement type: Against performance (lump-sum based) - not applicable Against evidance – tickets with price indication

Table 1 / Таблиця 1

Accommodation costs in Ukraine*

*The amounts in UAH corresponding to the amounts in EUR are calculated based on the official NBU exchange rate on the date of invoice

Four oblasts of assignment represent all four categories of Ukrainian territories according to the proximity of the frontline and the main tasks during the war, namely the following: frontline, liberated, support and backline