| Skills Task Force support for labour market development and employment reforms | Project number/ cost centre: G-011831-009 (50%) G-011831-011 (50%) |
| --- | --- |

Terms of reference

- List of abbreviations

AG	Commissioning party

AN	Contractor

AVB	General terms and conditions of contract (‘local terms and conditions’) for supplying services and work on behalf of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH in Ukraine

FK	Expert

FKT	Expert days

KZFK	Short-term expert

ToRs	Terms of reference

GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH

CMU 	 Cabinet of Ministers of Ukraine

MoES	Ministry of Education and Science of Ukraine

MoEU	Ministry of economy, environment and agriculture of Ukraine

NQA	National Qualification Agency

SES	State Employment Service of Ukraine

VET 	Vocational Education and Training

MDI 	Multi Donor Initiative

- Context

Ukraine is suffering from a catastrophic humanitarian crisis, enormous damage to its social and economic infrastructure and a sharp economic decline caused by the Russian war. The future development is currently unpredictable, but a post-war scenario has full attention on the rebuilding process. The Federal German Ministry for Economic Cooperation and Development (BMZ) assigned GIZ to develop the Programme “Vocational education in Ukraine / Skills4Recovery” in 2023. In 2024 new partners joined to the programme and more funds were granted. The Multi Donor Initiative Skills4Recovery (here and after, the Programme or MDI) is financed by the European Union, Germany, Poland, and Estonia. It is implemented by Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) and the Solidarity Fund PL (SFPL). Since 2025 the Danish co-financing is being integrated one-to-one into the existing outputs (content integration) and used to scale the value addition with special focus on agricultural sector and aimed on helping vulnerable groups such as women, ex-combatants, people with disabilities, IDPs for inclusive economic recovery.

The programme's objective is to increase the availability of qualified workforce for the Ukrainian recovery. The provision of qualified workforce in sufficient volume is based on creating adequate educational opportunities for people of all working age – this includes initial education for young people and further education for adults. It is expected that the educational system will activate different social groups for employment, such as internally displaced persons, veterans, returnees, and women.

Key outputs of the Multi Donor Initiative are:

- Institutional Strengthening of training providers

- Implementation of training programmes

- Support of transition to labour market

- Development of political and strategic concepts according to labour market needs

- Replication of best practices throughout Ukraine.

Key partners of the project are the Ministry of Education and Science of Ukraine (MoES), the Ministry of Economy of Ukraine (MoEU), National Qualification Agency (NQA), State Employment Center of Ukraine (SEC), regional state/military administrations, VET providers, employment organizations and employers’ representatives.

An active phase of reforms is currently underway in Ukraine’s vocational education and labour market sectors. The Law of Ukraine “On Vocational Education” dated 21 August 2025 No. 4574 has entered into force. In addition, the Employment Strategy of Ukraine for the period up to 2030 and its Operational Action Plan for 2026-2028 were approved by Cabinet of Ministers of Ukraine Resolution No. 92-r dated 7 January 2026 and the Labour Code of Ukraine have been adopted. Together, these reforms represent a significant update of the legislative and strategic framework for human capital development and labour market regulation.

Taken together, these documents form a coherent framework that sets new policy trajectories for human capital development and labour market regulation in the context of war, demographic challenges, digital transformation, structural economic change, and EU alignment.

Against this background, there is a need for comprehensive expert support to facilitate the implementation of ongoing reforms, strengthen the legislative and institutional framework, and ensure that policy development is evidence-based, coordinated among relevant stakeholders, and aligned with national priorities and the EU acquis. In addition, addressing rapidly changing labour market needs requires the development of innovative policy instruments, the design of practical and forward-looking solutions, and the application of adaptive approaches that foster institutional innovation, improve policy effectiveness, and support the successful implementation of reforms.

- Tasks to be performed by the contractor

The objective of this assignment is to provide comprehensive legislative, regulatory and policy support for the development and implementation of labour market, employment and skills reforms in Ukraine, including strengthening the institutional and regulatory framework in line with national reform priorities and the EU acquis. The assignment will be implemented through the Skills Task Force, working in close cooperation with the MoEU, MoES, NQA, SES and GIZ to ensure continuous expert support, policy dialogue and coordinated reform implementation.

The requested expert support may be summarised as follows:

- facilitating policy dialogue, coordination and implementation of labour market and skills reforms in cooperation with the Ministry of Economy of Ukraine;

- supporting the preparation, revision and approximation of legislation, secondary legislation and policy documents in line with the EU acquis and national reform priorities;

- providing continuous expert, analytical and methodological support, including stakeholder consultations, to advance labour market governance and employment policies.

  - Tasks

The contractor is responsible for providing the following services:

- Establish, conduct and facilitate minimum 3 regular meetings with the Ministry and GIZ teams to clarify objectives, expected outputs, timelines, and implementation arrangements, and develop a work plan for the assignment.

- Conduct a review and gap analysis of all existing legislation, regulations, and policy documents related to employment, labour market governance, reskilling and upskilling.

- Based on the results of conducted gap analysis develop at least 2 policy recommendations for improving the legislative, regulatory, frameworks related to reskilling, upskilling, employment promotion, labour market participation, active labour market programmes, skills development, lifelong learning, and inclusion.

- Draft at least 4 new legal documents and/or revise existing normative acts (together with accompanying documents according to the regulations of the CMU) including laws, government resolutions, ministerial orders, methodologies, procedures, and guidelines, and provide expert support throughout the refinement and adoption process by the relevant public authorities, including the facilitation of at least 3 online stakeholder consultation sessions.

- Provide expert legal and policy advice, analytical inputs, and methodological recommendations upon request of the Ministry and GIZ teams (at least 3 analytical notes/ methodological recommendations), including support for the implementation of labour market reforms and alignment with EU integration priorities

- Provide regular reporting in English and Ukrainian in accordance with GIZ requirements and submit analytical notes, draft documents, meeting summaries, progress reports, and other deliverables requested under the assignment.

•	The contractor is responsible for selecting, preparing, training and steering the international and national, short and long-term experts assigned to perform the advisory tasks.

•	The contractor provides equipment and supplies (consumables) and assumes the associated operating and administrative costs.

•	The contractor manages costs and expenditures, accounting processes and invoicing in line with the requirements of GIZ.(The contractor reports regularly to GIZ in accordance with the current AVB of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH.

Technical details to be considered

The contractor shall ensure that all written deliverables are of high professional quality, including correct grammar, spelling, punctuation, linguistic consistency, completeness, accuracy of information, appropriate referencing where applicable, and compliance with the agreed format. GIZ reserves the right to reject deliverables that do not meet these quality requirements and to request revisions at the contractor's expense.

Due to the sensitivity of the information processed under this assignment, the contractor shall not use artificial intelligence tools or any other software that transfers input data to external service providers or third parties unless explicitly authorised by the contracting party.

All deliverables shall be prepared in close consultation with the Ministry of Economy of Ukraine and GIZ, taking into account comments received during the drafting process and ensuring consistency with national reform priorities, applicable legislation, and relevant EU acquis.

Certain milestones, as laid out in the table below, are to be achieved during the contract term:

| Milestones/process steps/partial services | Anticipated deadline/place/person responsible |
| --- | --- |
| 1. Establish and conduct minimum 3 meetings with the Ministry of Economy of Ukraine and GIZ teams to clarify objectives, expected outputs, timelines, implementation arrangements (Task 1). | 15 December 2026, Kyiv city (online), the contractor |
| 2. Conduct a review and gap analysis of the existing legislative and policy framework related to employment, labour market governance, skills development, VET, active labour market programmes, and the State Employment Service, and prepare recommendations for improving the legislative and institutional framework (Tasks 2-3). | 31 October 2026, Kyiv city (online), the contractor |
| 3. Prepare draft legal and policy documents; facilitate continuous stakeholder consultations and policy dialogue; provide on-demand expert legal, policy, and methodological support to the Ministry of Economy and GIZ for the implementation of labour market, employment, and skills development reforms (Tasks 4-5). | 30 November 2026, Kyiv city (online), the contractor |
| 4. Provide regular reporting in English and Ukrainian, including analytical notes, draft legal documents, meeting summaries, progress reports, final report, and other requested deliverables (Task 6). | 15 December 2026, Kyiv city (online), the contractor |

Period of assignment is from 30.08.2026 till 31.12.2026.

  - Deliverables and Reporting:

The Contractor will be responsible for the following:

| Reporting/ Deliverable # | Requirements to the format | Anticipated period, by |
| --- | --- | --- |
| - Agendas of at least 3 meetings, at least 2 policy recommendations including results of gap analysis after reviewing the existing legislative, regulatory, and policy framework related to employment, labour market governance, skills development, vocational education and training (VET), active labour market programmes, lifelong learning, and the functioning of the State Employment Service, including alignment with relevant EU acquis and reform priorities (Tasks 1-3). | Documentation in English and Ukrainian, submitted in DOCX and PDF formats via email to GIZ, from 10,000 symbols to no length limits. Each document should be accompanied with: - Power Point presentation from 5 to 10 slides; - 1 page resume (Word). | 15 December 2026 |
| 2. At least 4 draft legal, regulatory, and policy documents, including draft laws, Government resolutions, ministerial orders, methodologies, procedures, guidelines, explanatory notes, presentations, and other implementation documents prepared or revised to support labour market, employment, skills development, and VET reforms (Task 4). | Documentation in English and Ukrainian, submitted in DOCX and PDF formats via email to GIZ, from 5,000 symbols to no length limits. | 30 November 2026 |
| 3. Minutes of at least 3 online meetings/events, including summaries of expert consultations, workshops / working group meetings /policy dialogue conducted with the MoEU, the State Employment Service and other stakeholders (Task 5). | Documentation in English and Ukrainian, submitted in DOCX and PDF formats via email to GIZ, from 5,000 symbols to no length limits. | 31 December 2026 |
| 4. At least 3 analytical notes/methodological recommendations prepared upon request of the MoEU and GIZ to support policy development (Task 5). | Documentation in English and Ukrainian, submitted in DOCX and PDF formats via email to GIZ, from 10,000 symbols to no length limits. Each document should be accompanied with: - Power Point presentation from 5 to 10 slides; - 1 page resume (Word). | 30 November 2026 |
| 5. Final report summarising the implementation of all assignment tasks, key outputs, analytical findings, recommendations (Task 6). | Documentation in English and Ukrainian, submitted in DOCX and PDF formats via email to GIZ, from 10,000 symbols to no length limits. Document should be accompanied with: - Power Point presentation from 5 to 10 slides; - 1 page resume (Word). | 15 December 2026 |

- Concept (technical-methodological design)

In the bid, the tenderer is required to show how the objectives defined in Chapter 2 (Tasks to be performed) are to be achieved, if applicable under consideration of further method-related requirements (technical-methodological concept). In addition, the tenderer must describe the project management system for service provision.

Note: The numbers in parentheses correspond to the lines of the technical assessment grid.

## Technical-methodological concept

Strategy (1.1): The tenderer is required to consider the tasks to be performed with reference to the objectives of the services put out to tender (see Chapter 1 Context) (1.1.1). Following this, the tenderer presents and justifies the explicit strategy with which it intends to provide the services for which it is responsible (see Chapter 2 Tasks to be performed) (1.1.2).

The tenderer is required to present the actors relevant for the services for which it is responsible and describe the cooperation (1.2) with them.

The tenderer is required to present and explain its approach to steering the measures with the project partners (1.3.1) and its contribution to the results-based monitoring system (1.3.2).

The tenderer is required to describe the key processes for the services for which it is responsible and create an operational plan or schedule (1.4.1) that describes how the services according to Chapter 2 (Tasks to be performed by the contractor) are to be provided. In particular, the tenderer is required to describe the necessary work steps and, if applicable, take account of the milestones and contributions of other actors (partner contributions) in accordance with Chapter 2 (Tasks to be performed) (1.4.2).

The tenderer is required to describe its contribution to knowledge management for the partner (1.5.1) and GIZ and to promote scaling-up effects (1.5.2) under learning and innovation.

## Project management of the contractor (1.6)

The tenderer is required to explain its approach for coordination with the GIZ project. In particular, the project management requirements specified in Chapter 2 (Tasks to be performed by the contractor) must be explained in detail.

The tenderer is required to draw up a personnel assignment plan with explanatory notes that lists all the experts proposed in the tender; the plan includes information on assignment dates (duration and expert months) and locations of the individual members of the team complete with the allocation of work steps as set out in the schedule.

The tenderer is required to describe its backstopping concept. The following services are part of the standard backstopping package, which (like ancillary personnel costs) must be factored into the fee schedules of the staff listed in the tender in accordance with Section 3.3.1 of the GIZ AVB:

- Service-delivery control

- Managing adaptations to changing conditions

- Ensuring the flow of information between the tenderer and GIZ

- Assuming personnel responsibility for the contractor’s experts

## Further requirements (1.7)

Not applicable.

- Personnel concept (proposed staff)

The Contractor is required to provide personnel who are suited to filling the positions described, on the basis of their CVs (see Chapter 10), the range of tasks involved and the required qualifications.

If the Contractor provides fewer experts than the number of positions described, the experts will be assessed for all requirements and qualifications for all positions they are intended to cover.

The below specified qualifications represent the requirements to reach the maximum number of points in the technical assessment.

## Team leader

Tasks of the team leader

- Overall responsibility for the advisory packages of the contractor (quality and deadlines)

- Coordinating and ensuring communication with GIZ, partners and others involved in the project

- Personnel management, in particular identifying the need for short-term assignments within the available budget, as well as planning and steering assignments and supporting local and international short-term experts

- Regular reporting in accordance with deadlines

Qualifications of the team leader

- Education/training (2.1.1): university degree Master/Specialist in law or management or political science

- Language (2.1.2): C1-level language proficiency in English

- General professional experience (2.1.3): 7 years of professional experience in the legislative consulting and policy advisory sector

- Specific professional experience (2.1.4): 5 years in strategic management and cooperation for government institutions

- Leadership/management experience (2.1.5): 7 years of management/leadership experience as project team leader or manager in a company

- Regional experience (2.1.6): 5 years of experience in policy development and/or regulatory reform projects in Ukraine, of which 2 years in projects at the national level

- Development cooperation (DC) experience (2.1.7): 5 years of experience in DC projects

- Other (2.1.8): 1 case of legal drafting, particularly in the field of labour market or public-private partnerships or VET sector reforms.

## Short-term expert pool with minimum 3, maximum 4 members

For the technical assessment, an average of the qualifications of all specified members of the expert pool is calculated. Please send a CV for each pool member (see below Chapter 10 Requirements on the format of the bid) for the assessment.

Tasks of the short-term expert pool

- Responsibility for working with advisory requests from political partners and GIZ

- Taking part in the regular meeting with the MoEU

- Performing advisory work in time and in the highest quality for achieving the objective and tasks of the assignment (cl.2 Tasks #1-6)

- Coordinating and communication with technical specialists of political partners

- Ensuring compliance and knowledge sharing, sustainability of results, dissemination of deliverables

- Regular reporting in accordance with deadlines

Qualifications of the short-term expert pool:

- Education/training (2.6.1): all experts with university degree Master/Specialist in law or management or political science or economy or IT sector

- Language (2.6.2): all experts with B1-level language proficiency in English

- General professional experience (2.6.3): all experts with 7 years of professional experience in the legislative consulting and policy advisory sector.

- Specific professional experience (2.6.4): all experts with 5 years in consultancy and/or legal advisory sector or scientific research of economy, labour market, VET education and skills validation.

- Regional experience (2.6.5): all experts with 3 years of experience in policy development and/or regulatory reform projects in Ukraine.

- Development cooperation (DC) experience (2.6.6): all experts with 2 years of experience in DC projects

- Other (2.6.7): all experts with 1 case of legal drafting, particularly in the field of labour market or public-private partnerships or VET sector reforms.

# Costing requirements

Assignment of personnel and travel expenses Travels are not foreseen

Specification of inputs

## Сontracts for services:

| Fee days | Unit of measurement | Number of experts | Total number of days | Comments (if any) |
| --- | --- | --- | --- | --- |
| ## Designation of Team leader | Expert-days | 1 | 38 |  |
| Designation of Short-term expert pool | Expert-days | 4 | 120 |  |

There is no contractual obligations to use up the full days/travel or budgets. The number of days/travel and the budgets will be contractually agreed as maximum amounts.

# Inputs of GIZ or other actors

Not Applicable

- Financial provisions

  - Contract value

The contract value shall be calculated according to the format of the financial bid (price schedule).

  - Financial bid (price schedule)

The total cost of the Contract is set in UAH, including all direct and related expenses, taxes and fees, but incl. VAT.

All costs connected to the contract implementation, e.g. connected management staff, should be covered according to the received amount of the total value of the Contract. No additional budget lines are allowed.

  - Payment Conditions

- The Contractor shall be paid 100% post payment upon performance on quarterly basis;

- All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

- All the activities shall be done exclusively within the timeframe of the Contract;

- All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF) and timesheets, submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment

  - Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF) and timesheets, etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract.

- Each invoice and act of acceptance shall contain the Project Number, contract number and the percentage for cost split as follows (if applicable):

- G-011831-009 (50%)

- G-011831-011 (50%)

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Timesheet standard template can be found here https://www.giz.de/sites/default/files/media/els-document/2025-09/time-record-template-days-and-hourly.xls

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

- Other Provisions

  - General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH and Supplements to General Terms of contract governing Contracts with Appraisers/Firms of Consultants (local) published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from GIZ side responsible for contract implementation and communication with the Contractor _______ (indicate name/-s, surname/-s, phone/-s, e-mail/-s) (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation)

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

  - VAT Exemption

Not Applicable

# Outsourced processing of personal data

# Not Applicable.

- Requirements to the format of the bid

  - Documents to be submitted

    - Technical bid

Tenderers must provide the following documents:

- a technical bid containing a description of the methodology proposed in relation to the identified tasks. Technical bid must be signed and stamped (if stamp is used);

- tentative work plan;

- personnel (team) concept

- CVs of all experts with relevant work experience, qualifications (education, certificates).

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English (language).

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The CVs of the personnel proposed in accordance with Chapter 4 of the ToRs must be submitted using the format specified in the terms and conditions for application (if such format of CV is set). The CVs shall not exceed 4 pages each. They must clearly show the position and job the proposed person held in the reference project and for how long. The CVs must be drawn up in English (language).

The technical bid must not include any financial information such as daily fees for experts or any other payments. Otherwise, the bid will be disqualified.

    - Financial bid (Price schedule)

The financial bid must include the costs associated with the implementation of the assignment and must be provided according to the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped (if stamp is used).

    - Registration documents of the tenderer

Shall be provide according to the requirements of tender documentation

The tenderer must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

- Annexes

Annex 1 - List of key experts