| Development of a Pre-Feasibility Study (Pre-FS) for the Technical Re-equipment of a Large Boiler House into a Multi-Fuel CHP Plant with a Capacity of 15–88 MWth and up to 25 MWe, including the Interconnection of Five Boiler Houses, Cherkasy. | Project number/ cost centre: G-012485-014 |
| --- | --- |

# List of abbreviations

| Abbreviation | Definition |
| --- | --- |
| AG | Auftraggeber / Commissioning party (GIZ) |
| AN | Auftragnehmer / Contractor |
| AVB | Allgemeine Vertragsbedingungen / General Terms and Conditions of Contract (GIZ Ukraine) |
| BAT | Best Available Techniques |
| CAPEX | Capital Expenditures |
| CEMS | Continuous Emissions Monitoring System |
| CHP | Combined Heat and Power |
| CO₂ | Carbon Dioxide |
| DBN | Державні будівельні норми України / State Building Codes of Ukraine |
| DH | District Heating |
| DOCX | Microsoft Word Document Format |
| E&S | Environmental and Social |
| EUR | Euro |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit GmbH |
| IRR | Internal Rate of Return |
| LCOE | Levelized Cost of Electricity |
| LCOH | Levelized Cost of Heat |
| MWe | Megawatt electrical |
| MWth | Megawatt thermal |
| NPV | Net Present Value |
| OPEX | Operational Expenditures |
| PDF | Portable Document Format |
| Pre-FS | Pre-Feasibility Study / попереднє техніко-економічне обґрунтування (пре-ТЕО) |
| RDF | Refuse-Derived Fuel |
| SCADA | Supervisory Control and Data Acquisition |
| TOR / ToR | Terms of Reference |
| UAH | Ukrainian Hryvnia |
| VAT | Value-Added Tax |
| WtE | Waste-to-Energy |

# 1. Context

The project “Bilateral Climate and Energy Partnerships” (hereinafter referred to as the Project / Secretariat of the German-Ukrainian Energy Partnership) supports the German Federal Ministry for Economic Affairs and Energy (BMWE) in the implementation of the Energy Partnership (EP) between Germany and Ukraine.

The Energy Partnership (EP) between Germany and Ukraine was launched in 2020 to establish a platform for high level dialogue and cooperation between the two countries in bilateral energy cooperation. The EP provides an umbrella for collaboration by different stakeholders on key topics such as energy efficiency, renewable energy, electricity markets, decarbonisation of industry under the overarching aim of mutual energy security and trade promotion.

Given the importance of the heating sector both in emergency response during winter and in Ukraine’s decarbonisation path, as well as the potential for economic cooperation in this area, the Secretariat of the EP joined forces with ReWarm project for implementation of a pilot study in the heating sector.

The Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH implements the project “Reforming the District Heating Sector of Ukraine” (ReWarm). The project supports the sustainable transformation of Ukraine’s district heating sector by contributing to sector reform, strengthening municipal energy planning, supporting district heating utilities, and preparing technically, economically and environmentally viable modernisation measures.

ReWarm promotes improvements in energy efficiency, reduction of greenhouse gas emissions, diversification of energy sources, increased use of renewable and locally available fuels, and greater resilience of municipal heat supply systems. The project also supports Ukrainian municipalities and district heating utilities in developing practical investment-preparation measures that can contribute to the climate-friendly reconstruction and long-term modernisation of the heating sector.

Within the framework of ReWarm, GIZ is supporting the City of Cherkasy and the municipal district heating utility, Communal Enterprise of Heat Networks “Cherkasyteplokomunenergo”, in preparing priority measures for the modernisation and decarbonisation of the city’s district heating system.

Cherkasyteplokomunenergo operates one of the largest district heating systems in central Ukraine. The system currently relies predominantly on natural gas and is exposed to fuel-price volatility, supply risks, ageing infrastructure, and greenhouse-gas emissions. The city intends to assess a structural transition toward locally available fuels and a more resilient district heating configuration.

The investment concept concerns the technical re-equipment of a large boiler house into a multi-fuel Combined Heat and Power (CHP) plant with an indicative configuration range of 15–88 MWth and up to 25 MWe. The concept includes biomass and RDF use, feedstock preparation and storage, advanced flue-gas cleaning, SCADA-based automation, and the interconnection of five nearby boiler houses through a ring-main district-heating network.

The present assignment is implemented as a joint activity of the Energy Partnership project and the ReWarm project and is limited to the preparation of a Pre-Feasibility Study. It shall compare technically and financially credible configurations, identify the preferred concept, quantify environmental and climate effects, and define a phased roadmap for the subsequent full Feasibility Study and design stages.

Detailed design documentation, bills of quantities for construction tendering, submission to State Expertise, permitting procedures, procurement of equipment, construction works and investment financing are outside the scope of this contract. Preparation of the Pre-Feasibility Study under this assignment does not constitute a commitment by GIZ, the Energy Partnership project or the ReWarm project to finance the subsequent implementation of the proposed investment.

# 2. Tasks to be performed by the contractor

## 2.1 Tasks

The Contractor shall provide works of the development of a Pre-Feasibility Study (Pre-FS) for the technical re-equipment of a large boiler house in Cherkasy into a multi-fuel CHP plant with a capacity range of 15–88 MWth and up to 25 MWe, including the interconnection of five boiler houses through a ring-main district-heating network.

The Contractor shall manage costs and expenditures, accounting processes, reporting, and invoicing in line with GIZ requirements and the applicable AVB.

### Stage 1 – Inception, data review and baseline validation

• Kick-off meeting with GIZ, the municipality, and Cherkasyteplokomunenergo;

• Review of available technical, operational, environmental, fuel-supply, and network data;

• Preparation of a structured data-gap list and requests for supplementary information, including a preliminary demand forecast based on available data and transparent assumptions (current demand, expected demand in the next 25 years based on implementation of individual heat substations, billing by individual metered heat consumption, improvements of the grids, reduction of water losses, global warming, etc.);

• Validation of the baseline: existing heat generation, seasonal load profiles, network constraints, natural-gas consumption, and emissions;

• Stakeholder map and consultation plan covering utility representatives, municipal authorities, grid operators, and waste-management actors;

• Inception report with detailed methodology, work plan, and risk register;

Initial site visit, travel and inception workshop package.

### Stage 2 – Comparative technical Pre-Feasibility Study

• Development and comparison of at least 2–3 technically viable project scenarios, including phased implementation options;

• Assessment of multi-fuel CHP configurations using biomass, RDF, or calculated fuel blends, including the indicative range of 15–88 MWth and up to 25 MWe. At least one scenario shall be designed as a maximum decarbonisation / fossil-free heat generation scenario, with the remaining emissions transparently quantified;

• Comparison of turbine arrangements, including one combined turbine and a two-turbine configuration for seasonal flexibility;

• Assessment of feedstock preparation, storage, quality-control, and logistics requirements, including RDF volumes of approximately 120,000 t/year and seasonal biomass availability;

• Preliminary thermal and electrical energy balances, load-duration analysis, and evaluation of operational modes;

• Preliminary hydraulic assessment of the ring-main interconnection of five boiler houses, including comparison of Ukrainian and European design approaches;

• Assessment of flue-gas cleaning configurations, continuous emissions monitoring, and compliance pathways with Ukrainian requirements and EU-aligned BAT principles;

• Assessment of SCADA, automation, digital monitoring, and future integration of heat pumps or solar-thermal solutions;

• Order-of-magnitude CAPEX estimates for the principal investment packages.

### Stage 3 – Environmental, financial and implementation roadmap package

• Preparation of the comparative financial model with CAPEX, OPEX, revenues, payback period, NPV, IRR, LCOH, and LCOE;

• Sensitivity analysis for fuel prices, tariff assumptions, RDF-gate fee assumptions where applicable, financing parameters, and phased implementation;

• Calculation of natural-gas substitution, CO₂ reduction, and methane-avoidance effects using transparent assumptions and emission factors;

• Preliminary Environmental and Climate Safeguards Summary for each scenario;

• Risk analysis covering fuel supply, permitting, technology integration, network implementation, market assumptions, and institutional capacity;

• Preparation of a phased implementation roadmap, including the scope of the subsequent full Feasibility Study, required surveys, permitting steps, and design packages;

• Identification of potential financing pathways and preparation steps for subsequent investment planning.

• Preparation of a non-exhaustive market overview of relevant German, European and Ukrainian technologies, suppliers and products potentially applicable to the proposed investment, without pre-selection or recommendation of any specific supplier for future procurement.

### Stage 4 – Stakeholder workshop, revisions and final Pre-FS report

• Preparation and implementation of one multi-stakeholder workshop to present and discuss findings;

• Collection and documentation of stakeholder comments, with an issues-and-response matrix;

• Finalisation of the Pre-FS report and financial model;

• Preparation of an executive presentation for the municipality, GIZ, and project partners, as well as one presentation for sector experts explaining the approach and serving as a best-practice example.

Place of performance: Cherkasy, Ukraine for stakeholders, Contractor will provide online. Additional technical requirements are provided in Annex 1 – Technical Specifications for the development of a Pre-Feasibility Study (Pre-FS).

| Milestones/partial works | Anticipated deadline/place/person responsible | Criteria for acceptance |
| --- | --- | --- |
| Stage 1. Inception, data review and baseline validation | Within 3 weeks from contract signing / Contractor | Inception report; validated baseline; data-gap list; stakeholder map; work plan and risk register approved by GIZ. |
| Stage 2. Comparative technical Pre-FS | Within 10 weeks from contract signing / Contractor | Comparative technical package covering 2–3 scenarios, energy balances, ring-network options, fuel logistics, emissions control, and preliminary CAPEX. |
| Stage 3. Environmental, financial and implementation roadmap package | Within 14 weeks from contract signing / Contractor | Financial model; safeguards summary; sensitivity analysis; risk analysis; implementation roadmap and financing pathways. |
| Stage 4. Stakeholder workshop, revisions and final Pre-FS report | Within 16 weeks from contract signing / Contractor | Workshop conducted; comments incorporated; final Pre-FS report, executive presentation, sector expert presentation, editable model, and issues-and-response matrix submitted. |

The contract duration is from 15.09.2026 till 31.01.2028from contract signing.

## 2.2 Deliverables and Reporting

The Contractor will be responsible for the following:

| # | Reporting/Deliverable | Requirements to the format | Anticipated period, by |
| --- | --- | --- | --- |
| 1 | Inception report: baseline review, data-gap list, stakeholder map, methodology, operational plan, and risk register | PDF and DOCX; EN; report with annexes | Within 3 weeks from contract signing |
| 2 | Comparative technical Pre-FS package with at least 2–3 scenarios: CHP configuration, turbine options, RDF/biomass logistics, ring-network options, flue-gas treatment, automation, and preliminary CAPEX | PDF and DOCX; EN; editable calculations in Excel | Within 10 weeks from contract signing |
| 3 | Environmental, financial and implementation roadmap package: financial model, sensitivity analysis, safeguards summaries, climate indicators, risk analysis, financing pathways, and next-stage scope | PDF and DOCX; editable Excel model; EN | Within 14 weeks from contract signing |
| 4 | Final Pre-FS report, executive presentation, sector expert presentation, stakeholder workshop materials, and issues-and-response matrix | PDF, DOCX, XLSX, PPTX/PDF; final Pre-FS report in EN and UA; executive summaries and workshop/sector presentations in EN and UA; other materials in EN | Within 16 weeks from contract signing |

In addition to the deliverables listed above, the Contractor shall submit short monthly progress reports to GIZ. Each report shall specify completed activities, progress against milestones, identified risks, data gaps, pending decisions, and planned activities for the next period.

All final deliverables shall be submitted in English. Executive summaries and workshop presentations shall be provided in English and Ukrainian. The final Pre-FS report shall be submitted in English and Ukrainian. All final deliverables shall be submitted electronically in editable and PDF formats. Four hard copies of the final Pre-FS report shall be provided if requested by GIZ.

### General activities

• Maintain regular coordination with GIZ, the municipality of Cherkasy, and Cherkasyteplokomunenergo through online and in-person meetings as required;

• Prepare concise meeting minutes and maintain an issues-and-decisions log;

• Implement internal quality assurance and peer review before submission of deliverables;

• Conduct one knowledge-transfer session as part of the stakeholder workshop;

• The Contractor shall hand over all calculations, models, maps and planning files developed under this assignment in an accessible digital structure. Third-party proprietary tools, licensed datasets and background materials not created under this assignment are excluded, unless transfer is legally permitted.

# 3. Concept (technical-methodological design)

In the bid, the tenderer is required to demonstrate how the objectives defined in Chapter 2 are to be achieved. The proposal shall be structured according to the positively weighted criteria in the technical assessment grid.

## Strategy (1.1)

• Interpretation of the objectives and critical examination of the tasks (1.1.1): demonstrate understanding of the early-stage Pre-FS scope, the scale of the CHP concept, the multi-fuel challenge, the network-integration challenge, and the limits of the assignment;

• Description and justification of the contractor’s strategy (1.1.2): explain the sequence from baseline validation to scenario comparison, financial modelling, safeguards screening, roadmap development, and stakeholder validation.

## Relevant actors and cooperation (1.2)

• Identify the municipality, Cherkasyteplokomunenergo, waste-management stakeholders, biomass suppliers, heat and electricity grid operators, environmental authorities, and potential implementation partners (1.2.1);

• Describe a practical cooperation strategy, including consultations, issue tracking, and timely feedback (1.2.2).

## Steering and results-based monitoring (1.3)

The tenderer shall explain how progress will be monitored against milestones, how risks and data gaps will be escalated, and how decisions will be documented and validated with GIZ and project partners.

Approach for monitoring progress against milestones, escalating risks and data gaps, and documenting decisions with GIZ and project partners (1.3.1)

Description of results monitoring arrangements and handling of challenges related to data availability, assumptions, and stakeholder validation (1.3.2)

## Operational plan (1.4)

The tenderer shall provide a work plan and schedule showing the logical sequence of activities, responsibilities, assignment locations, quality-control steps, consultations, and the preparation of each deliverable.

Presentation and explanation of the implementation plan: work steps, milestones, schedule, responsibilities, locations, quality-control steps, consultations, and deliverables (1.4.1)

Presentation and explanation of how partner inputs, available data, data gaps, and transparent assumptions will be integrated into the Pre-FS  (1.4.2)

## Knowledge management and learning (1.5)

The tenderer shall explain how findings, calculation assumptions, and lessons learned will be transferred to the utility and documented for replication in other Ukrainian cities.

Approach for transferring findings, calculation assumptions, models, lessons learned, and digital files to the utility and GIZ (1.5.1)

Approach for documenting replication potential and presenting the Pre-FS approach as a best-practice example for sector experts (1.5.2)

## Project management of the contractor (1.6)

• Management and coordination structure, including an organisational chart and reporting lines;

• Quality assurance, peer review, monitoring, and reporting arrangements;

• Backstopping and administrative support concept.

Management and coordination structure, including reporting lines and coordination with GIZ, the municipality, and Cherkasyteplokomunenergo (1.6.1)

Personnel assignment plan showing who performs which work steps and when, including allocation of expert days to Pre-FS tasks (1.6.2)

Quality assurance, peer review, backstopping, and administrative support concept (1.6.3)

## Further requirements – Environmental and climate safeguards (1.7)

• Quantify expected fossil-fuel substitution, CO₂ reductions, and methane-avoidance effects using transparent assumptions;

• Describe the preliminary handling routes for ash, flue-gas residues, and other by-products;

• Assess climate resilience, environmental risks, and permitting considerations for each scenario.

# 4. Personnel concept (proposed staff)

The Contractor shall provide personnel suited to the positions described below. If fewer experts are proposed than positions listed, the proposed experts will be assessed against all requirements of the positions they are intended to cover. The qualifications below represent the requirements for achieving the maximum technical score.

## Team Leader / CHP Project Manager

Tasks:

- Overall responsibility for quality, deadlines, coordination, and reporting;

- Coordination of the Pre-FS methodology and consolidation of technical, environmental, and financial inputs;

- Stakeholder consultations and presentation of results;

- Quality assurance and final approval of deliverables.

- Plan, organise and conduct the stakeholder workshop and the sector-expert presentation, including preparation of the agenda, presentation and working materials, facilitation of discussions, documentation of comments, preparation of minutes and participant lists, and follow-up through an issues-and-response matrix.

Qualifications:

• Education/training (2.1.1): Master’s degree in energy engineering, mechanical engineering, civil engineering, or related technical field;

• Language (2.1.2): B1 level in English (CEFR);

• General professional experience (2.1.3): 10 years of professional experience in energy infrastructure or utilities;

• Specific professional experience (2.1.4): 5 years of experience managing feasibility studies, CHP, district-heating, or renewable-energy projects;

• Leadership/management experience (2.1.5): 3 years of leadership experience.

- Regional experience (2.1.6): 10 years of experience in Ukraine.

- 3 years of stakeholder coordination experience, (2.1.7).

## Key Expert 1: CHP / Thermal Systems Engineer

Tasks:

• Assessment of baseline heat loads and operational modes;

• Development of multi-fuel CHP configurations;

• Preparation of heat and mass balances;

• Assessment of thermal-storage and renewable-integration options;

• Contribution to CAPEX and implementation roadmap.

Qualifications:

• Education/training (2.2.1): Master’s degree in thermal-power engineering or related discipline;

• General professional experience (2.2.3): 7 years of experience in CHP, boiler-house modernisation, or district heating;

- Specific professional experience (2.2.4): 5 years of heat-load assessment, multi-fuel CHP configurations, heat and mass balances, thermal storage and renewable integration.

- Regional experience (2.2.6): 5 years of experience in Ukraine.

## Key Expert 2: WtE and Turbine Technology Specialist

Tasks:

• Assessment of RDF-based WtE solutions;

• Comparison of turbine configurations and seasonal operating modes;

• Assessment of technology readiness, efficiency, and key interfaces;

• Contribution to preliminary CAPEX estimates and risks.

Qualifications:

• Education/training (2.3.1): Master’s degree  in thermal-power engineering, mechanical engineering, or related discipline;

• General professional experience (2.3.3): 7 years of relevant experience in design documentation development in DH network;

• Specific professional experience (2.3.4): Demonstrated experience with WtE, steam-cycle, or industrial CHP projects (3 similar projects).

- Regional experience (2.3.6): 3 years Ukrainian or European DH network design approaches

## Key Expert 3: District Heating Network / Hydraulics Specialist

Tasks:

• Preliminary hydraulic analysis of the ring-main network interconnecting five boiler houses;

• Comparison of Ukrainian and European network-design approaches;

• Assessment of routing, pumping, and integration risks;

• Contribution to preliminary CAPEX.

Qualifications:

• Education/training (2.4.1): Master’s degree in heat-supply engineering, hydraulics, or related field;

• General professional experience (2.4.3): 7 years of experience with district-heating networks;

• Specific professional experience (2.4.4): Experience in hydraulic modelling and network-modernisation studies (3 similar projects).

- Regional experience (2.4.6): 3 years Ukrainian or European DH network design approaches

## Key Expert 4: RDF / Biomass Logistics Specialist

Tasks:

• Assessment of RDF and biomass availability, quality, and seasonal variability;

• Feedstock preparation, storage, mixing, and handling concept;

• Logistics analysis and risk assessment;

• Contribution to OPEX model.

Qualifications:

• Education/training (2.5.1): Master’s degree in energy, logistics, waste management, or related discipline;

• General professional experience (2.5.3): 5 years of relevant experience in design documentation development in DH network;

• Specific professional experience (2.5.4): Experience with biomass and/or RDF supply chains (3 similar projects).

- Regional experience (2.5.6): 3 years Ukrainian or European DH network design approaches

## Key Expert 5: Electrical, Grid and SCADA Specialist

Tasks:

• Assessment of electrical integration and auxiliary loads;

• Preliminary grid-interface and SCADA concept;

• Assessment of automation, metering, digital monitoring, and dispatching requirements;

• Contribution to CAPEX and risk analysis.

Qualifications:

• Education/training (2.6.1): Master’s degree in electrical engineering, automation, or related discipline;

• General professional experience (2.6.3): 6 years of relevant experience in design documentation development  in DH network;

• Specific professional experience (2.6.4): Experience with industrial energy systems and SCADA (3 relevant projects).

- Regional experience (2.6.5): 3 years Ukrainian or European DH network design approaches

## Key Expert 6: Environmental, BAT and E&S Specialist

Tasks:

• Assessment of emissions-control options and BAT alignment;

• Calculation of CO₂ and methane effects;

• Preliminary environmental and climate safeguards summaries;

• Assessment of by-products, residues, and permitting pathways.

Qualifications:

• Education/training (2.7.1): Master’s degree in environmental engineering, ecology, or related discipline;

• General professional experience (2.7.3): 7 years of experience in environmental assessments for energy or infrastructure projects;

• Specific professional experience (2.7.4): Experience with emission modelling and permitting (3 relevant projects).

- Regional experience (2.7.5): 3 years Ukrainian or European DH network design approaches

## Key Expert 7: Financial / Economic Analyst

Tasks:

• Development of CAPEX/OPEX model;

• Calculation of LCOH, LCOE, NPV, IRR, and payback period;

• Sensitivity analysis and financing-pathway assessment;

• Preparation of editable financial annexes.

Qualifications:

• Education/training (2.8.1): Master’s degree in economics, finance, or business administration;

• General professional experience (2.8.3): 7 years of experience in financial analysis of infrastructure projects;

• Specific professional experience (2.8.4): 5 years of experience in energy or utility modelling.

- Regional experience (2.8.5): 3 years Ukrainian or European DH network design approaches

## Key Expert 8: Independent QA / Peer Review Specialist

Tasks:

• Independent technical review of assumptions, calculations, scenario comparison, and final recommendations;

• Quality-control review of the final Pre-FS report and model.

Qualifications:

• Education/training (2.8.1): Master’s degree in economy, finance or relevant area;

• General professional experience (2.8.3): 5 years of relevant professional experience in design documentation development;

• Specific professional experience (2.8.4): Demonstrated experience in review of energy-sector feasibility studies (3 relevant projects).

- Regional experience (2.8.5): 3 years Ukrainian or European DH network design approaches.

# 5. Costing requirements

The contract shall be concluded as a contract for works at a lump-sum price. The expert days below are indicative estimates for orientation and budget justification. The Contractor remains responsible for completion and acceptance of the agreed deliverables regardless of the actual allocation of effort.

| Name | Position / cost item | Unit | Indicative quantity |
| --- | --- | --- | --- |
| Milestone 1 | Stage 1 – Inception, data review and baseline validation |  | 61 |
| Team leader | Team Leader / CHP Project Manager | expert day | 11 |
| Key expert 1 | CHP / Thermal Systems Engineer | expert day | 13 |
| Key expert 2 | WtE and Turbine Technology Specialist | expert day | 7 |
| Key expert 3 | District Heating Network / Hydraulics Specialist | expert day | 7 |
| Key expert 4 | RDF / Biomass Logistics Specialist | expert day | 8 |
| Key expert 5 | Electrical, Grid and SCADA Specialist | expert day | 3 |
| Key expert 6 | Environmental, BAT and E&S Specialist | expert day | 6 |
| Key expert 7 | Financial / Economic Analyst | expert day | 6 |
| Milestone 2 | Stage 2 – Comparative technical Pre-Feasibility Study |  | 242 |
| Team leader | Team Leader / CHP Project Manager | expert day | 14 |
| Key expert 1 | CHP / Thermal Systems Engineer | expert day | 50 |
| Key expert 2 | WtE and Turbine Technology Specialist | expert day | 40 |
| Key expert 3 | District Heating Network / Hydraulics Specialist | expert day | 37 |
| Key expert 4 | RDF / Biomass Logistics Specialist | expert day | 32 |
| Key expert 5 | Electrical, Grid and SCADA Specialist | expert day | 22 |
| Key expert 6 | Environmental, BAT and E&S Specialist | expert day | 20 |
| Key expert 7 | Financial / Economic Analyst | expert day | 17 |
| Key expert 8 | Independent QA / Peer Review Specialist | expert day | 10 |
| Milestone 3 | Stage 3 – Environmental, financial and implementation roadmap package |  | 8 |
| Team leader | Team Leader / CHP Project Manager | expert day | 6 |
| Key expert 6 | Environmental, BAT and E&S Specialist | expert day | 2 |
| Milestone 4 | Stage 4 – Stakeholder workshop, sector-expert presentation, revisions and final Pre-FS report |  | 1 |
| Team leader | Team Leader / CHP Project Manager | expert day | 1 |
|  | Total | expert day | 312 |
| Fixed travel budget |  |  | A budget is earmarked for travel within Ukraine. A fixed budget of UAH 51 510,00 is earmarked for settling travel expenses against evidence. This amount includes accommodation, travel costs (train, bus). Settlement is possible only until the budget is depleted. |

# 6. Inputs of GIZ or other actors

Available client-supplied data will be provided by GIZ and Cherkasyteplokomunenergo. The Contractor shall verify the completeness and quality of the data during Stage 1 and maintain a data-gap list. Where detailed data are unavailable, the Contractor shall use transparent assumptions and clearly identify the limitations.

Cherkasyteplokomunenergo and/or the City of Cherkasy will facilitate access to the relevant facilities and, subject to availability and prior coordination, provide suitable premises for the stakeholder workshop. The Contractor shall remain responsible for workshop preparation and facilitation, presentation and working materials, and other organisational arrangements necessary for conducting the online workshop.

# 7. Financial provisions

## 7.1 Contract value and anticipated payment schedule

The contract value shall be calculated according to the format of the bid. Payments shall be made against accepted work packages and deliverables.

## 7.2 Financial proposal

The total cost of the Contract shall be stated in UAH, including all direct and related expenses, taxes, fees, and VAT where applicable. All costs connected with contract implementation, including management, administration, travel, workshops, printing, and backstopping, shall be included in the lump-sum price. No additional budget lines shall be allowed after contract award unless agreed through a formal amendment.

## 7.3 Payment conditions

• The Contractor shall be paid 100% post-payment upon performance and acceptance of the relevant deliverables (WPs) in the agreed instalments on monthly basis

• All the payments shall be done exclusively in the national currency of Ukraine (UAH) by means of a bank transfer to the bank account of the Contractor;

• All activities shall be completed within the Contract timeframe;

• All the payments shall be done exclusively for the actually performed works/services (“up to”), on the ground of original invoices, acts of acceptance, service entry sheet (LERF), submitted in original form within 15 working days after their submission by the Contractor and acceptance by GIZ. The invoice is considered not accepted for payment in case of errors and/or provision of an incomplete package of documents for payment.

## 7.4 Requirements to the submission of the financial reporting documents

- Originals of Invoices, acts of acceptance, service entry sheet (LERF), etc. shall be submitted to the address of the GIZ Project together with the technical documents (reporting/ deliverables) and other financial supporting documents as and if stipulated by the Contract. If the prices in the contract are specified in foreign currency, the Contractor is obliged to indicate prices in all invoices and/or acts of acceptance in two currencies: in foreign currency and in the equivalent amount in UAH and to indicate applied currency exchange rate in accordance with Contract conditions.

- Each invoice and act of acceptance shall contain the Project Number, contract number and the percentage for cost split as follows:

- G-012485-014 - 90%

- G-010965-001 - 10%

- By submitting the Invoice the Contractor should indicate (in the invoice) whether the Contractor is a Single Tax Payer (e.g. 5%, 2%) or a VAT Payer (20%);

Act of acceptance for completed works /services standard template can be found here: https://www.giz.de/sites/default/files/media/els-document/2026-03/act-service-acceptance-final_0.doc

# 8. Other provisions

## 8.1 General

The Contract will be signed by the Parties in original form. Each Party agrees to provide the other Party with the original signed Contract and annexes. In this case, the Party that sent the Contract is responsible for the authenticity of the signatures of its authorized representatives and imprint of seal (if any).

The implementation of activities under present Contract can be started only after the Contact enters in force.

At the same time, the Period of Assignment, during which the Contractor is anticipated to work in order to perform the Contract, is defined by the Article 3 of this Contract.

Implementation of any activities under the present Contract /Supplement to this Contract (if any) can be started only after the Contact/Supplement (if any) enters in force and must take place only during the Period of Assignment.

Costs that are incurred outside the Period of Assignment are not eligible.

With signing of this contract, the parties are fully aware of the respective GIZ provisions, namely General terms and conditions of contract for supplying services and work on behalf of the Deutsche Gesellschaft fur Internationale Zusammenarbeit GmbH in Ukraine, Code of Conduct for Contractors of the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH published on the link Ukraine Tenders | GIZ (section “Terms of procurement of services”/ секція “Умови закупівель послуг”) and such provisions shall be binding on the parties as if stated in full in this agreement.

On the date of signing this Contract, the Contactor confirms that in accordance with the Tax Code of Ukraine, the Contractor is/is not (shall be specified at the time of contract preparation by the procurement unit responsible for contract preparation) a payer of value added tax under general conditions.

In case if on the date of Contract signing the Contractor is not registered as a VAT payer and during execution of the Contract the Contractor becomes registered as a VAT payer, and the given procurement of services/ works upon the Contract shall not be determined free from VAT,  the cost of the Contract remains unchanged and is to be considered with VAT.

The Contractor shall be responsible for all taxes and other payments according to the Ukrainian law. Taxes, levies or fees to the Government of Ukraine shall be paid by the Contractor.

Contact person from the GIZ side responsible for contract implementation and communication with the Contractor: Oleksii Snikhovskyi, +380 67 247 47 63, oleksii.snikhovskyi@giz.de.

The Contractor shall be solely responsible for all the security issues according to the own security concept during the implementation of the Contract. GIZ shall not be reliable and/or responsible for any damages and/or injuries occurred during the implementation of the Contract by any Person directly or indirectly involved into the implementation of the Contract and/or by any other third Person.

The Contractor is obliged to provide the originals of documents indicated in the special agreement at his own expense.

Additionally, the Contractor must:

- be a registered legal entity/private entrepreneur in Ukraine;

- not be on the sanctions list of Ukraine, the EU, the UN;

- ensure that the final beneficiaries/participants are not on the sanctions list of Ukraine, the EU, the UN;

- not be in the process of termination;

- not be registered on temporary occupied territories of Ukraine;

- not have the ultimate beneficial owner, member or participant (shareholder), having a share in the authorized capital of 10 percent or more, which is the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran, a citizen of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran except for those who live on the territory of Ukraine on legal grounds, or a legal entity created and registered in accordance with the legislation of the Russian Federation, the Republic of Belarus, the Islamic Republic of Iran.

GIZ reserves the right to verify the information at any time. The tenderer confirms that he agrees to the processing of personal data in accordance with the provisions of the EU General Data Protection Regulation (GDPR) and the Law of Ukraine "On the Protection of Personal Data" No. 2297-VI dated 01.06.2010.

## 8.2 VAT exemption – not applicable

VAT exemption is not applicable. The Contractor shall be responsible for all taxes and other payments according to Ukrainian law.

# 9. Outsourced processing of personal data

The performance of the contract may involve limited processing of personal data by the Contractor, such as names, positions, signatures and contact details of representatives participating in project coordination, workshops, reporting and contract administration. Such data shall be collected and processed solely to the extent necessary for performance of the Contract.

For such processing, the Contractor shall act as an independent data controller and shall comply with all applicable data-protection obligations, including applicable Ukrainian legislation and, where relevant, the principles of the General Data Protection Regulation (EU) 2016/679.

The Contractor shall apply the principles of lawfulness, purpose limitation, data minimisation, accuracy, storage limitation, transparency, integrity, confidentiality and accountability, and shall implement appropriate organisational and technical measures to protect personal data.

Where the Contractor processes personal data under the documented instructions of a GIZ partner, the relevant partner shall act as the data controller, and the Contractor shall process such data in accordance with those instructions and the applicable legal requirements.

The processing described above shall not constitute outsourced processing of personal data on behalf of GIZ unless such processing is explicitly agreed in writing and regulated by a separate data-processing arrangement.

# 10. Requirements to the format of the bid

## 10.1 Documents to be submitted

### 10.1.1 Technical bid

Tenderers must provide the following documents within technical bid:

• Work Plan and Schedule, including a Gantt chart and allocation of responsibilities;

• Team Composition and Organisational Chart;

• Methodology aligned with Chapter 3 and the technical assessment grid;

• Description of quality assurance, peer review, reporting, and stakeholder coordination;

• CVs of proposed experts, not exceeding 4 pages each, in English. They must clearly show the position and job the proposed person held in the reference project and for how long.

The structure of the technical bid must correspond to the structure of the ToRs. In particular, the detailed structure of the concept (Chapter 3) should be organised in accordance with the positively weighted criteria in the assessment grid (not with zero). The technical bid must be legible (font size 11 or larger) and clearly formulated. It must be drawn up in English.

The complete technical bid must not exceed 10 pages (excluding CVs). If one of the maximum page lengths is exceeded, the content appearing after the cut-off point will not be included in the assessment. External content (e.g. links to websites) will also not be considered.

The technical bid must not include any financial information such as daily fees or other payments. Otherwise, the bid may be disqualified.

### 10.1.2 Financial bid (Price schedule)

The financial bid shall include all costs associated with implementation and shall be submitted using the format provided in the tender documentation.

Financial bid (price schedule) must be signed and stamped if a stamp is used.

### 10.1.3 Registration documents of the tenderer

Registration documents shall be provided according to the tender documentation requirements.

# 12. Annexes

• Annex 1 – Technical Specifications for the development of a Pre-Feasibility Study (Pre-FS) for the conversion of a large boiler house in Cherkasy into a multi-fuel CHP plant and the interconnection of five boiler houses;

# Annex 1 – Technical Specifications for the development of a Pre-Feasibility Study (Pre-FS)

## A1. Project title

Technical re-equipment of a large boiler house into a multi-fuel CHP plant with a capacity of 15–88 MWth and up to 25 MWe, including the interconnection of heat networks of five boiler houses with the prospect of carbon neutrality.

## A2. Objective of the Pre-FS

The Pre-FS shall identify and compare technically, economically, environmentally, and institutionally viable configurations and shall recommend a preferred concept for the subsequent full Feasibility Study. The Pre-FS is an early-stage decision-support document and not a detailed design package.

## A3. Indicative project parameters

• Multi-fuel CHP capacity range: 15–88 MWth and up to 25 MWe;

• Potential fuels: wood chips and RDF, separately or in calculated proportions;

• Indicative RDF volume: approximately 120,000 t/year;

• Potential modular WtE configuration: two lines and one or two turbine options;

• Ring-main DH network interconnecting five boiler houses;

• Flue-gas cleaning: cyclones, bag filters, wet/dry scrubbers, and CEMS;

• Digitalisation: SCADA, load monitoring, forecasting, and operational optimisation;

• Potential future integration of heat pumps and solar-thermal solutions.

## A4. Minimum scenarios to be assessed

1. Baseline / reference scenario: continuation of the existing gas-based configuration with only essential rehabilitation;

2. Biomass-led CHP scenario with phased network integration;

3. Multi-fuel biomass + RDF CHP scenario, including comparison of one-turbine and two-turbine arrangements and phased implementation packages.

## A5. Required analysis

• Baseline technical and operational assessment;

• Heat-load validation and load-duration analysis;

• Preliminary heat and power balances for each scenario;

• Fuel-mix, moisture, quality, storage, preparation, and logistics assessment;

• Preliminary hydraulic analysis of ring-network alternatives, including comparison of design velocities and pipe concepts;

• Assessment of emissions-control configurations and EU-aligned BAT pathway;

• Preliminary CAPEX and OPEX estimates by major investment package;

• Financial and economic analysis: LCOH, LCOE, NPV, IRR, payback, sensitivity analysis;

• Climate and environmental effects: gas substitution, CO₂ reduction, methane avoidance, by-products, and safeguards;

• Risk assessment, financing pathway, phased roadmap, scope for the subsequent full FS, and a non-exhaustive market overview of relevant German, European and Ukrainian technologies, suppliers and products potentially applicable to the proposed investment, without pre-selection or recommendation of any specific supplier for future procurement.

## A6. Expected outputs

• Validated baseline and data-gap register;

• Comparative technical-options report;

• Editable financial model and investment-cost breakdown;

• Environmental and Climate Safeguards Summary;

• Implementation roadmap and recommended scope for the subsequent FS and design stages;

• Executive presentation, sector expert presentation and stakeholder-workshop package.

## A7. Explicit exclusions from this contract

• Detailed Design Documentation or Working Documentation;

• Construction drawings, IFC/BIM models, and equipment-installation drawings;

• Construction Bill of Quantities and cost estimates for State Expertise;

• Submission to State Expertise or support during State Expertise;

• Obtaining permits, approvals, or technical conditions on behalf of the municipality.

## A8. Initial data to be requested and reviewed

• Heat-generation and natural-gas consumption data for the large boiler house and the five connected boiler houses;

• Hourly or daily load profiles and seasonal heat-sales data;

• Available network schemes, route information, hydraulic data, pipe diameters, and pumping data;

• Land, building, and site-layout information;

• Waste-generation, RDF-quality, and waste-logistics information;

• Biomass availability, quality, moisture, seasonal supply, and transport-distance information;

• Existing emissions data and permits;

• Available electricity-grid connection and consumption data;

• Municipal strategies and relevant previous studies.

Annex 2 – Energy Report Template shall be provided separately by GIZ.